# NPS

PROJECT SUMMARY

| Cooperative Ecosystem Studies Unit Cooperative Agreement Modification |
| --- |
| FUNDING AGENCY: National Park Service |
| MODIFICATION NO.: [CESU info only] | COOPERATIVE AGREEMENT NO.: H1200-04-002 | FUNDING AMOUNT: $ 17,999.00 |
| INVESTIGATORS Contact Information: David Ostergren, Associate Professor, Environmental Sciences and Political Science, Northern Arizona University (928) 523-0701; david.ostergren@nau.edu/ Jonathan Nez, Graduate Student Political Science and Social and Behavioral Science, Northern Arizona University (928) 600-6889; jmn34@dana.ucc.nau.edu |
| PROJECT TITLE: Cultural Affiliation Consultations |
| EFFECTIVE DATES: 01/01/05 – 09/30/05 |
| PROJECT ABSTRACT: The goal of this project is to individually and collectively consult with 10 American Indian Tribes for the purpose of ensuring accurate completion of the Native American Graves Protection and Repatriation Act (NAGRPA) inventory for the Flagstaff Area National Monuments (Sunset Crater Volcano, Walnut Canyon, Wupatki National Monuments) and to proceed with publication of the Notice of Inventory Completion in the National Register to meet the 1994 requirements of NAGPRA. |
| Agency Representative: Ron Hiebert, NPS Research Coordinator CPCESU Northern Arizona University P.O. Box 5765 Flagstaff, AZ 86011-5765 Tel: (928) 523-0877 Fax: (928) 520-8223 Ron.Hiebert@nau.edu | Agency Administration Representative Lynell Wright Budget Assistant Intermountain Support Office Denver, CO 80225-0287 Tel: (303) 969-2654 Lynell_Wright@nps.gov | Principal Investigator: David Ostergren Associate Professor Environmental Sciences and Political Science Northern Arizona University Box 5694 Flagstaff, AZ 86011 Phone (928) 523-0701 David.Ostergren@nau.edu | Partner Admin. Contact: Cindy Judge Grants and Contracts Program Coordinator Northern Arizona University Box 4130 Flagstaff, AZ 86011-4130 phone (928) 523- 6917 Cindy.judge@nau.edu |
| List of Key Words: Native American Graves Protection and Repatriation Act (NAGPRA), consultation |
| Agency Manager/Technical Representative from National Park - Include contact information @ Specific Park: Jeri L. DeYoung Archeologist/ Curation and Compliance Program Manager 6400 N. Hwy 89 Flagstaff, AZ 86004 Phone (928) 526-1157 ext. 236 Fax (928) 526-4259 Jeri_DeYoung@nps.gov |
| Project Initiation: January 1, 2005 1st Progress Report: March 1, 2005 Invoice Payable up to 25% of total project cost March 31 1, 2005 2nd Progress Report: May 1, 2005 Invoice Payable up to 50% of total project cost May 30, 2005 3rd Progress Report: August 1, 2005 Invoice Payable up to 75% of total project cost August 31, 2005 4th Progress Report: September 1, 2005 Invoice Payable up to 100% of total project cost September 30, 2005 |
| This Modification is subject to all the provisions included in the Cooperative Agreement, dated 6/18/04. |

Attach any supporting material as necessary.