Final Report

Catalog Northern Arizona University Quaternary Sciences Program Specimens from Six National Park Service Units on the Colorado Plateau and Inventory Entire Collection from Sixteen NPS Colorado Plateau Units

Prepared by

Sandra L. Swift

and

Jim I. Mead

Submitted by

Jim I. Mead

Project PI

Northern Arizona University

Laboratory of Quaternary Paleontology

Center for Environmental Sciences and Education

June 2008

Work Accomplished

Work began on September 1, 2006.  Cataloger, Lisa Schaff was hired to help Quaternary Sciences Collections Manager, Sandy Swift, for several months of the project. A 100% inventory of the Colorado Plateau NPS unit collections was completed by means of physically checking the collections and cross-checking the catalog records in ANCS+. During this time, all un-cataloged specimens were identified, culled, and cataloged. Sandy Swift worked with FLAG Curator, Gwenn Gallenstein, to obtain park catalog numbers for new cataloging. All specimens not previously housed in archival containers were upgraded. All vials in packrat middens now include catalog number labels. Principle Investigator, Dr. James Mead, identified hundreds of previously unidentified specimens to their appropriate taxonomic level. The information was entered into ANCS+ by Sandy Swift. Updated tray and cabinet information was also entered into the location field of ANCS+ by Sandy Swift. Corrected databases were sent to the parks by Gwenn Gallenstein. All work ended in May 2008.

Unanticipated Changes

While the project originally included Hovenweep National Monument, the PI and Collections Manager found that there were in fact no Hovenweep collections in the QSP repository. The inventory established that a number of park units had duplicate numbers in the QSP collections. Sandy Swift corrected the problem, working with Gwenn Gallenstein to obtain new catalog numbers from parks. Loan paperwork between the QSP repository, parks, and sub-loan institutions was incomplete at best, so could not be resolved as a part of this project. Several insect specimens from GRCA and CANY could not be located and are thought to be part of an old loan to a researcher in Tucson. The original scope of work for this project stated that 450 specimens would be cataloged from six of the NPS units. Instead, over 800 new catalog records were created from 13 of the NPS units. May 2007 was the deadline set by the original scope of work. Due to the additional work required to complete the project, a no-cost extension was approved by the CESU in September 2007. The Flagstaff Area National Monuments provided an additional $4,940.00 directly to Swift and Mead for the extra work they did to complete the project.

New specimen numbers entered as part of this project are listed in Table 1.

Table 1.  Listing of the specimen numbers added to each park unit in ANCS+.

| NPS Unit | Total numbers | Specimen numbers |
| --- | --- | --- |
| ARCH | 4 | 3316-3319 |
| BLCA | 4 | 1791-1794 |
| BRCA | 1 | 8125 |
| CANY | 9 | 5562 23750 23799 23834 34468 35855 45903 45904 45906 |
| CARE | 230 | 5546-5775 |
| CEBR | 11 | 981-991 |
| COLM | 24 | 2217 3990-4009 5073-5075 |
| DINO | 22 | 15998-16091 |
| GLCA | 177 | 750 751 20063 22235-22236 22969-23066 23070-23146 |
| GRCA | 275 | 69777-69787 69790-69793 69795 69797-69818 69820 74605-74649 76515-76563 76336 93394-93493 93594-93635 93161 |
| PISP | 10 | 2588-2596* 2801* |
| WUPA | 48 | 25927-25965 27475 27514-27521 |
| ZION | 1 | 18276 |
| N=13 | N=816 | - |

* = changed numbers