PR Number:		R8213110120

Award Number:           P11AT10599 – NAU-403

Park/NPS Unit:	Grand Canyon National Park

Title of Project:	Ethnographic Research Data Management and NAGPRA Activities

Administered through the:

Colorado Plateau Cooperative Ecosystem Studies Unit Cooperative Agreement Number H1200-09-0005

Desert Southwest Cooperative Ecosystem Studies Unit Cooperative Agreement Number H1200-10-0001

Rocky Mountains Cooperative Ecosystem Studies Unit Cooperative Agreement Number H1200-09-0004

CESU Partner:    Northern Arizona University

Project Contacts

Principal Investigator:  Francis E. Smiley, Professor of Anthropology, Department of Anthropology, Northern Arizona University, P.O. Box 15200, Flagstaff, AZ 86011-5200, 928-607-0014, Francis.Smiley@nau.edu

Partner Administrative Contact: Cindy Judge, Grants and Contracts Administrator, Northern Arizona University, P.O. Box 4130, Flagstaff, AZ, 86011, 928-523-6917, cindy.judge@nau.edu

NPS Certified ATR:  Ellen Brennan, Cultural Program Manager, P.O. Box 129, Grand Canyon, AZ, 86023, 928-638-7742, (fax)928-638-7650, ellen_brennan@nps.gov

NPS Technical Expert (if appropriate): Ellen Brennan, Cultural Program Manager, P.O. Box 129, Grand Canyon, AZ, 86023, 928-638-7742, (fax)928-638-7650, ellen_brennan@nps.gov

Funding Information:

Amount Funded:  $4,680.00

Project Dates:

Start Date:	8/15/2011

Any Other Product Milestone Dates you need to include: Data entry completed by 5/30/2012.  Draft completion report June 30, 2012.  Final report August 30, 2012

End Date: September 30, 2012

PROJECT ABSTRACT:

This project focuses on research, data management, and archival tasks for ethnographic resources of the Grand Canyon as defined for the 11 traditionally associated tribes.