**PR Number: R8630N0009**

**Award Number:** **P12AC10480**

**Project Number: UNM-78**

**Park/NPS Unit:** CORO/CHIR

**Title of Project:** *FY12-FY13 Continuing Documentation of Archaeological Sites Impacted by Illegal Border Activities within the NPS Units of Coronado National Memorial (CORO) and Chiricahua National Monument*

**Administered through the:** Colorado Plateau Cooperative Ecosystem Studies Unit Cooperative Agreement Number H1200-09-0005

**CESU Partner:** University of New Mexico

**Project Contacts**

**Principal Investigator:** Dr. Bruce Huckell, Senior Research Coordinator, Maxwell Museum of Anthropology MSC01-1050, University of New Mexico, Albuquerque, NM 87131 Tel. (505) 277-4491 bhuckell@unm.edu

**Partner Administrative Contact:** Nancy Carr, Sponsored Research Project Specialist, 1700 Lomas NE, Ste 2200 / MSC01 1247, 1 University of New Mexico, Albuquerque, NM 87131-0001, Phone 505-277-9512, Fax 505-277-4185, Email [ncarr@unm.edu](mailto:ncarr@unm.edu)

**NPS Certified ATR:** Duane Hubbard, Archeologist, Southern Arizona Office, 2120 North Central Avenue-Suite 120, Phoenix, Arizona 85004, 602-571-4326, duane\_hubbard@nps.gov

**Funding Information:**

**Amount Funded: $78,200**

**NPS Account Numbers (amounts in parentheses):** $78,200 total - 8630-F4WS-E13 ($4,300), 1249-F3KV-E13 ($8,900), 8630-2012-PYC ($65,000)

**Fund Source (e.g., ONPS, FLREA, CRPP, CESU, etc.): ONPS and Fire**

NPS Funding

Is this funded using a reimbursable account number? If yes, IMR contracting needs a copy of the Interagency Agreement.

**Project Dates:**

**Start Date:**  May 15, 2012

Draft Final Report July 1, 2013

Final Report September 30, 2013

**End Date:** September 30, 2013

**PROJECT ABSTRACT:**

This project continues the recording and surficial, high precision mapping, recording and pedestrian survey of the lower grasslands in Coronado National Memorial and Chiricahua National Monument. These sites include a range of site types from historic ranching features to Archaic period lithic scatters. Due to the specific skill-set required in mapping and recording Archaic sites, a specialist in this time period will be required.

UNM staff will focus onreconnaissance and relocation of archaeological sites including identifying or verifying boundaries of sites. Using a variety of mapping methodologies, each site will be mapped to include identification of in-situ architecture and wall fall (mapping individual rocks) when appropriate. Any associated features will be mapped. High precision site mapping including all features and architectural remains, topography, site boundaries, drainages, significant flora, and bedrock may be required. Finally, mapping of UDA/DT features (trails/camps), trash piles, disturbance or vandalism will be conducted.