**PR Number:** R7230110007

**Award Number: P11AT10602 ASU-71**

**Park/NPS Unit:** Fort Union National Monument (FOUN)

**Project Title:** Museum Exhibit Plan, Fort Union National Monument Visitor Center

**Administered through the:** Colorado Plateau Cooperative Ecosystem Studies Unit Cooperative Agreement Number H1200-09-0005

**CPCESU Partner:** Arizona State University, School of Historical, Philosophical, and Religious Studies, Public History Program (ASU)

**Project Contacts:**

**Principal Investigator:** Nancy Dallett, ASU Public History Program, PO BOX 4302, Tempe, AZ 85287-4302; 480 965-9367; [Nancy.dallett@asu.edu](mailto:Nancy.dallett@asu.edu)

**Partner Administrative Contact*:*** Rena Saltzman, Research Advancement Administrator, Coor 3305 PO Box 876505, Tempe, AZ 85287-6505. Tel: (480) 965-2054, [rena.saltzman@asu.edu](mailto:rena.saltzman@asu.edu)

**Certified ATR**: Marie Frias Sauter; Superintendent Fort Union National Monument; P.O. Box 127 Watrous, NM 87753; (505) 425-8025; [marie\_frias@nps.gov](mailto:marie_frias@nps.gov)

**NPS Technical Expert:** Lorenzo Vigil, Chief of Interpretation, Fort Union NM;P.O. Box 127 Watrous, NM 87753; (505) 425-8025; [Lorenzo\_vigil@nps.gov](mailto:Lorenzo_vigil@nps.gov)

**Funding Information:**

**Funded Amount:** $134,471.00 Total Project cost

$43,388for Phase I Schematic Design

$46,185 for Phase II Design Development

$39,898 for Phase III Construction Documents

**Project Dates:**

**Start Date:** August 18, 2011

**Milestone Dates:**

Phase I SCHEMATIC DESIGN August 18, 2011 to November 30, 2011

Phase 2 DESIGN DEVELOPMENT December 1, 2011 to June 1, 2012

Phase 3 CONSTRUCTION DOCUMENTS June 2012 - August 2012

**End Date:** July 31, 2013

**PROJECT ABSTRACT:**

The purpose of this project is to assist NPS with development of a Final Exhibit Plan for the Fort Union National Monument Visitor Center, located in New Mexico (www.nps.gov/foun). The Final Exhibit Plan for Fort Union National Monument Visitor Center will include interpretive copy and museum exhibit resource database for all exhibits, production-ready graphic files, and final design, including construction drawings and all documentation necessary to fabricate and install exhibits. The planning team will consist of Arizona State University faculty and graduate students, Fort Union National Monument and the NPS Intermountain Regional staff. NPS will consult with affiliated tribes/pueblo nations and correspond with key stakeholders to advise them of the commencement of, and their desired input into, the exhibit rehabilitation project.