Sunset Crater Volcano National Monument

5-Year Trail Management Plan

National Park Service

U.S. Department of the Interior

A

A

An

An Internship Project of the Flagstaff National Monuments and the Northern Arizona University Department of Geography, Planning, and Recreation

November 30, 2011

Jake Case – Intern – Northern Arizona University

James Sell – Faculty Supervisor – Northern Arizona University

Matt Snider and Don Sharlow – National Park Service Supervisors

Mike Jones – Computer Mapping

This is a student internship project in which the Northern Arizona National Monuments staff at their Flagstaff office has been very generous in providing time, funding, and critical information to completion of the project.  Special thanks go to Diane Chung, Don Sharlow, and Matt Snider for their support from the Park Service side.  Thanks also go to Pam Foti and Nicole Harris for their help at the Department of Geography, Planning and Recreation at Northern Arizona University. Judy Bischoff of the Colorado Plateau Cooperative Ecosystem Studies Unit provided valuable critical support.  Mike Jones, of the Park Service, deserves special thanks for making the GIS maps. Joshua Kleinman provided valuable comments on the draft.  It is also worth mentioning that Karl Knapp, of California State Parks, and Kevin Meyer of the National Park Service, were crucial mentors in their conduct of a trail planning workshop in Winter 2011.

Table of Contents

Page

Executive Summary									8

Introduction										10

Sustainability and the National Parks

Purpose of the Sunset Crater Trail Management Plan

Existing Conditions									14

Threatened or Endangered Species

Cultural Resources

Current Management Planning

Trail Concept Planning								19

Concept Plan

Trail Sustainability and Design Parameters			    		22

Federal Trail Fundamentals

Managed Use and Designed Use

Trail Management Objectives Documentation

Trail Factor Triangle

User Characteristics

Environmental Site Conditions

Weather/Climate

Sustainable Design

Control Points

Accessibility Parameters							33

Grade and Cross Slope

Width

Sustainable Trails at Sunset Crater					   	34

Trail Factors

Sustainable Design for Lenox and Other Cinder Slopes

Park-Wide Sustainability Factors

Viewsheds							   		40

Viewsheds at Lenox Crater

Viewsheds on the Campground Connector Trail

Viewsheds on the Lenox-Lava Flow Connector Trail

Viewsheds on the Lava Loop Trail

Viewsheds on the Lava Flow Overlook

Interpretation									43

Existing Interpretive Opportunities

Interpretation on the Planned Lenox Crater LoopTrail

Interpretation on the Planned Campground Connector Trail

Signage Protocol

Lenox Crater Trail Rehabilitation Proposal					45

Alternative 1

Alternative 2

Alternative 3

Lenox Crater Loop Trail Proposal				   		48

Supporting Factors

Federal Trail Categorization

Site Conditions

Control Points

Trail Characteristics

Campground Connector Trail Proposal			   		52

Supporting Factors

Federal Trail Categorization

Site Conditions

Control Points

Trail Characteristics

Lenox – Lava Flow Connector Trail Proposal		   		56

Lava Flow Overlook Trail Proposal				   		59

Lava Loop Trail Proposal					  		61

Lava Flow Trail Maintenance Prescription			  		66

Equipment and Noise Mitigation Parameters				70

Materials								     		71

Summary	of Internship Report						     	72

References Cited								76

Appendix A – Trail Feature Diagrams				   		78

Appendix B – Trail Prescriptions				   		101

Appendix C – Cost Estimate Details				   		122

Appendix D – TMOs Form					 		132

Figures

Page

1. National Trail Management Class Matrix						25

2. Trail Factor Triangle									27

3. Flagging Used to Mark Location of a Trail Alignment				32

4. Summer Monsoon Engulfs O’Leary Peak						34

5. Entrenchment										36

6. Gullying on Trail										37

7. The San Francisco Peak from Lenox Crater						40

8. Views of O’Leary Peak, Darton Dome, and Bonito Lava Flow			41

9. Sunset Crater										41

10. Sunset Crater and Bonito Lava Flow							42

11. Small Interpretive Panel, Lava Flow Trail						43

12. A Large Interpretive Panel, Lava Flow Trail						43

13. Expansive Viewshed on Lenox Crater Summit					44

14. Existing Trail Sign									44

15. Mitigating a Large Berm								45

16. Lady’s Tresses										48

17. Basalt Rocks – Social Trail								52

18. Edge of Bonito Lava Flow								52

19. View of Road 545									53

20. Decommissioned Road								56

21. Views of the Bonito Lava Flow							59

22. Existing Social Trail on Bonito Lava Flow						61

23. Erosion on High Grade Cinder Slope							61

24. Lava Loop Trail										63

25. Wind Pocket Accelerating Erosion on Lava Flow Trail				66

26. Improperly Placed and Secured Bench, Lava Flow Trail				67

27. Concrete Undermining, Lava Flow Trail						67

Figures (cont.)

28. Improperly Secured Interpretive Panel						67

29. Trail Assessment Matrix								74

Maps

SUCR Trail Plan Reference Map								21

Viewsheds Reference Map									42

Planned Lenox Crater Loop Trail								47

Existing Lenox Crater Trail 								51

Planned Campground Connector Trail							55

Planned Lenox Lava Flow Connector Trail						58

Planned Lava Flow Overlook Trail							61

Planned Lava Loop Trail									65

Existing Lava Flow Trail									69

Sunset Crater National Monument Existing Conditions					136

Executive Summary

The goal of the Sunset Crater Trail Plan Internship project is to propose an integrated system of trails that are in compliance with the needs of the park and the recent federal directives on sustainable park management.  The student intern received training in sustainable trail planning and was able to work closely with NPS personnel to develop proposals and prescriptions for five trails in Sunset Crater National Monument.  The discussion is summarized as follows.

Sustainability in the National Parks.  The recent directives from the Bush and Obama administrations have tied sustainability to park management and design, as well as included a wide range of concepts, including climate-friendly park planning, to environmental management in the national parks.  Trail planning and design are placed within that larger context.  In fact trail design has incorporated sustainability concepts in planning trails that use local materials, minimize disruption of natural environments, reduce maintenance requirements, and in essence, “design with nature.”

Existing Conditions.  Sunset Crater National Monument is a volcanic park with the main sightseeing and interpretive features being the cinder cones (especially Sunset Crater) and the accompanying lava flows.  The lava and cinders bring special needs to consider in sustainable trail planning, including habitat for specialized plant and animal species, erosion potential, sensitivity to human impacts on cinders, and a potential, if somewhat remote, earthquake or eruptive hazard.  Sunset Crater itself has few cultural artifacts in the immediate vicinity, but is directly related to the ruins of the nearby Wupatki National Monument.  There is also a sacred significance to the site for the Native American nations in northern Arizona which needs to be considered.

Concept Planning.  The goals and objectives of the overall trail concept plan are to place the trail proposals in the larger planning context and to provide measurable objectives so that success of the plan can be monitored.  A summary of the goals and objectives follows.

Goal 1. Create an integrated trail system for Sunset Crater National Monument that encourages sustainable practices.

Objective 1.1.  Connect the Bonito Campground, Visitor Center, and Lava Flow Trail with a continuous set of trails so that hikers can walk from any of the three above sites to all others.

Objective 1.2 Encourage walking and bicycling in the park by providing an alternative to driving.

Goal 2. Use trail design principles to build more sustainable trails in the Park.

Objective 2.1 Design the trails to reduce environmental impacts.

Objective 2.2. Design the trails to reduce maintenance.

Goal 3.  Provide opportunities to educate and interpret sustainable trail design for the public.

Objective 3.1. Provide interpretive exhibits that discuss sustainable trail design at key points along the trails.

Trail Sustainability and Design Parameters. This section is a review of the current “state of the art” in trail design standards, with of view to incorporating sustainability.  It outlines federal trail fundamental concepts and classifications for managed use as well as introduces the sustainable “trail factor triangle” proposed by Kevin Meyer.  In addition, it discusses integration of the ADA requirements into sustainable trail design.

Sustainable Trails at Sunset Crater.  The concepts discussed above were incorporated in specific trail proposals based upon field assessment to create an overall set of five proposed new trails:

1. Lenox Crater Loop Trail (and obliteration of the existing unsustainable trail)

2. Campground Connector Trail linking the Bonito Campground to the sunset Crater trail system.

3.  Lenox-Lava Flow Connector Trail

4.  Lava Flow Overlook Trail

5.  Lava Loop Trail

In addition, the existing Lava Flow Trail at the base of Sunset Crater was evaluated for maintenance needs and improvements have been prescribed.

Specific discussions of conditions, viewsheds, and interpretive opportunities were presented for the proposed trails.

Trail Prescriptions and Cost Estimates.  A detailed set of trail prescriptions were made based upon field assessment.  These prescriptions were given cost estimates based upon software developed by Karl Knapp of the California State Parks system.

Introduction

The purpose of this project is to propose new trails to key areas in the Sunset Crater National Monument that can serve the recent federal directives and guidelines on sustainability and climate friendly park management.  Trail design in a volcanic area has special characteristics and the proposals in this document are meant to help develop trails that are sustainable on the micro-level, but also serve the larger needs of climate friendly planning.  It is clear that the needs of environmental sustainability are driving a new set of changes in the National Park Service that may be the most significant in the next one hundred years of Park Service existence.  The context in which all park management is conducted will require a new set of operational and planning principles that incorporate sustainability.  It is hoped that this project will contribute in a small way toward that change.

Sustainability and the National Parks

The mission of the National Park Service is as follows:

…the fundamental purpose of the said parks, monuments, and reservations, which purpose is to conserve the scenery and the natural and historic objects and the wild life therein and to provide for the enjoyment of the same in such manner and by such means as will leave them unimpaired for the enjoyment of future generations (Congress of the United States, National Park Service Organic Act of 1916).

This Organic Act places the National Park Service permanently in the business of sustainable planning, whose general purpose is to ensure that future generations enjoy the same conditions experienced by people today.  The question faced by the Park Service, as well as the other federal agencies, is how to position the national parks and monuments to protect themselves against threats to valued natural and cultural resources and to provide examples of sustainable planning, not just for preservation of natural and cultural resources, but as an example for all.

The primary function of preserving valued national parks, monuments, and lands – unimpaired – is central to the NPS mission, but has been complicated by “external” threats to the parks and monuments resources.  This expanded set of threats, such as climate change from greenhouse gases, pollution from outside the parks, wear and tear from increasingly large numbers of park visitors, encroachment of land uses from outside park boundaries, force NPS personnel to expand their range of operations beyond the park boundaries – both physical and conceptual.

This expanded role of the parks in promoting and building sustainably is seen in Executive Orders EO13514 and EO13423, which declare that the policy of the federal government and its agencies is to conduct their activities in a sustainable manner, and, as noted in EO 13514,

In order to create a clean energy economy that will increase our Nation’s prosperity, promote energy security, protect the interests of taxpayers, and safeguard the health of our environment, the Federal Government must lead by example. It is therefore the policy of the United States that Federal agencies shall increase energy efficiency; measure, report, and reduce their greenhouse gas emissions from direct and indirect activities; conserve and protect water resources through efficiency, reuse, and stormwater management; eliminate waste, recycle, and prevent pollution; leverage agency acquisitions to foster markets for sustainable technologies and environmentally preferable materials, products, and services; design, construct, maintain, and operate high performance sustainable buildings in sustainable locations; strengthen the vitality and livability of the communities in which Federal facilities are located; and inform Federal employees about and involve them in the achievement of these goals (EO-13514, 2009, 3).

In essence, the Park Service is required to consider not simply the immediate environmental impacts of new construction, but also indirect impacts on such diverse elements as greenhouse gas emissions, regional community wellbeing, and even local markets for sustainable products and technologies.

This mandate has been supplemented with a set of guidelines newly issued for federal landscaping (United States Botanic Garden, 2011Guidance for Federal Agencies on Sustainable Practices for Designed Landscapes).  These guidelines include such aspects as:

Use an integrated site development process

Preserve areas with permeable soils

Protect and conserve existing landscapes, forests and wilderness areas

Minimize site disturbance

Preserve threatened and endangered species and their habitats

Improve linkages and connections to surrounding destinations and neighborhoods

There are other guidelines as well (see pp.6-8), but the above seem most appropriate to trail planning.  The major point here is that there is a new context for sustainable planning and the National Park Service is obligated to work within that context.

In this context, Sunset Crater National Monument offers a distinctive laboratory for planning and design in the new context of sustainable operations.  At present it has one improved trail that is partly ADA compliant, and has a need for building a complete trail system to suit needs for sustainability.  At present, the proportion of paved road to trail is over 25 to one.  This is an opportunity to examine sustainable trail design concepts, plan an integrated trail system, provide for enhanced visitor experience and interpretation, and integrate the plans with the other local agencies, especially the United States Forest Service and Flagstaff Urban Trail Systems.

Sustainability is not well defined as yet, since it is a concept in the making.  The actions of the Park Service will to a great extent help define what sustainability is because the concept is integral to its mission of preservation “for all time.” That is in the same spirit as the Brundtland Commission’s 1986 definition of sustainable development:  "…development which meets the needs of current generations without compromising the ability of future generations to meet their own needs.”

We can define some dimensions of sustainability as they relate to park trails, specifically Sunset Crater:

1. Use of alternative transportation – hiking and bicycling should be emphasized over driving, or at least have equivalent status.  One issue that is very important in this regard is the need to separate trails from roads as much as possible.  This separation is shown as effective in the Flagstaff Urban Trail System (FUTS), providing uncongested, safe routes for walkers and bicyclists.

2. Use of local, natural materials – to reduce fossil fuel use and design in ways appropriate to the existing natural environment of each park.  Attention should be paid to the concept of embodied energy in manufacturing and transportation of materials. For example, it is often taken as a given that redwood is a superior wood for trail and other building because of its durability.  However, when one considers the distance traveled from the redwood logging areas in northern California to Flagstaff, truck transport over an 1100 mile distance can use a large amount of fossil fuel energy, with large amounts of greenhouse gas emissions.  Keeping that in mind, the construction of trails in SUCR will use locally procured juniper or cedar as the more sustainable alternative.

3. Design with nature – use native materials, minimize impact in construction, and take advantage of local terrain to reduce environmental impacts.

4. Plan for multiple publics, including people who are mobility or otherwise impaired – while not everyone can go everywhere, it is possible to provide a reasonable experience of the environment for everyone.

5. Sustainability should be a topic of interpretation as much as the natural environment. All sustainable design aspects should be a matter of interpretation along the trails..

Purpose of the Sunset Crater Trail Management Plan

Trails provide a valuable means for visitors to intimately enjoy the unique and fascinating attractions offered within the park, and ultimately carry out the mission of the National Park Service.  The purpose of the Sunset Crater Volcano National Monument 5-Year Trail Management Plan is to:

- Outline sustainable trail designs and other key trail management concepts

- Describe sustainable trail design concepts in specific yet comprehensible terms that will allow the reader to easily understand the reasoning behind design and management choices

- Apply these concepts to a series of trail maintenance, re-design and new construction proposals

- Enhance visitor satisfaction and safety, increase recreation opportunities, and utilize interpretive opportunities to inform and educate visitors of the importance of preserving natural and cultural resources

- Emphasize the benefits of a fully integrated and interconnected trail system that will connect major parking areas and visitor services and allow visitors to hike multiple park trails from one access point

As described in the Existing Conditions section following, the park receives substantial visitor traffic due to its proximity to the Flagstaff population base, a popular Forest Service campground (Bonito Campground) and the prominent US Highway 89 and Interstate 40 traffic corridors.  As such, the current 1.35 miles of official trail within the park are inadequate for the park’s current and future recreation needs.  The trail maintenance, re-design and new construction proposals will allow for increased non-motorized recreation opportunities that will better serve the needs of the park and improve connectivity between Sunset Crater and the Bonito Campground.

Proposed actions may have alternative actions listed when deemed appropriate.  This plan will indicate support for alternatives that best serve to maintain sustainable design qualities and promote user satisfaction.  Alternatives may be included in the proposed actions that are not supported by the trail plan but are none the less viable options should management deem them to be advantageous for other reasons.

Existing Conditions

The existing conditions will be discussed in general as they relate to an overall concept for planning.  Later more specific conditions will be examined as they directly affect trail planning (for example the cinder surface of the volcanoes).

Sunset Crater Volcano National Monument (SUCR) consists of 3,040 acres of pristine volcanic terrain within the San Francisco Volcanic Field of northern Arizona. Its primary reasons for National Monument status consist of the volcanic features of Sunset Crater and some rather young lava flows. The Sunset Crater Unit also ties closely with the Wupatki National Monument as a related cultural feature.

SUCR is located approximately 15 miles north of Flagstaff, a city of moderate size (c. 60,000 population) with a substantial tourism sector that provides a strong visitor base for the park.  The park is also located along the corridor of US Highway 89, a major regional artery that serves as an important route between many of the region’s natural attractions such as Sedona, the Grand Canyon, Lake Powell and many of the Utah State and National Parks. Interstate 40 (Route 66), about 15 miles south, is also a primary east-west highway for the continental USA.   As a result of its prime location near major highways it is an area of heavy tourist traffic; the average annual visitation for the monument is 201,775 over the years 2006-2010 (National Park Service, 2011).

The climate is best described as cool, semi-arid. Annual precipitation amounts to about 16-17 inches (400-425 mm), with perhaps 1/3 of that in the form of snow.  The “monsoon” summer months of July and August have the most rain, which falls sporadically in short intense cloudbursts, usually in the afternoon.  Spring, winter, and fall rain comes from large mid-latitude storms that usually drop steady rains over a period of several days.  The low amount of rainfall barely supports an arid-adapted ponderosa pine or pinyon pine forest (generally it takes about 20 inches per year to support any sort of forest).  This makes the region of the park very vulnerable to climate warming.  For trail planning purposes, global warming can cause an increase in summer cloudbursts which can threaten to erode trails and their surrounding areas, as well as weaken the ecological viability of the forests by increased drought (Western Regional Climate Center, 2011).

The San Francisco Volcanic Field is a relatively young volcanic area (about 6 million years of age).  It exists over a “hot spot” in the interior of the North American plate.  As a hot spot, volcanoes erupt as the plate passes over the hot spot.  In this case the oldest volcanoes are in the west near Williams, and Sunset Crater, farthest east, is the youngest.  The major implication here is that seismic activity and further eruptions also require consideration.  Thornberry-Ehrlich (2005) notes that

Although there has been no significant volcanic activity in the San Francisco Volcanic Field for nearly 1,000 years, it is likely that eruptions will continue in the

future. The average interval between large eruptions is several thousand years. Predicting future events is difficult (10).

As far as environmental conditions exist, that means that eruptive events must be considered as a possibility (however remote), and low-level seismicity (90 earthquakes of Richter level less than 3 have occurred from May 15-October 15, 2011,according to the Arizona Earthquake Information Center) is a condition that must be considered in trail planning.  No one can predict or plan for large earthquakes, so long term land use planning and monitoring should be done to prepare for such events. This involves location of permanent structures away from the immediate hazard zone and constant seismic monitoring.  There is a seismograph located near the Sunset Crater rim to provide some warning (Thornberry-Ehrlich, 2005). For immediate trail planning needs, the likely probability of earthquakes of Richter 3 or less, with an occasional 4, should cause some slumping, soil creep, and small rockslides (Thornberry-Ehrlich,2005, pp. 21-22), which can be mitigated by maintenance..

Sunset Crater itself is the youngest volcano in the San Francisco Volcanic Field, a cinder cone that erupted approximately 1,000 years ago (the eruptive sequence extended from about 1064 to 1180 CE).  Associated with the Sunset Crater eruption are the Bonito and Kana-a Lava Flows, the jagged remnants of a smoldering flood that poured out of the volcano’s base.  A smaller cinder cone, Lenox Crater, is also located within the park, although Sunset is the better preserved.  As a cinder cone, Sunset Crater is susceptible to erosion from water runoff and hiking, and so the cone itself has been closed to hikers since 1973 (Sunset Crater National Monument, 2002; United States Geological Survey.  2002).

Cinder cones form from small scale eruption of lavas rich in gas.  The lava spews out of the crater, cools in the air in the form of small fragments, then falls in the area near to the crater in a circular pattern.  Over time this circle grows to form a moderately high cone of cinders (Sunset Crater is about 1000 feet – 305 meters – above the local valley floor).  The cinders are small, averaging about 4mm in diameter (Thornberry-Ehrlich, 2005) and intermixed with finer fragments of ash as well as a few larger “bombs.” This material is not consolidated and so is highly susceptible to erosion.

…slumps and other forms of slope failure are common for volcanic units. Loosely packed or unconsolidated materials are especially vulnerable to failure when exposed on a slope. Precipitation necessary to produce flash flooding at Sunset Crater Volcano loosens rock and soil on slopes lacking stabilizing plant and tree roots. Rock and soil suddenly saturated with water slip down the slope to cause a slump or flow (Thornberry-Ehrlich, 2005, 112).

The Bonito and Kana’a Lava Flows constitute a unique and expansive volcanic feature that includes a large portion of the park’s land, running roughly northwest and north- east respectively.  The flows are defined by black, angular basalt lava rock (known to geologists as a’a) that creates a very rocky rugged landscape.  The Bonito Lava Flow is also a scenic attraction that is of incredible interest to park visitors.  Trail construction within the park requires special care due to the ruggedness of the lava and the loose nature of the cinders that are also prominent in the area. Related features for interpretation include xenoliths, lava tubes, volcanic bombs, and fumarole deposits (Thornberry-Ehrlich, 2005).  In all, the unique, young, volcanic landscape offers many opportunities for interpretation as well as some challenges in building trails on cinder slopes and lava flows.

This 11th century eruptive sequence is closely tied to the agricultural productivity that allowed the culture of the Ancient Pueblo (Sinagua) people to thrive nearby in what is now Wupatki National Monument.  While the cinder/ash environment immediately around Sunset Crater is not fertile, the Sinagua (sin=without, agua=water) found the ashfall north of the volcanic field was an excellent mulch and could support agriculture.  So while Sunset Crater National Monument is primarily created to preserve the volcanic habitat, there is also a scattering of archaeological sites nearby (Sunset Crater National Monument, 2002; National Park Service, 2007)

The volcanic landscape constitute as number of considerations in trail planning, as well as for planning in general.  Major earthquakes are very unlikely but minor ones could contribute to slumping and soil creep.  Trails over cinders may be relatively easy to build, but their surface will be loose and easily eroded, so much care must be spent on keeping trail slope and width at sustainable levels.  The lava fields will be hard to cut trails and will most likely take the most time and expense.  It must be kept in mind that there are cultural artifacts as well as cultural meaning for the tribes traditionally associated with the monument.

The monument itself is surrounded by the Coconino National Forest, which is a ponderosa and pinyon pine forest, typical of semi-arid forests in the uplands of Arizona.  Located next to the monument visitor center is the Coconino National Forest’s Bonito Campground, a popular summer recreation area containing 44 sites with RV access.  This campground serves as the primary developed camping area for monument visitors.

The official trails in the park are concentrated near Sunset and Lenox Craters.  The Lava Flow Trail is a 1 mile interpretive loop that leads visitors on a geologic tour through the Bonito Lava Flow at the base of Sunset Crater. The trail to the crater rim is closed to foot traffic because of high erosion potential on the cinders (it has been closed since 1973 and the scar is still visible).  Approximately 0.3 miles of the Lava Flow Trail is paved and is compliant with Americans with Disabilities Act (ADA) Standards for Accessible Design.  The Lenox Crater Trail climbs the small cinder cone to the west of Sunset Crater, reaching a summit of 7,252 feet above sea level.  At the summit, visitors are greeted with a commanding view of the San Francisco Peaks, including Humphrey’s Peak, the highest point in Arizona at 12,633 feet.

Threatened or Endangered Species

While the list of threatened or endangered species in northern Arizona is somewhat large, those whose habitats are in or around volcanic cinder or lava fields are more limited.  The surrounding forests provide hunting, wintering, and nesting areas for a number of birds of prey (golden eagle, goshawk, Mexican spotted owl) as well as pronghorn antelope.  Aside from the Mexican spotted owl, the other animals are not on the endangered species list, but they are listed as “species of concern” or of public interest in the latest park management plan EIS (2002, 86, 137-39).  All of these could have nesting or wintering sites near the proposed trails and thus could be affected by the trail construction process. The 2002 EIS reports nesting sites for northern goshawk, Mexican spotted owl, and golden eagle at O’Leary Peak, north of Sunset Crater, but none at the Crater itself (p.138}.  The pronghorn antelope herd west of Wupakti has used the Bonito Park area as a fawning ground but again there is no recorded observation of them at the base of Sunset Crater (p. 88).  While there is no documentation of these animals nesting in the Sunset Crater-lava flow areas, an inventory of potential environmental effects must be sensitive to the possibility of these animals in the area.      .

In terms of plant species in the cinder/lava fields, there are the Sunset Crater penstemon (Penstemon clutei), the saw phacelia (Phacelia serrata), and Welsh’s scorpionweed (Phacelia welshii).also known as lady’s tresses (Sunset Crater National Monument, 2002).  These are plants who live on cinder habitats and must be treated in the trail design, usually by salvage procedures.

Habitat zones in the area that can be affected included “islands” of pioneering vegetation in both cinder fields and lava flows that “float” on the lava or cinder surfaces and, because of weak soil formation, can be easily disturbed by construction or use.  Another set of small critical habitats is formed at the toes of the lava flows, where water can flow out from under the volcanic material and create moist microhabitats.  These are habitats that are prime study areas for ecosystem recovery after volcanic eruptions and should be protected when trails are built (Sunset Crater National Monument, 2002, 89).

Cultural Resources

Sunset Crater is considered to be a Traditional Cultural Property (TCP) with special meaning and uses, as identified by several of the Native American Nations.in the area.  The Hopi, Zuni, and Navajo Nations have each identified resources in the park of sacred or ceremonial significance, including the cinder cones, lava flows, the ice cave and forms of vegetation.  The eagle population is sacred to the Hopi (Sunset Crater National Monument, 2002, p. 80). Archaeological sites have not been identified in the proposed trail corridors, however a complete survey will be conducted prior to any undertaking.

Current Management Planning

For many visitors, Sunset Crater Volcano is largely a drive-through experience, often in conjunction with a visit to Wupatki National Monument. A typical visit includes stops at the visitor center, one or two roadside pullouts, and the Lava Flow Trail (Sunset Crater National Monument, 2002).

By the 1950s and 60s Sunset Crater developed into a typical drive-through park, supporting automobile-based tourism with a 35 mile loop drive through Sunset Crater and Wupatki National Monuments, including roadside pull-outs and a short interpretive trail at the base of Sunset Crater itself.   About three miles of paved road (R545) are contained within the Sunset Crater National Monument itself, and the proposed trails will surround much of that road with a network of trails that will provide a viable pedestrian alternative to driving.

Trail Concept Planning

The purpose of the preceding discussion is to place the trail plan within the context of park planning on the national and local level.  The direction of policy is toward, not simply making parks more sustainable, but making their efforts more transparent and open to education and interpretation.

The basic idea of a concept plan is to present general goals and objectives which allow the results of the more direct activities (the trails) to be measured.  The goals are generalized strategies and the objectives are sets of actions that produce measurable results.  The objectives are written in such a way as to develop tools for monitoring effects of the plan, such as counts of hikers, miles of trails constructed, cost of maintenance.   For the purposes of this plan, the concepts will provide an overall context in which the trail proposals can be placed.

Concept Plan

Goal 1. Create an integrated trail system for Sunset Crater National Monument that encourages sustainable practices.

Objective 1.1.  Connect the Bonito Campground, Visitor Center, and Lava Flow Trail with a continuous set of trails so that hikers can walk from any of the three above sites to all others.  The existence of the connected system of trails between the three points will constitute achievement of the objective.

Objective 1.2 Encourage walking and bicycling in the park by providing an alternative to driving.  This objective can be measured by observing the ratio of trail users to automobile users.  Over time, it would be expected that there will be a higher proportion of hiking and bicycle use compared to vehicles.

Goal 2. Use trail design principles to build more sustainable trails in the Park.

Objective 2.1 Design the trails to reduce environmental impacts including surrounding vegetation, wildlife, volcanic surface and cultural resources.

Objective 2.2. Design the trails to reduce maintenance.  A trail built using sustainable trail design should also require fewer resources put into maintenance.

Goal 3.  Provide opportunities to educate and interpret sustainable trail design for the public.

Objective 3.1. Provide interpretive exhibits that discuss sustainable trail design at key points along the trails.

Trail Sustainability and Design Parameters

Federal Trail Fundamentals

The Federal Trail Fundamentals establish guidelines for federal agencies such as the National Park Service to properly manage their trails.  Trails within Sunset Crater Volcano National Monument will be designed and managed utilizing the four Federal Trail Fundamentals, which are:

- Trail Type

- Trail Class

- Managed Use

- Designed Use

These fundamentals closely intertwine with the Trail Factor Triangle, which will be discussed later in this section.  The Federal Trail Fundamentals can be followed in conjunction with the triangle to successfully determine the best design and management plan for a given trail (for further reference see National Park Service, 2008; United States Forest Service. 2011, upon which this section is based}.  The terms used have a precise meaning which is found in the glossary of the Trail Fundamentals Manual (United States Forest Service. 2011, 73-77).

Trail Type

The Federal Trail Fundamentals define trail type as the predominant trail surface and general mode of travel accommodated by a trail.  The three trail type categories are:

- Standard/Terra Trail: A trail that has a surface consisting predominantly of the ground and that is designed and managed to accommodate use on that surface.

- Snow Trail: A trail that has a surface consisting predominantly of snow or ice and that is designed and managed to accommodate use on that surface.

- Water Trail: A trail that has a surface consisting predominantly of water (but may include land-based portages) and that is designed and managed to accommodate use on that surface.

The only trail type to be utilized at SUCR is the Standard/Terra Trail.  During the winter, visitors sometimes use cross-country skis or snow-shoes, however the vast majority of use remains in the Standard/Terra Trail category, so the Snow Trail category will not be used at this park.

Trail Class

The Federal Trail Fundamentals define trail class as the prescribed scale for development of a trail, representing its intended design, use and management standards.  Each trail is to be assigned one of the five trail classes, which range from “primitive” to “fully developed”.  The designated trail class should reflect management’s intended direction for the trail, which may or may not reflect the current condition of the trail.  The parameters for each trail class are detailed in the National Trail Management Class Matrix located on the following page.

Managed Use and Designed Use

The Federal Trail Fundamentals define managed use as ”a mode of travel that is actively managed and appropriate on a trail, based on its design and management.” (United States Forest Service, 2011, 75)   Managed use indicates management intent to accommodate a specific use, and a trail can have multiple managed uses.  Also, managed uses may not necessarily encompass all of the allowed uses for a trail.  However, within the bounds of SUCR, a trail’s managed uses will typically cover all of the allowed uses for that trail.  There is a direct relationship between trail class and managed use, and one cannot be determined without considering the other.

Designed use is defined by the Federal Trail Fundamentals as the managed use of a trail that requires the most demanding design, construction and maintenance parameters, in conjunction with the applicable trail class, determines which Design Parameters or technical specifications will apply to the trail.  While a trail may have numerous allowed and managed uses, only one managed use will be identified as designed use for a trail.

Twelve types of uses are identified within the Federal Trail Fundamentals, which include:

Hiker / Pedestrian			Pack and Saddle

Bicycle				Motorcycle

All Terrain Vehicle			Four Wheel Drive Vehicles > 50” in width

Cross-Country Ski			Dog Sled

Snowshoe				Snowmobile

Motorized Watercraft		Non-Motorized Watercraft

Only two of the above listed uses will be allowed within the park, which are hiker/pedestrian use and bicycle use.

Figure 1.  National Trail Management Class Matrix

| Trail Attributes | Class 1 Primitive/ Underdeveloped | Class 2 Simple/Minor Development | Class 3 Developed/Improved | Class 4 Highly Developed | Class 5 Fully Developed |
| --- | --- | --- | --- | --- | --- |
| Tread and Traffic Flow | -Tread Intermittent and often indistinct -May require route finding -Single lane with no allowances constructed for passing -Predominantly native materials | -Tread continuous and iscernible, but narrow and rough -Single lane with minor allowances constructed for passing -Typically native materials | -Tread continuous and obvious -Single lane with allowances constructed for passing where required by traffic volumes in areas with no reasonable passing opportunities available -Native or imported materials | -Tread wide and smooth with few irregularities -Single lane with allowances constructed for passing where required by traffic volumes in areas with no reasonable passing opportunities available -Native or imported materials May be hardened | -Tread wide, firm, stable and generally uniform -Single lane, with frequent turnouts where traffic volumes are low to moderate -Double lane where traffic volumes are moderate to high Commonly hardened with asphalt or other imported material |
| Obstacles | -Obstacles common, naturally occurring, often substantial and intended to provide increased challenge -Narrow passages; brush, steep grades, rocks and logs present | -Obstacles may be common, substantial and intended to provide increased challenge -Blockages cleared to define route or protect resources -Vegetation may encroach onto trail corridor | -Obstacles may be present, but not substantial or intended to provide challenge -Vegetation cleared outside of trail corridor | -Obstacles infrequent and insubstantial Vegetation cleared outside of trail corridor | -Obstacles not present -Grades typically less than 8% |
| Constructed Features and Trail Elements | -Structures minimal to non-existent -Drainage typically provided without structures -Natural fords -Typically no bridges | -Structures of limited size, scale and quantity; typically constructed of native materials -Structures adequate to protect trail infrastructure and resources -Natural fords -Bridges needed for resource protection and appropriate access | -Structures may be common and substantial; constructed of native or imported materials -Natural or constructed fords -Bridges as needed for resource protection and appropriate access | -Structures frequent and substantial; typically constructed of imported materials -Constructed or natural fords -Bridges as needed for resource protection or user convenience -Trailside amenities may be present | -Structures frequent or continuous; typically constructed of imported materials -May include bridges, boardwalks, curbs, handrails, trailside amenities and similar features |
| Trail Attributes | Class 1 Primitive/ Underdeveloped | Class 2 Simple/Minor Development | Class 3 Developed/Improved | Class 4 Highly Developed | Class 5 Fully Developed |
| Signs | -Route identification signing limited to junctions -Route markers present when trail location is not evident -Regulatory and resource protection signing infrequent -Destination signing, unless required, generally not present -Information and interpretive signs generally not present | -Route identification signing limited to junctions -Route markers present when trail location is not evident -Regulatory and resource protection signing infrequent -Destination signing infrequent outside of wilderness areas, generally not present in wilderness areas -Information and interpretive signs uncommon | -Route identification signing at junctions as needed for user reassurance -Route markers as needed for user reassurance -Regulatory and resource protection signing may be common -Destination signing likely outside of wilderness, generally not present in wilderness areas -Information and interpretive signs may be present outside of wilderness | -Route identification signing at junctions as needed for user reassurance -Route markers as needed for user reassurance -Regulatory and resource protection signing common -Destination signing common outside of wilderness, generally not present in wilderness areas -Information and interpretive signs may be common outside of wilderness -Accessibility information likely displayed at trailhead | -Route identification signing at junctions for user reassurance -Route markers as needed for user reassurance -Regulatory and resource protection signing common -Destination signing common -Information and interpretive signs common -Accessibility information likely displayed at trailhead |
| Typical Recreation Environments and Experience | -Natural and unmodified | -Natural and essentially unmodified | -Natural and primarily unmodified | -May be modified | -May be highly modified |

Trail Management Objectives Documentation

In order to ensure proper communication between the monument and any other entities involved in the trail planning, construction or maintenance processes (such as contracted trail crews), SUCR will maintain a Trail Management Objectives (TMO) form for all proposed and existing trails at SUCR.  The TMO form allows the monument to maintain documentation of the class, use, design and maintenance standards and specifications determined for a trail.  The TMO form template for the park is provided in Appendix D.

Figure 2. Trail Factor Triangle

Trail Factor Triangle

The Trail Factor Triangle sets forth the essential factors that influence the design of a trail.  There are three factor categories that represent the triangle’s three points: User Characteristics, Environmental Site Conditions, and Climate/Weather.  Within each factor category are the specific factors that must be considered.  The six Sustainable Design Guidelines are also listed on the Trail Factor Triangle, which should be followed throughout the course of any trail project to ensure that the trail minimizes its impact on the environment while maximizing its longevity. (Knapp and Meyer, 2011; Meyer 2011)

User Characteristics

Four factors comprise the User Characteristics corner of the Trail Factor Triangle: type, season, volume, intensity.  The User Characteristics of a trail are used to determine the trail tread width and clearing width, durability requirements, frequency of maintenance, or any other specific need required by a trail’s users.

- User Type is well covered in the Federal Trail Fundamentals in the above section.  Major types include: hiker/pedestrian, pack and saddle, bicycle, and off-highway vehicle.  Each of these user types can have different needs and effects on a trail, such as intensity of use, which is described in factor number 4 below.

- Season refers to what times of year a trail will see use, or if certain times of year receive exceedingly heavy use.

- Volume refers to the number of visitors that use a trail during a given amount of time.  Trails that see a high volume of use must be more developed and see more frequent maintenance than lower volume trails.

- Intensity of use is determined by considering both the User Type and Volume factors.  Pedestrian/hikers, cross-country skiers and snow-shoers are considered to be low intensity use types while others (such as bicyclists) are considered high intensity use types.  However, a high volume of pedestrian/hikers may have a higher intensity than a low volume of bicyclists or other users.

Environmental Site Conditions

Seven factors comprise the Environmental Site Conditions corner of the Trail Factor Triangle: slope, aspect, elevation, soils, hydrology, biology and cultural resources.  Environmental Site Conditions influence almost all aspects of trail design, including optimal trail corridor and alignment placement, maximum sustainable grade, and design grade.

- Slope refers to the steepness of the terrain on which trail will be built, and can influence items such as trail width and grade, as well as relating directly to other environmental conditions such as hydrology and the effects of Weather/Climate factors.  Slopes are more desirable to build on than flat areas, as water is easily deflected downhill in a sloped area.  During the course of a trail, the slope of the terrain may change frequently and abruptly, causing the trail design to accommodate multiple slope characteristics.

- Aspect refers to the main compass direction that a slope faces.  A slope’s aspect can determine what type of microclimate is present in a specific area.  Aspect affects how much sunlight a slope or area may receive, which directly affects snowmelt and evaporation rates, as well as vegetation type.  A slope facing into the predominant wind direction (windward slope) may receive more precipitation than a slope facing away from the predominant wind direction (leeward slope), also affecting vegetation type as well as erosion rates.  Additionally, slopes with aspect toward the predominant wind direction may also be more prone to wind erosion, or be uncomfortable to users during times of extreme winds.

- Elevation refers to the vertical distance from sea level for a given point on the earth’s surface.  Elevation is an important factor in relation to climate and microclimates along a trail, as well as influencing visitors’ ability to perform while using a trail.  Higher elevations can often mean more precipitation due to orographic uplift, but wind-direction and slope aspect are also important factors in local precipitation differences.  Higher elevations may also see extremely cold temperatures and snowfall in the winter, which may influence user type and season, or cause increased erosion due to freeze and thaw cycles.  Higher elevations have less oxygen in the atmosphere than lower elevations, causing users or trail workers to breathe more heavily and work harder.  Altitude sickness may become an issue at extremely high elevations.  Lower elevations, especially in the intermountain region, may result in extremely high temperatures during summer, which influence the usage season and volume, as well as potential hazard for off-season users.

- Soil types are important in considering the stability of terrain, especially terrain consisting of steep slopes.  Coarse soils are considered to be better than fine grained or sandy soils when considering soil stability.

- Hydrology refers to the movement of water in relation to the earth’s surface and its resulting effects.  The hydrologic features of the terrain are often important focus points at which the correct trail design choice is essential to prevent unnecessary erosion and other sustainability issues from occurring.  The most common type of hydrologic feature is a drainage, which may have flowing water seasonally or perennially.  Special trail features such as drainage dips are used to navigate drainages.  Weather/Climate factors as well as the other environmental site conditions often have a profound effect on the hydrology of an area, especially if an area is prone to large amounts of precipitation occurring during a short period of time.

- Biology refers to the effects that plants and wildlife have on the terrain’s ability to hold a trail, but also the possibility of sensitive life present in the area.

- Cultural Resources refers to Native American artifacts and ruins, pioneer dwellings and tools, pictographs and petroglyphs, or any other trace of human life that contain valuable information about how people lived before us.  Cultural Resources are extremely sensitive and are of high priority for protection, but also provide valuable educational and interpretive opportunities that often maximize visitor enjoyment and satisfaction.

Weather/Climate

Four factors comprise the Weather/Climate corner of the Trail Factor Triangle: precipitation, timing/intensity, extreme events and climate change.

- Precipitation refers to the amount of rain or snow that falls during a given amount of time.  The environmental site conditions of slope, aspect, and elevation can have a profound impact on local precipitation differences between nearby areas.

- Timing/Intensity refers to when precipitation occurs, and if it occurs during short or long periods of time.  Knowing the timing of big precipitation events can help trail management determine when and how much maintenance is required on a certain trail or trail system.

- Extreme Events such as flash floods or sheet flow that erode terrain and trails at a fast pace may require attention to detail in trail design to minimize their impacts.

- Climate Change should be taken into consideration in sustainable trail building as environmental changes may take place in the future that can affect intensity of use and maintenance.

Sustainable Design

Sustainable trail design is defined as placing the trail on the land so that impacts to the environment are minimized while the longevity of the trail is maximized.  While the user characteristics, environmental site conditions and weather/climate may be different for each individual trail, there are six sustainable trail design characteristics that should be adhered to on all trails.  Descending from most important to least important, the six keys to sustainable trails are: contour curvilinear alignment, controlled grade, integrated water control, full bench construction, durable tread, and regular appropriate maintenance.

- Contour Curvilinear Alignment utilizes side hill construction that follows, or crosses at an oblique angle, the natural contours of the terrain and gently dips into and out of all natural drainages.

- Controlled Grade allows the trail to maintain consistent grades for moderate to long sections with no abrupt grade changes.

- Integrated Water Control utilizes drainage dips at all natural drainages to ensure that water follows its natural course and is not diverted onto the trail. (see Appendix A Figure 1)

- Full Bench Construction requires cutting the full width of the tread into the hillside and dispersing the excavated soil off-trail in a way that appears natural. (see Appendix A Figures 2 and 3)

- Durable Tread requires that the trail tread be hardened and out-sloped to resist erosion and gully formation. (see Appendix A Figure 4)

- Regular Appropriate Maintenance requires that cyclical maintenance is conducted based on the individual needs of a specific trail, and that it is conducted on a regular basis to maintain the integrity of the trail. (see Appendix A Figure 4)

Control Points

Control Points are used to interpret factors identified within the Trail Factor Triangle, determining the best placement of a trail corridor, and eventually the trail alignment.  Control points are delineated into two categories: positive control points and negative control points.  Positive control points are the most appropriate places for the trail to pass, while negative control points are the most inappropriate areas for the trail to pass.  Control points are also delineated into major control points and minor control points.  Major control points are generally larger areas such as meadows or highly sensitive areas such as cultural sites.  Minor control points are generally much smaller, mainly constituting objects such as trees.  Major control points are considered to determine the general trail corridor, minor control points are considered to determine the much more precise trail alignment.

Positive control points can be destinations or other areas of interest to visitors that will not be adversely affected by visitation or areas and features that are conductive to sustainable trail design.  Examples of major positive control points:

- Destinations and Interest Areas

  - Viewpoints and peaks

  - Pristine forest

  - Cultural sites

  - Geologic features

  - Riparian zones, creeks and waterfalls

- Sustainable Design Features

  - Strong soils

  - Moderate side-slopes

  - Natural turn placement locations

Negative control points can be sensitive areas that are adversely affected by visitation or areas and features that are not conductive to sustainable trails.  Examples of major negative control points:

- Sensitive Areas

  - Fragile vegetation

  - Sensitive cultural sites

  - Over-used riparian zones

- Non-Sustainable Design Features

  - Poor soils

  - Flat and/or boggy areas

  - Extremely steep slopes

Fig.3. Flagging used to mark the location of a trail alignment

Initial major control point reconnaissance and identification may be done in the office using a map or satellite imagery, and by communicating with resource personnel about sensitive locations.  However, information collected in the office may not accurately or precisely describe an area’s actual conditions.  Checking for major control points in the field is the next step in order to determine the best place for the location of a trail.  Seeing the environment in person may reveal positive or negative control points that were not evident in the office reconnaissance, and allow the accuracy of office reconnaissance to be evaluated.

Once major control points are confirmed in the field, the trail corridor can be set.  Ribbons tied on tree branches, bushes or other objects are typically used to indicate location of the trail corridor.  After the trail corridor has been determined, identification of minor control points can be conducted in order to determine the trail alignment, which is the specific location of the trail.  Flagging placed in the ground should be used to mark the trail alignment once determined.

Accessibility Parameters

Accessibility parameters are determined by the Standards for Accessible Design set forth in the Americans with Disabilities Act (ADA) by the U.S. Department of Justice.  These parameters dictate the appropriate grade, width, outslope and surface characteristics that an accessible trail should have.  ADA compliant trails have been considered within Sunset Crater Volcano National Monument where topographically feasible.  The existing Lava Flow Trail contains an existing .3 mile loop that is ADA compliant.  The planned Lava Flow Overlook Trail will provide additional ADA compliant opportunities within the park (see p.59 of this document).  The following ADA compliant standards are the guidelines for concrete, asphalt or board surfaces (Department of Justice.  2010).

Grade and Cross Slope

Optimal grade for an ADA accessible trail is 5% or less.  Grades exceeding 5% are acceptable as long as resting areas or pullouts of no more than a 2% slope are provided at the proper intervals.  Grades between 5% and 8.33% are acceptable if resting areas or pullouts are provided at 200 foot intervals.  Grades between 8.33% and 10% are acceptable if resting areas or pullouts are provided at 30 foot intervals.  Grades between 10% and 12% are acceptable if resting areas or pullouts are provided at 10 foot intervals.  Grades exceeding 12% are never acceptable on ADA compliant trails.  Cross slope on an ADA compliant trail must never exceed 2%.

Width

Minimum tread width for an ADA accessible trail is 36 inches.  However, if the tread width is less than 60 inches, a passing space with a 5% maximum grade with a minimum area of 5 feet by 5 feet must be provided every 1,000 feet.  In the case of immovable obstacles such as large rocks or trees, a tread width of 32 inches is acceptable for a trail section no longer than 2 feet in length.  The minimum distance between sections of 32 inch tread width is 2 feet.

Sustainable Trails at Sunset Crater

Trail Factors

The following section provides an overview of the trail factors present at SUCR as described by the trail factor triangle.

User Characteristics

- User Type:  User types on trails within the park are restricted to hiker/pedestrian on all existing and planned trails.  Winter use of snow-shoes and cross country-skis is permitted.

- Season:  The typical heavy use season for the park is spring to fall, with peak visitation occurring in the summer months.  Trails still get light to moderate hiking use in the winter, especially during dry winters with below-normal snowfall.  During normal or above-normal snowfall years, uses such as cross-country skiing or snow-shoeing may be present.

Fig. 4. Summer monsoon engulfs O’Leary Peak.  The monsoon season during July, August and September is a time of increased precipitation and potential for extreme events.

Volume:  Current user volumes are moderately high, especially during peak summer months and considering small to moderate trailhead size and short trail lengths.  Winter time use is much lighter.

- Intensity:  User type is strictly hiker/pedestrian, which is a low intensity activity.   Intensity may be heightened during heavy use times.

Weather/Climate

- Precipitation:  SUCR has a semi-arid climate, with average annual precipitation of 16.7 inches, and average annual snowfall of 59.3 inches.

- Timing/Intensity:  Precipitation is highest during the summer monsoon season, with July, August and September being the wettest months of the year.  The spring months of April, May and June are driest.  The fall and winter months average about 1.2 inches of precipitation, with heavy snow as a distinct possibility.

- Extreme events: Flash flooding and sheet flow related to the cinder slopes are the most common extreme events in the park, and will need to be considered in the trail design process.

- Climate Change:  Trail design processes will take special care to focus on mitigating concerns related to extreme events, in case of increased frequency of such events in the future.  Trails should be built to withstand increased intensity of use in case of a warmer climate extending popular use seasons.  Increased aridity may affect local vegetation and soil types.

Environmental Site Conditions

- Slope:  The steepest slopes in the park are the cinder slopes of the cinder cone volcanoes, which do not exceed a 30% grade.

- Aspect: Differences in environment that are dependent on aspect are relatively small.  North-facing slopes hold snow longer, hold moisture longer due to smaller evaporation rates, may have more defined drainage systems, and may have greater bio-diversity of plants such as mosses.  Areas open to the strong south-west winds may be more exposed to wind erosion.

- Elevation:  Elevation range within the park is approximately 6800 feet to 8000 feet, with no trails climbing higher than 7300 feet.  The park is considered to be at a relatively high elevation, which should be taken into account by users and trail workers when engaging in physical activity.  Elevation changes in the park create no other real environmental challenges to trail building.

- Soils:  The two prominent soil types within the park are cinder-based soils, and hard basaltic lava rock.  The cinders are loose and form relatively steep slopes, contain a clay layer 6 inches below the surface that influences hydrology, and both characteristics create a unique set of challenges for trail building.  In-depth analysis of sustainable trail design in cinders is described in the next section.  Areas with basaltic lava rock require mechanized tools such as pionjars to carve out a treadway, but also provide for a highly durable trail tread.

- Hydrology: With no perennial water within in the park, hydrologic concerns are tied directly to extreme precipitation events.  Sheet flow, a phenomenon of sheets of water flowing across a broad area, occurs during heavy rain on cinder slopes due to a sub-surface clay layer that prevents the soil from properly absorbing water.  Additionally, small seasonal stream beds are present on some slopes.  Sustainable design concepts such as contour curvilinear alignment and integrated water control will be utilized to mitigate these concerns.  Flash floods, especially those associated with the Schultz Burn areas of the nearby San Francisco Peaks, are of concern in the areas near the Bonito Lava Flow, which serves as a local drainage basin.  Trail alignments will avoid such areas where large amounts of water may surge during extreme weather events.

- Biology:  The park is dominated by ponderosa pine forests, intermixed lightly with quaking aspen near the edges of the Bonito Lava Flow.   Trees less than 6 inches in diameter have been approved for removal where necessary, while trees more than 6 inches in diameter in line of a planned trail alignment will be discussed with park resources division.  Sensitive plants such as mosses growing on north-facing slopes and ladies tresses growing on open cinders will be avoided by trail alignments.  Noise mitigation will be considered for sensitive fauna, such as the Mexican Spotted Owl.

- Cultural Resources:  There are no significant or sensitive cultural resources in this area of the monument that require consideration for sustainable trail design.

Sustainable Design for Lenox Crater and Other Cinder Slopes

Fig. 5. Entrenchment along a section of the Lenox Crater Trail where grades exceed 20% . (measuring wheel provided for scale)

Most sustainability issues for trails at SUCR are rooted in the loose nature of the cinders that dominate much of the top soil combined with the steep slopes that define a cinder cone volcano.  Cinders are small, round, porous lava fragments that average 4mm in diameter.  Cinders are composed of “dark” minerals such as iron and olivine, and hence take on a dark gray-black color.  Cinders do not compact well, thus forming loose terrain that erodes easily and is often unpleasant to walk across.

The existing Lenox Crater Trail climbs nearly straight up the cinder dominated north-east slope of Lenox Crater, exhibiting sustainability issues that stem from its grades that often exceed 20% and reach 30% at multiple points.  Destruction on the trail by the forces of erosion and use are evident at these high grades, as well as trail widening and braiding that results from hiking at an uncomfortable grade.  During a Trail Design and Cost Estimating Course held at Sunset Crater Volcano National Monument during the week of March 27, 2011, the existing Lenox Crater Trail was analyzed to determine the maximum sustainable grade for the area.

The maximum sustainable grade for Lenox Crater’s cinder slopes has been determined to be 20%.  The existing trail exhibits grades ranging from 14% to 30%.  Grades below 20% show almost no signs of substantial deterioration due to either erosion or pedestrian use.  Grades in the 20-24% range show signs of entrenchment, but do retain the tread surface (cinders) where side-hill construction is present.  Grades above 25% in general, or above 20% where fall-line construction is present, exhibit high erosion rates that have stripped away the tread surface (cinders) and exposed the fragile clay soil layer below.

Fig. 6. Fall line development and grades approaching 25% have caused gullies to form in the trail tread near the Lenox Crater Summit. (measuring wheel provided for scale)

The design grade goal for the proposed Lenox Crater Loop Trail is 15% or less.  Falling well within the restrictions of the maximum sustainable grade, the design grade goal allows for a comfortable hiking grade.  On the existing trail, a short stretch of 14% grade exhibited a relatively narrow trail corridor, indicating that hikers are staying in a small area and minimizing impact to the surrounding terrain.  In segments where the grade exceeds 20%, the trail corridor is noticeably wider, often exceeding a width of 20 feet and forming braided sections at places.  On these steep segments, hikers spread out in an attempt to find a more comfortable hiking grade and thus increase impact over a broad area.  The 12-15% design grades are comfortable for hiking and will help greatly in keeping hikers within the designated trail corridor, thus reducing impact to the surrounding terrain.

In addition to maintaining sustainable design grades, the planned Lenox Crater Loop Trail will follow the six sustainable trail design guidelines outlined in the Sustainability section.  Contour curvilinear alignment, which requires use of side-hill development where feasible, will be highly utilized.  Controlled grades were maintained during the corridor and alignment phases of planning.  Integrated water control, in the form of drainage dips, will be utilized at all drainage crossings.  The entirety of the trail will utilize full bench construction.  Achieving durable tread on cinder soils is difficult, but regular appropriate maintenance will ensure that the trail tread is prevented from disintegrating.

While maintaining simple side-hill construction, at no place will the planned Lenox Crater Loop exceed the maximum sustainable grade of 20%.  At other localities in the park involving trail construction on cinder slopes, such as the planned Lava Loop Trail, construction on cinder slopes may exceed 20%, at which point structures such as rock retaining walls, rock stairs, or sand ladders may be required to prevent trail erosion.

Park-wide Sustainability Factors

In addition to sustainable design characteristics, regular maintenance is also integral to retaining the sustainability of a trail.  While a regular trails maintenance schedule has not been maintained at the park, routine cyclical maintenance should be conducted in the future to maximize sustainability of park trails.  Routine cyclical maintenance for trails in the park will include slough and berm removal, reshaping of out slope, clearing and brushing, cleaning of drain dips, and maintaining wood/rock trail delineations, causeways or turnpikes.  Keeping up with a cyclical maintenance routine prevents costly repairs that result from deteriorating trail and retains the smallest possible environmental footprint.  Appendix A offers diagrams illustrating the maintenance practices listed above.

In order to protect valuable natural resources at SUCR, off-trail travel or use of social trails within the park is discouraged.  To encourage users to remain on designated trails, design of park trails will incorporate specialized elements that include:

- Use of wood/rock trail delineations, causeways or turnpikes to clearly define trails in areas of open cinders that are inviting to visitors

- Use of interpretive signage to educate visitors about sensitive areas

- Use of split-rail wooden fence in conjunction with signage to discourage use of social trails or decommissioned trails, or off-trail use in general

- Evaluation of acceptable social trails for integration into the park’s official trails system

- Discouraging off-trail travel in the Bonito Lava Flow by providing users with safer and more confined access on the planned Lava Loop Trail

Viewsheds

A viewshed is defined as a natural environment that is visible from one or more viewing points.  Maximizing the availability of viewsheds in conjunction with sustainable design is essential to visitor enjoyment on trails.

Viewsheds at Lenox Crater

Fig.7. The San Francisco Peaks from Lenox Crater.

In its existing state, the purpose of the Lenox Crater Trail is to provide visitors with access to the expansive viewshed at the summit of Lenox Crater, which provides views of the San Francisco Peaks towering above the forested depression of Lenox Crater.  The existing trail also provides fleeting views of Sunset Crater, which is partially obscured by trees.  These views are more prominent when descending the trail, as hikers are facing the direction of Sunset Crater on descent.

Viewshed quality will be improved on the planned Lenox Crater Loop Trail, which utilized more viewsheds than the existing trail, and will better utilize the views of the San Francisco Peaks and Sunset Crater.  Interpretive signage will also be installed at view locations to enhance the user experience.  At multiple locations along the ascending leg from the trailhead to the north-west saddle, the proposed trail will utilize north-facing views of the Bonito Lava Flow, O’Leary Peak and Robinson Mountain.  Interpretive panels will explain the origin of these volcanic features, as well as a prominent mining scar on the slopes of Robinson Mountain.

As the trail crests the north-west saddle of Lenox Crater, views of Mount Elden and the San Francisco Peaks open up in the distance, as well as a close proximity view of Lenox Crater’s cinder clad depression.  While the existing trail utilizes this viewshed only at a single point, the proposed trail will retain use of this viewshed for approximately one-third of a mile in trail length.  As the trail ascends from the north-west saddle to the summit, and then descends from the summit to the south-east saddle, multiple interpretive panels will be used to direct user attention to the viewshed, and to explain the various natural features present..

Fig. 8. Views of O’Leary Peak, Darton Dome and the Bonito Lava Flow through ponderosa pine forest along the ascending leg of the planned Lenox Crater Loop Trail.

The descending leg from the south-east saddle to the trailhead will provide views of Sunset Crater similar to that on the existing Lenox Crater Trail.  However, the views on the proposed trail are less obscured than on the existing trail, and viewing opportunities are also increased in number.  The reduced grade of the proposed trail will also provide hikers with easier and safer viewing while walking.

Viewsheds on the Campground Connector Trail

Fig. 9. Sunset Crater dominates the skyline over the Bonito Lava Flow on the planned Campground Connector Trail.

On its stretch from the Bonito Campground to the Lenox Crater Trailhead, the planned Campground Connector Trail will incorporate a close-up look at the margins of the Bonito Lava Flow, giving users an intimate experience with the interesting details of this unique volcanic feature, and providing interpretive opportunities.  In addition to close-proximity lava rock views, the trail will also provide users with views of the O’Leary Peak complex, the Bonito Lava Flow, Sunset Crater, and the San Francisco Peaks.

Viewsheds on the Lenox – Lava Flow Connector Trail

The planned Lenox – Lava Flow Connector Trail will utilize generally open views of Sunset Crater, with the south-east flanks of the Bonito Lava Flow at close range.  As the trail approaches its junction with the Lava Flow Trail, views of the Sunset Crater proper disappear as one of the mountain’s flanking cinder slopes dominates the view.

Viewsheds on the Lava Loop Trail

The planned Lava Loop Trail will feature predominantly close-proximity views of the rugged lava structures found in the Bonito Lava Flow.  At the beginning and end of the loop, views of the O’Leary Peak complex are visible, as well as views of Sunset Crater.

Viewsheds on the Lava Flow Overlook Trail

Fig. 10. Sunset Crater and the Bonito Lava Flow viewed from the planned Lenox – Lava Flow Connector Trail. (Below) Map of planned and existing trails.

The planned Lava Flow Overlook Trail will access an expansive viewshed overlooking the Bonito Lava Flow, which also includes a great view of Sunset Crater.  This viewshed is very unique because it gives users a view of the Bonito Lava Flow that is not available from any other trail or viewpoint in the park.  Additionally, a remarkable “squeeze-up” type volcanic feature is also present at close proximity to the location of the planned trail, which will further enrich visitor experience and provide an excellent interpretive opportunity.

Interpretation

Existing Interpretive Opportunities

Fig. 11. A small interpretive panel on the Lava Flow Trail.

Sunset Crater Volcano’s existing interpretive opportunity is the 1 mile long Lava Flow Trail located at the base of Sunset Crater.  Interpretive panels on this trail educate users on the volcanic features associated with the eruption of Sunset Crater and the Bonito Lava Flow.  Visitors can take a self-guided tour by picking up a pamphlet that is available at the trailhead.  The tour has numerous stops, at each of which the pamphlet provides fascinating details on the unique volcanic geology of the park.  The tour is supplemented with large interpretive panels that provide visitors with additional geologic information and vivid images, as well as small interpretive panels that typically describe native flora species.

Interpretation on the planned Lenox Crater Loop Trail

Fig. 12. A large interpretive panel on the Lava Flow Trail.

The planned Lenox Crater Loop Trail will integrate approximately 15 interpretive signs that will inform and educate visitors on the unique environment of a cinder cone volcano located in a ponderosa pine forest.  As Lenox Crater is not a prime example of a cinder cone, interpretive signage will be a powerful tool in heightening the user experience at this location.  Interpretive panels will also be used to encourage users to remain on trail.  Interpretive opportunities will be enhanced by viewsheds that provide visitors with expansive views of the surrounding volcanic terrain.  The trail will be advertised as “one-way”, encouraging users to travel counter-clockwise and follow the interpretive signage in the correct order in conjunction with an interpretive pamphlet that will be provided at the trailhead.

Fig. 13. The expansive viewshed at the Lenox Crater Summit provides copious and varied interpretive opportunities.

Specific opportunities for interpretive signage on the planned Lenox Crater Trail may include old growth-ponderosa pine forest, view of the Bonito Lava Flow and O’Leary Peak, view of a mining scar on Robinson Mountain, moss growing on the north-facing slopes of Lenox Crater, sensitivity of plant growth in the depression of the crater, eruption of the San Francisco Peaks, burn area of the 2010 Schultz Fire, geology of Lenox Crater, root structure of a fallen Ponderosa Pine, and the presence of lichen growing on cinders.

Interpretation on the Planned Campground Connector Trail

The planned Campground Connector Trail will receive light interpretive signing at designated overlooks, emphasizing the unique volcanic terrain of the Bonito Lava Flow that the trail parallels.  This will especially heighten the experience of the trail’s pedestrian users, and encourage them to remain on trail.  The trail will also utilize various viewsheds, permitting opportunities for interpretive signing that explains the geologic origin and cultural of the surrounding mountains.

Signage Protocol

Fig. 14. Existing trail sign in Sunset Crater Volcano National Monument.

New signs installed on existing or planned trails should match appropriately to existing signage already in place in the monument.  Photos of existing signage have been provided throughout this section.

Lenox Crater Trail Rehabilitation Proposal

The Lenox Crater trail area was a point of concentration in the planning internship.  The alternatives discussed below were used to help decide on the proposed alternative, which follows.

Alternative I

This alternative proposes that the existing Lenox Crater Trail be obliterated and the existing trail corridor be rehabilitated to its natural state based on these factors:

Fig. 15. Mitigating the large berm that has developed on the downslope side of the Lenox Crater Trail is of major concern (measuring wheel for scale).

The existing trail is poorly designed in regard to sustainability, user experience and visitor satisfaction

- The benefits of constructing a sustainable layout and design outweigh the high costs of structurally repairing and maintaining the existing trail

With no complex structures in place on this trail, re-contouring, obliteration and rehabilitation will be a relatively simple process entailing hand-movement of the trail’s extensive berm to fill in the tread bench, re-establishing cinders where excessive trails grades have caused erosion down to the clay layer, and spreading native plant material over the area in a random manner so that it appears natural.  (Appendix A)

If management chooses to utilize this alternative, it will be used in conjunction with the planned Lenox Crater Loop Trail.

Cost and Time Estimate for Alternative 1

Labor and Transportation Cost			$ 64160.56

Material Costs					$   6457.40

Lenox Crater Loop Trail Cost Total		$ 70,617.96

Estimated time for a crew of 10 workers		7 weeks

Alternative 2

This alternative proposes maintaining the current trail alignment.  While retaining the existing treadway, trail narrowing would be performed (including reduction of the existing berm – see Appendix A Figure 4), additional tread material laid down where severe gully formation and entrenchment has taken place, and then cable steps (Appendix A) would be constructed in order to limit cinder erosion on the steep trail grades.  The work described above may temporarily remedy the issues present on the trail, however, the poor design of the existing trail will only continue to deteriorate over time.  Therefore, this plan does not favor this alternative.

Cost and Time Estimate for Alternative 2

Labor and Transportation Cost			$ 49,725.01

Material Costs					$   8,820.22

Lenox Crater Loop Trail Cost Total		$ 58,545.23

Estimated time for a crew of 10 workers		3 weeks

Alternative 3

No action.  If management chooses this alternative, the existing trail will be left as it is in its current state.  This plan does not support this alternative as the existing trail is not sustainable and will continue to deteriorate if the park does not make an attempt to rehabilitate the trail in some way.

Detailed cost estimates are located in Appendix C.  A map of the trail area is located on the following page.

Lenox Crater Loop Trail Proposal

The proposed Lenox Crater Loop Trail is a replacement of the existing Lenox Crater Trail.  The new trail will incorporate sustainable design elements and focus on user experience through the utilization of viewsheds and interpretive signage, greatly enhancing visitor satisfaction.  .

Supporting Factors

- Utilizes sustainable design concepts and replaces the existing Lenox Crater Trail, a poorly designed trail severely lacking sustainability

- Utilizes interpretation to enhance visitor experience and encourage resource protection

- Maximizes visibility of impressive viewsheds in comparison to the existing trail

Federal Trail Categorization

This proposed trail is being designated a Class 3 developed trail, with the single allowed, managed and designed use being hiker/pedestrian.  As specified previously in the Sustainability section, the maximum sustainable grade for the area is 20%, with a design grade goal of 15% or less.  Tread width will be 18-24 inches.

Fig. 16. Ladies Tresses, common to the open cinders of Lenox Crater, are sensitive to foot traffic. (pen for scale)

Site Conditions

Specific site conditions of the corridor of this planned trail include:

- Steep cinder slopes

- Small seasonal drainages

- Mossy north-facing slopes and ladies tresses growing in the cinders

- Ponderosa pine forest

Control Points

The first positive control point is determined to be the Lenox Crater Trailhead, where the trail is to start and end.  The two saddles on the north-west and south-east rims of the crater are positive control points where the topography provides a natural break where sustainable turns in the trail can be constructed.  The Lenox Crater summit is a major positive control point that represents the goal of the hike for users, and boasts incredible viewshed and interpretive opportunities.

The major negative control point on Lenox Crater consists of the open cinders of the crater’s depression.  Ladies tresses, tiny plants that make their home in the depression, are highly sensitive to the impacts of foot-traffic.  The unique nature of the open cinder area is inviting to visitors, so special care must be taken to entice hikers to remain on trail.  The south-west rim of Lenox Crater is a negative control point as a trail in that vicinity would be at high risk for users venturing off trail to reach the crater summit.

Trail Characteristics

This planned trail is designed as an interpretive loop, encouraging use in a one-way counter-clockwise manner through the availability of self-guided tour pamphlets at the trailhead.  Curvilinear contour alignment and side-hill construction will be used prominently on this trail due to steep cinder slopes being present for the entirety of the trail (Appendix A Figures 2 and 3).  Sustainable climbing turns will be used at the control points defined at the crater’s two saddles.  All grades will fall below the maximum sustainable grade for cinder slopes (20%) as described in the Sustainable Design for Lenox Crater and Other Cinder Slopes section on page 17.  Integrated water control through use of drain dips (Appendix A Figure 1) at all seasonal drainage crossings will ensure natural drainage patterns are maintained, and trail integrity is not compromised in the case of extreme precipitation events.   In addition to copious interpretive signage describing the unique and interesting natural features found in the area, signage will also educate users on the importance on staying on trail in order to minimize impacts to sensitive areas.  Wood trail delineation/puncheon or turnpike (Appendix A Figure 8) will additionally be constructed near the crater rim to discourage off-trail use.  Tread durability bolstered by advanced sustainable design elements should be sufficient to handle the low intensity nature of hiker/pedestrian use, but routine and regularly performed trail maintenance should be conducted in order to ensure trail integrity and prevent excessive berm development.

Cost and Time Estimate

Labor and Transportation Cost			$ 64,160.55

Material Costs					$   6,457.40

Lenox Crater Loop Trail Cost Total		$ 70,617.96

Time estimate for a crew of 10 workers		9 weeks

Detailed cost estimates are located in Appendix C.  A map of the trail area is located on the following page.

Campground Connector Trail Proposal

The planned Campground Connector will help to interconnect all trails within the park with the Visitor Center, creating a continuous and fully-integrated trails system at Sunset Crater Volcano National Monument.

Fig. 17. Basalt rocks delineate the existing social trail located on Coconino National Forest land.  Footprints in the cinders indicate seasonally heavy use.  Part of the this social trail will be integrated into the planned Campground Connector Trail.

From the Visitor Center, the trail will first connect to the Bonito Campground, both of which are located on the Coconino National Forest. From the Bonito Campground, the trail will integrate much of an existing social trail that runs from the campground’s amphitheater to the western park boundary, with new trail being constructed from the western park boundary to the Lenox Crater.

Supporting Factors

- Enables a continuous inter-connected trail system within SUCR

- Provides additional recreational opportunities at the SUCR Visitor Center and the Coconino National Forest Bonito Campground

- Complements and incorporates usage of an existing social trail

Fig. 18. The edges of the Bonito Lava Flow are ripe with unique combinations of vegetation and geology, which will heighten user enjoyment on the planned Campground Connector Trail.

Federal Trail Categorization

This planned trail is designated Class 4 Highly Developed, with the single allowed, managed and designed use being hiker/pedestrian.  Maximum sustainable trail grade on cinder slopes is 20%.  Tread width will be 36 inches.

Site Conditions

Specific site conditions of the corridor of this planned trail include:

- Flat to moderately sloped cinder fields with intermixed rocky terrain

- Drainages stemming from culverts under the nearby roadway

Fig. 19. View of Road 545 from the planned Sunset Crater Multi-Use Trail.   Trail proximity to roads will be avoided where possible.

Mossy north-facing slopes and ladies tresses growing in cinders

- Proximity to roadway and campground

Control Points

The first set of positive control points consists of the endpoints of the trail, which are the Bonito Campground near the visitor center and the Lenox Crater Trailhead.  The edge of the Bonito Lava Flow forms a positive control point as it is of interest to users, especially at prominent viewpoints.  A drainage that drains from the Lenox Crater Trailhead into a low area between the Bonito Lava Flow and the road is a negative control point due to the high erosion potential that would quickly deteriorate a trail.  For approximately 700 feet, the trail will enter the rugged terrain of Bonito Lava Flow, avoiding the erosion potential of the drainage.  The trail will also avoid a basin near the Bonito Campground where erosion and flood danger is high.  When possible, the trail will avoid being within close range to road 545, the main thoroughfare in Sunset Crater Volcano National Monument.

Trail Characteristics

This planned trail expects moderate intensity use as the trail will see hiker/pedestrian usage from park visitors, as well as campers staying at the Bonito Campground.  In order to accommodate the potential for trail deterioration related to heightened intensity of use, this planned trail will utilize a single tier rock causeway (Appendix A Figure 9) to retain the hardened aggregate trail surface that will perform with durability superior to that of a normal Class 3 trail built in the cinders.  Causeway construction will also allow for easier walking and better user experience as visitors will not be required to hike in the loose cinders.  Concerns involving the potential for trail deterioration in flat areas due to standing water on the trail will be mitigated by proper crowning and out-sloping allowed by the rock causeway construction.  The trail will utilize side-hill construction where appropriate in order to minimize the concerns of flat ground trail development.  Single or multi-tier rock walls and rock steps are required in some sections to maintain grades or maintain sustainability on steep slopes (Appendix A Figures 12-15).  Culverts will be required for the trail to cross drainages that come out from culverts underneath the nearby roadbed (Appendix A Figures 16-17).  In a section where the trail enters the rugged Bonito Lava Flow, a technique called rip rap will be utilized. Rip rap is an extremely durable cobble-like structure that provides an armored walking surface, providing a safe and erosion resistant trail that blends well with the terrain.

This planned trail will incorporate an existing social trail that leads from the Bonito Campground on the Coconino National Forest to the SUCR park boundary.  From the end of the existing social trail at the park boundary, a new trail alignment has been designed to connect the park boundary to the Lenox Crater Trailhead.  Additionally, four realignments have been designed to enhance the user experience and practicality of the trail.  These realignments include:

- Two spur trails to prominent viewpoints on the Bonito Lava Flow

- Realignment allowing users to bypass a hilltop viewpoint on the existing trail

- Connector trail between the SUCR Visitor Center and the existing trail

Cost and Time Estimate

Labor and Transportation Cost			$ 511,560.96

Material Costs					$   84,996.77

Campground Connector Trail Cost Total		$ 596,557.73

Time estimate for a crew of 10 workers		71 weeks

Detailed cost estimates are located in Appendix C..  A map of the trail area is located on the following page.

Lenox – Lava Flow Connector Trail Proposal

The planned Lenox – Lava Flow Connector Trail will serve as a connector between the Lenox Crater Trailhead and the Lava Flow Trailhead, and in conjunction with the Sunset Crater Multi-Use Trail, will create a continuous interconnecting trail system at Sunset Crater Volcano National Monument.  An existing but decommissioned road may be used as part of the alignment for the trail.

Supporting Factors

- Enables a continuous interconnecting trail system within SUCR

- Utilizes an existing trailhead

Federal Trail Categorization

Fig. 20. This decommissioned road has been avoided as a possible trail alignment for the planned Lenox – Lava Flow Connector Trail.

This planned trail will be a Class 4 Developed/Improved trail with the allowed, managed and designed use to be hiker/pedestrian.  Trail grades should not exceed 20% on cinders, and the tread width will be 36 inches.

Site Conditions

Specific site conditions for the corridor of this planned trail include:

- Flat to moderately sloped cinder fields intermixed with rocky areas

- Ponderosa pine forest and desert brush

- Existing but decommissioned dirt road

Control Points

The first main control points for this trail are the existing Lenox Crater Trailhead and the existing Lava Flow Trail, which will form the endpoints of the trail.  A faint remnant of a decommissioned road bed near the Lenox Crater Trailhead has been ruled out as a possible trail location due to its poor aesthetic qualities, especially when compared to the incredibly pleasant areas nearby along the Bonito Lava Flow.    Additionally, the decommissioned road is also in view of the planned loop alignment of the nearby Lenox Crater Trail.  There is potential for hikers on the planned Lenox Crater Loop Trail to be lured off trail if they see the trail alignment on the decommissioned road, especially if other hikers are visible.  The trail will instead maintain close proximity to the Bonito Lava Flow, providing visitors with access to an expansive viewshed and enhancing visitor satisfaction.

Trail Characteristics

The planned Lenox – Lava Flow Connector Trail expects low to moderate intensity usage as the trail will see usage as this trail will be a connector trail between two existing recreation focal points.  In order to accommodate the potential for trail deterioration related to heightened intensity of use,    this planned trail will utilize single tier rock causeway (Appendix A Figure 9) to retain the hardened aggregate trail surface that will perform with durability superior to that of a normal Class 3 trail built in the cinders.   Causeway construction will also allow for easier walking and better user experience as visitors will not be required to hike in the loose cinders.  Concerns involving the potential for trail deterioration in flat areas due to standing water on the trail will be mitigated by proper out-sloping allowed by the rock causeway construction.  The trail will utilize side-hill construction where appropriate in order to minimize the concerns of flat ground trail development.  Appropriate signage at the junction with the Lava Flow Trail will be required in order avoid hiker confusion, especially for those users following the self-guided interpretive tour on the Lava Flow Trail.

Cost and Time Estimate

Labor and Transportation Cost			$    154,905.80

Material Costs					$      56,700.81

Lenox Crater Loop Trail Cost Total		$    211,606.61

Time estimate for a crew of 10 workers	 	24 weeks

Detailed cost estimates are located in Appendix C.  A map of the trail area is located on the following page.

Lava Flow Overlook Trail Proposal

The planned Lava Flow Overlook Trail will be a short, paved ADA compliant footpath that leads from the existing Lava Flow Trailhead south to an expansive overlook that sports breathtaking views of the Bonito Lava Flow and Sunset Crater.

Supporting Factors

- Expands ADA compliant trail within SUCR

- Utilizes an ADA compliant parking area

- Area is conductive to ADA compliant construction

- Provides access to a unique viewshed

Fig. 21. Views of the Bonito Lava Flow, Robinson Mountain and Lenox Crater from the planned Lava Overlook Trail.

Utilizes interpretive signage to enhance user experience

Federal Trail Categorization

This planned trail is designated as a Class 5 Fully Developed trail, with the allowed, managed and designed use being hiker/pedestrian.  Tread width, grade and outslope will comply with the ADA standards outlined in the Accessibility section.  Pavement will be concrete.  A truss bridge may be utilized to span a trench to the overlook.

Site Conditions

Site conditions specific to the corridor of this planned trail include:

- Expansive flat ground and slopes consisting of cinders

- Isolated rocky areas

- Moderate quantities of desert shrubs

- Exposure to south-west winds

Control Points

The control points that determine the alignment of this trail are highly influenced by the demanding ADA guidelines outlined in the Accessibility section.  Incredibly rocky and rugged areas are negative control points as they are not conductive to constructing an ADA compliant fully developed trail.  An area of gentle terrain dominated by cinders is the positive control point that will allow access to the impressive lava flow overlook, another positive control point.

Trail Characteristics

The lack of rugged terrain in this area is very compatible with the shallow grades required by an ADA compliant trail.  The trail tread will be constructed out of concrete pavement, which will provide substantial durability for the low intensity usage levels of a hiker/pedestrian trail.  The paved construction of this trail will also mitigate concerns regarding the lack of the side-hill construction options in the trail corridor.  Split-rail fencing will be constructed on both sides of the path in order to encourage users to remain on trail, protecting nearby resources.  A small ravine must crossed to reach the overlook area, requiring construction of either a multi-tier rock causeway (Appendix A Figure 12-15) or a hip truss style bridge (Appendix A Figure 18) in order to maintain ADA compliant grades.  The cost difference between the bridge and causeway options is outlined in the cost estimate section below.  The overlook platform will feature interpretive signage and an impressive view of Sunset Crater and the Bonito Lava Flow.

Cost and Time Estimate – Bridge Option

Total Labor and Transportation Costs		$   31,213.11

Total Material Costs					$   80,998.89

Total Cost						$ 112,212.00

Time estimate for a crew of 10 workers	 	4.5 weeks

Cost and Time Estimate – Causeway Option

Total Labor and Transportation Costs		 $   48,836.53

Total Material Costs					 $   59,506.87

Total Cost						 $ 108,343.40

Time estimate for a crew of 10 workers	 	7 weeks

Detailed cost estimates are located in Appendix C.  A map of the trail area is located on the following page.

Lava Loop Trail Proposal

Fig. 22. This existing social trail in the Bonito Lava Flow forms the blue print for the planned Lava Loop Trail.

The planned Lava Loop Trail will improve an existing social trail, integrating it into the official trail system.  Approximately 900 feet in length, the existing social trail forms a loop on the Bonito Lava Flow at the Lenox Crater Trailhead.  In addition to the main loop, a short 100 foot interior loop trail is also present.  Due to the nature of the a’a type basaltic lava, the terrain that the existing social trail crosses is extremely rugged with an abundance of sharp and angular rocks.

Supporting Factors

- The existing social trail receives relatively high use

- The rugged nature of the terrain causes safety concerns with use of existing social trail

- A trail corridor can easily be carved into the lava flow utilizing the existing social trail, confining user impacts to the designated trail corridor

- Sustainability issues related to erosion and drainage are virtually non-existent in the vicinity of the existing social trail due to its rocky nature

- Minor sustainability issues related to cinders can easily be mitigated

Federal Trail Categorization

Fig. 23. Grades on the cinder slope exceed 20%, resulting in erosion that has exposed the soil’s sensitive clay layer.  Sidehill construction is not possible at this location, so a series of two sand ladders will be used to mitigate this sustainability issue.

This planned trail is being designated as Class 3 Developed/Improved, with the allowed, managed and designed use being hiker/pedestrian.  The trail width will be 18-24 inches.

Site Conditions

Site conditions specific to the corridor of this planned trail include:

- Steep cinder slopes of moderately short length

- Isolated aspen and ponderosa pine trees

- Rugged, rocky terrain

Control Points

Fig. 24. The Lava Loop Trail area viewed from the Lenox Crater Trailhead.

Being that this trail will essentially improve upon an existing social trail, and as such the trail corridor and alignment are pre-determined, control points will not be used in the typical manner of determining the most appropriate trail corridor.  The existing social trail that circumnavigates the area will act as the positive control points, while overly rugged and rocky areas or cliffs are negative control points.

Trail Characteristics

The single sustainability issue on this proposed trail is a short section of trail that requires crossing a cinder slope at a grade that exceeds the maximum sustainable grade for cinders as determined at 20%.  To mitigate this issue, a series of two cable steps (Appendix A Figure 11) will be constructed in order to maximize sustainability of the slopes.  Hand tools, Pionjars, Cobra Combis, and/or Bosch Brutes will be used to break up rock to form a proper trailway out of the existing social trail.  Unstructured rock wall will be used to fill in gaps between large rocks to mitigate safety concerns.  Due to the extremely rocky nature of the terrain and lack of erosion concerns associated with soils and other loose materials, and a distinct lack of traditional drainage features, side hill construction is not necessary or feasible at this location.   Being that the trail tread will be comprised of hard basaltic lava rock, tread durability will be supreme.

Cost and Time Estimate

Labor and Transportation Cost			$ 13,288.67

Material Costs					$   4,902.80

Lenox Crater Loop Trail Cost Total		$ 18,191.47

Time estimate for a crew of 10 workers 		2 weeks

Detailed cost estimates are located in Appendix C.  A map of the trail area is located on the following page.

Lava Flow Trail Maintenance Prescription

The Lava Flow Trail is currently the park’s premiere hiking experience.  Approximately one mile in length, the trail contains a .25 mile paved section that meets ADA compliance standards.  The trail also features high-quality interpretive signage, which is supplemented with a pamphlet available to hikers at the trailhead, allowing users to take a self-guided tour through some of the nation’s most unique and recently created volcanic terrain.  Additionally, ranger guided tours are given on a regular basis.

Federal Trail Categorization

The ADA compliant trail section is designated as Class 5 Fully Developed, while the remaining trail section is designated Class 3 Developed/Improved.  The single allowed, managed and designed use for the trail is hiker/pedestrian.

Site Conditions

Specific site conditions in the vicinity of the Lava Flow Trail include:

- Cinders and rugged, rocky terrain

- Exposure to strong south-west winds

- Ponderosa pines intermixed with desert vegetation

Class 5 Section Improvements

Fig. 25. A wind pocket is accelerating erosion on the right side of the Lava Flow Trail at this location.  A single-tier rock retaining wall will be constructed to prevent undermining of the concrete and prevent wind erosion.

The .25 mile Class 5 section is paved with concrete that is still in good condition, but is at risk of being undermined due to cinder migration at the trail edges.  At a bend in the trail where a curb protects users from a small drop-off, this problem is accentuated by a wind pocket that accelerates erosion at the base of the concrete.  At the location where visitors can leave the paved Class 5 section and enter the unpaved Class 3 section, the concrete is undermining at a rapid rate due to heavy foot traffic on the ground next to the pavement.

To mitigate concrete undermining throughout the paved trail, the entire length of the Class 5 section will be shouldered, in which cinders at the trail edges are re-established.  Single-tier or multi-tier rock retaining wall will be built in two separate sections, to further maintain the integrity of the concrete.

Fig. 26. An improperly placed and secured bench on the Lava Flow Trail.  This bench is one of which that will be mounted to a new concrete slab, encouraging more frequent use of the bench.

To mitigate the wind pocket scenario, single-tier rock or multi-tier rock retaining wall will be utilized at this location to protect the sidewalk from wind erosion and prevent further concrete undermining.

Fig. 27. Concrete undermining at the junction between the Class 5 and Class 3 sections.  Rock stairs will constructed to mitigate this concern.

At the location where the Class 5 trail intersects the Class 3 trail, a small set of rock stairs will be constructed.  This will help prevent the concrete from further undermining, as well as providing users with more comfortable hiking as they enter the Class 3 trail section.

Fig. 28. An improperly secured interpretive panel on the Lava Flow Trail.  This and other signs will be mounted to new concrete slabs.

Interpretive panels and benches along the paved section are not properly secured to the ground and require attention.  Additionally, some benches are set off from the concrete, discouraging use by some users with disabilities.  Prescribed action for these features is to pour eight new concrete slabs and then mount the interpretive panels and benches to the concrete.  The slabs will be 4 inches in thickness, and range in dimension from 10 feet by 6 feet to 14 feet by 8 feet.

Class 3 Section Improvements

The Class 3 section of the Lava Flow Trail is a standard hiking trail (not paved) that is in generally poor condition, although some sections remain in fair condition.  Rehabilitation of this section requires a variety of trail typical trail maintenance techniques that will be performed throughout most of the Class 3 trail section.  These techniques include:

- Light brushing of vegetation

- Removal of rocks and debris to smooth tread surface

- Delineating trail to make its appearance obvious to users

  - Includes practices like trail narrowing, installing liner rocks on trail edges, and installing vertical and horizontal mulching

At five different locations, rehabilitation of unauthorized social trails will be performed to prevent resource damage outside of the managed trail corridor.  This process includes a combination of loosening and spreading of compacted soil, and placing duff (organic plant material consisting of pine needles, leaves, and wood debris) over the social trail.  Vertical mulching may also be used to hide entrances to social trails along the authorized trail corridor.  Two sections of single tier rock retaining wall will be construction of prevent trail degradation along the Class 3 section.  Construction of post rail fence to contain users to the trail corridor will be performed on a section of trail where a fence is already present on one side of the trail.

A segment of trail from that forms a shortcut from the Class 5 trail section to the main loop of the Class 3 trail section requires construction of rock causeway in order to better delineate the trail for users and prevent trail erosion.  Along this same segment, re-enforcement of an existing retaining wall needs to be performed to prevent wall failure.

Cost Estimate

Labor Cost						$ 30,001.98

Material Cost						$ 19,900.00

Total Cost						$ 49,901.98

Equipment and Noise Mitigation Parameters

In order to preserve the wilderness experience valued by park visitors and to minimize the impact of noise on native fauna, trail construction within Sunset Crater Volcano National Monument will favor use of hand-powered equipment.  Hand tools used on SUCR trail projects may include:

- Rigging

- Wheelbarrows

- Rakes

- Shovels

- McClouds

- Sledges

In circumstances that require the use of motorized and/or mechanized equipment, the following equipment may be used (maximum decibel levels have been provided):

- Pionjars – Combination drill/jack hammer used to excavate rock – 112 db

- Cobra Combi/Bosch Brute	- Gas-powered jackhammer – 108

- Chainsaws – Motorized saw used for tree cutting – 103 db

- Mucktrucks – Motorized wheelbarrow – 97 db

- Bobcat S-100 – Light tractor used to transport soil, rock, etc – 96 db

- Toters	- Motorized wheelbarrow – 95 db

- Plate Compactors and Steel Roller Wheels – Mechanized equipment used to harden trail tread – 90db

- Honda EU 3000 Generator	- Power generator – 58 db

In addition to favoring use of hand tools, trail crew leaders working on SUCR trail projects will use consult the park’s resource division in order to determine times when local wildlife is especially sensitive to noise and use of motorized and/or mechanized equipment should be avoided.  Simultaneous use of multiple motorized and/or mechanized tools will be avoided when feasible to minimize the possibility of increased decibel levels.  Trail supervisors will maintain open lines of communication with the resource division to ensure that noise levels are appropriate during all trail construction and maintenance operations.

Materials

Use of Local Materials

This plan emphasizes using local materials in order to maximize the sustainability and natural appearance of trail building projects.  Use of local materials significantly reduces the amount of fossil fuels consumed and pollution expelled during transportation of materials to the worksite.  Local materials will be selected on the following criteria:

- Material maintains a natural appearance that will mesh well with the forested volcanic landscape present at Sunset Crater Volcano National Monument

- Material has a reputation of durability, maximizing the life span of trail structures and reducing the frequency of major trail maintenance projects

General Material Requirements

Described below are the general material requirements for each trail proposal.  Specific material selections will be made by park management after considering the alternatives of each trail proposal.

The planned Lenox Crater Loop Trail requires construction of wood/rock trail delineations, causeways or turnpikes, as well as rock retaining walls.  Juniper and cedar are the preferred wood in terms of durability and local availability, however, ponderosa pine may be used from trees felled during trail corridor clearing.  Local rock will be imported for any rock structures.  Juniper for wooden structures will be imported.

The planned Lava Loop Trail requires non-structural walls to be built using native basalt rock that can be gathered on site.

The planned Campground Connector Trail and the Lenox – Lava Flow connector trails may use an aggregate base material surface causeway that requires local rock retaining walls to be built.  Local rock and aggregate will be imported to the worksite.

The planned Lava Overlook Trail will require use of concrete for tread construction and juniper for split rail fencing.  Both of these materials will be imported to the worksite.

The Lava Flow Trail Maintenance Prescription requires single-tier and multi-tier rock retaining wall using local rock that will be imported to the worksite.

All Interpretive panels required for any park trails will be procured from an NPS-approved source.

Summary of Internship Report

(Jake Case and James Sell)

Trail Corridor Proposals

Completion of the Campground Connector Trail and Lenox – Lava Flow Connector Trail projects will create an interconnected trail system that links the park Visitor Center with the two existing trailheads.  Completion of the Lava Loop Trail and Lava Overlook Trail projects that spur from existing trailheads will also create a fully integrated trail system.   Creating a fully integrated trail system will allow users to hike multiple trails from one access point, maximizing the time that visitors spend out of their vehicles and creating a more interactive Sunset Crater experience.  Connection with the Bonito Campground will improve recreational opportunities for campers, and create an inter-agency trail system, coordinating with the U.S. Forest Service. The interconnected system will provide visitor access to the core areas of the park without needing to use their cars.

If utilized, the trail maintenance, re-design, and new construction actions proposed in this plan will greatly improve the trail system for Sunset Crater Volcano National Monument and the surrounding area.  This plan intends to maximize sustainability, quality of user experience, and availability of recreation opportunities, which are the essential qualities of any viable trail system.  Improvement of the SUCR trail system will bolster the park’s ability to serve the public’s thirst to explore the unique geology of the park, while protecting park resources by providing approved avenues for visitor exploration.

Attention to viewsheds, interpretative possibilities, accessibility and sustainable design concepts that enrich the user experience have been emphasized in order to ensure that visitor satisfaction is maximized.  Design characteristics that are specialized for construction in cinders will ensure for proper sustainability and ease of use.  Sustainable design concepts set forth in the trail factor triangle have been employed and will ensure that impacts to the park’s resources are minimal and trail life span to be optimal.

Improvement, expansion and full integration of the SUCR trail system will prove to have a positive effect on visitor satisfaction and park sustainability.  This plan prioritizes trail sustainability, enhancement of visitor experience, protection of park resources, and creating an interconnected trail system as the key goals to be met that will boost the park’s recreational offerings to a higher level, while following the mission of the National Park Service.

The trail plan proposals presented here are intended to remedy an existing deficit – of a mere 1.35 miles of trails in a park dominated by facilities for sightseeing by road.  In a larger sense, however, they must be viewed within the context of sustainable park planning:

1. On the level of trail planning, a sustainable trail has minimum environmental/cultural impact and minimal maintenance.

2. In the current context of climate friendly planning, a sustainable trail plan requires minimal use of fossil fuels and maximizes visitor experience and education.

This trail plan meets those needs. When completed, it will be possible for park visitors to experience all the key features of Sunset Crater volcanism without using their cars.  This transportation alternative will greatly contribute toward transforming Sunset Crater National Monument from a motorized sightseeing park to a more non-motorized climate friendly park

Evaluation of Trail Sustainability

Any design is an experiment and requires evaluation.  The set of standards created by the Guide to Sustainable Mountain Trails:  Assessment, Planning, and Design Sketchbook (Basch, et al. 2007), under the leadership of Hugh Duffy, provides a basis for trail corridor sustainability evaluation using ten standards,  which require a process that looks beyond the trail corridor itself to the larger sustainability issue.  The Sunset Crater trails did not explicitly use those standards but they do provide a basis for evaluation that can be used to point out areas of improvement.

The matrix presented below is derived from the Basch, et al.(2007) standards for mountain trail design,.  In this case, the matrix has been partially filled in to reveal strengths and weaknesses in the proposed trails.

Figure 29. Trail Assessment  Matrix (based on Basch, et al., 2007)

|  |  |  |  |  | Lenox Crater | Campground Connector | Lava Flow Connector | Lava Flow Overlook | Lava Loop |  | Lava Flow |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Meets trail’s established purpose |  |  |  |  | Y | Y | Y | Y | Y | Y |  |
| Originates at appropriate location |  |  |  |  | Y | Y | Y | Y | Y | Y |  |
| Destination at appropriate location |  |  |  |  | Y | Y | Y | Y | Y | Y |  |
| Allows appropriate uses |  |  |  |  | Y | Y | Y | Y | Y | Y |  |
| Appropriate corridor control points |  |  |  |  | Y | Y | Y | Y | Y | Y |  |
| Scenic viewpoints taken advantage of |  |  |  |  | Y | Y | Y | Y | Y | Y |  |
| Interpretive opportunities taken advantage of |  |  |  |  | Y | Y |  |  |  | Y |  |
| Protects natural resources |  |  |  |  | Y |  |  |  |  | Y |  |
| Protects cultural resources |  |  |  |  |  |  |  |  |  |  |  |
| Nonprofit agency or individual volunteer support |  |  |  |  | ? | ? | ? | ? | ? | ? |  |

This matrix has not been completely filled out, and it would be expected that modifications will be made to existing work as well.  In essence, what is needed at this point is to allow a more wide-ranging examination of environmental/cultural/institutional impacts, including the more indirect effects of trail construction such as interpretation, local procurement, fossil fuel reduction, and any other influences.

Beyond the trail matrix are considerations of regional context, local materials procurement, user behavior and education, use of renewable energy, or the other parameters mentioned in the executive orders cited in the introduction to this report.  For example, the Flagstaff Urban Trail System could be extended to connect to the Sunset Crater trails and provide a hiking/biking route from Flagstaff to the national monument.

The important point here is that these trail proposals are starting points for a more complete sustainability planning process.  Once the corridor proposals are identified, then the Green Team or representatives from the other divisions can make a more detailed examination of the impacts as they relate to the Environmental Management System now under development.  This matrix also provides a solid starting point for an evaluation system that can be refined as more trails are built.

Basch, et al. (2007) recommend a trail sustainability evaluation along planned corridors for each 100 foot section of trail, in a format similar to the more usual trail prescriptions.  Once the Sunset Crater Trail corridors are located, then a similar assessment can provide a valuable starting point for monitoring.

Sustainability itself is a term that has multiple meanings.  It has often been taken to mean trail construction that requires minimal maintenance and makes minimal impacts to the total environment, and that is a good starting point.  However, federal mandates are requiring that all efforts in sustainability be broadened in scope to go beyond trail corridors to the larger regional and social context.  The plan presented here should also provide a basis for monitoring and evaluation that considers both contexts.

References Cited

Arizona Earthquake Information Center. 2011,  Arizona Earthquake History. Northern Arizona University http://www.cefns.nau.edu/Orgs/aeic/eq_history.html.

California State Parks.  1991.  Trails Handbook.  Sacramento:  California Department of Parks and Recreation.

Congress of the United States 1916. National Park Service Organic Act of 1916.

Department of Justice.  2010.  2010 ADA Standards for Accessible Design, http://www.ada.gov/regs2010/2010ADAStandards/2010ADAstandards.htm, accessed 21 October 2011.

Hooper, L. 1981 Trails and Walks: Inventory/Maintenance Guide. Denver Service Center, National Park Service.

Knapp, Karl and  Meyer, Kevin.  2011.  Workshop Talk: Trail Factor Triangle, given 28 March2011.

Meyer, Kevin G.. 2011. DRAFT: A Comprehensive Framework for Off-Highway Vehicle Trail Management. 1123 2804. Missoula, MT: U.S. Department of Agriculture, Forest Service, Missoula Technology and Development Center.

Basch, D., Duffy, H. Giordanengo, J., Seabloom, G. 2007. Guide to Sustainable Mountain Trails: Assessment, Planning & Design Sketchbook, 2007 Edition.  Denver Service Center, National Park Service.

National Park Service.  2007.  History and Culture.  Sunset Crater Volcano National Monument, http://www.nps.gov/sucr/historyculture/index.htm, accessed 21 October 2011.

National Park Service.  2008.  Appendix A.  Federal Trail Data Standards (FTDS) Version 1 Trail Fundamentals, http://www.nps.gov/gis/trails/Doc2/Appendix%20A.pdf, accessed 21 October 2011.

National Park Service.  2011.  NPS Stats, http://www.nature.nps.gov/stats/viewReport.cfm, accessed 21 October 2011.

National Park Service.  Mission, http://www.nps.gov/aboutus/mission.htm, accessed 21 October 2011.

Office of the President of the United States, 2007 Executive Order 13423 of January 24, 2007  Strengthening Federal Environmental, Energy, and Transportation

Management.  Federal Register, Vol. 72, No. 17

Office of the President of the United States Executive Order 13514 of October 5, 2009 Federal Leadership in Environmental, Energy, and Economic Performance.  Federal Register, Vol. 74, No. 194

Smithsonian National Museum of Natural History.  2011.  Sunset Crater.  Global Volcanism Program, http://www.volcano.si.edu/world/volcano.cfm?vnum=1209-02-, accessed 21 October 2011.

Sunset Crater Volcano 2002 General Management Plan, Final Environmental Impact Statement.  National Park Service, Flagstaff Area National Monuments, Flagstaff, AZ..

United States Botanic Garden, 2011Guidance for Federal Agencies on Sustainable Practices for Designed Landscapes.  Washington, DC: Office of the Architect of the Capitol.

United States Forest Service. 2011 Trail Fundamentals and Trail Management Objectives Training Reference Package.  http://www.fs.fed.us/recreation/programs/trail-management/trail-fundamentals/Fundamentals_Trng_Pkg_05_01_2011.pdf.

United States Geological Survey.  2002. Arizona Volcanoes and Volcanics,  http://vulcan.wr.usgs.gov/Volcanoes/Arizona/description_arizona_volcanoes.html, accessed 21 October 2011.

Thornberry-Ehrlich, T. 2005. Sunset Crater Volcano National Monument Geologic Resource Evaluation Report. Natural Resource Report NPS/NRPC/GRD/NRR—2005/004. National Park Service, Denver, Colorado.

# Western Regional Climate Center.  2011.  Sunset Crater Natl Monu, Arizona (028329) Period of Record Monthly Climate Summary Historical Climate Information, http://www.wrcc.dri.edu/cgi-bin/cliMAIN.pl?az8329, accessed 21 October 2011.

Appendix A – Trail Feature Diagrams

Appendix A contains diagrams illustrating methods for construction and maintenance of common trail features that are typically used.  All diagrams in Appendix A are courtesy of Karl Knapp of the California State Parks Trail Program. They were used as illustrations in the 1991 Trails Handbook for California State Parks.

Table of Contents

Figure A1 – Drain Dip						Page 79

Figure A2 – Trailway Excavations (1)				Page 80

Figure A3 – Trailway Excavations (2)				Page 81

Figure A4 – Slough and Berm Removal				Page 82

Figure A5 – Clearing and Grubbing				Page 83

Figure A6 – Brushing Maintenance				Page 84

Figure A7 – Cleaning a Waterbar					Page 85

Figure A8 – Turnpike						Page 86

Figure A9 – Causeway						Page 87

Figure A10 – Typical Rehab for Trail Reroute			Page 88

Figure A11 – Cable Steps						Page 89

Figure A12 – Drywall Fundamentals				Page 90

Figure A13 – Laying Rock						Page 91

Figure A14 – Multi-Tier Rock Wall					Page 92

Figure A15 – Rock Steps						Page 93

Figure A16 – Metal Culvert						Page 94

Figure A17 – Rock Culvert						Page 95

Figure A18 – Hip Truss Bridge					Page 96

Figure A19 – Rock Waterbar					Page 97

Figure A20 – Typical Check Dam					Page 98

Figure A21 – Typical Switchback Details (1)			Page 99

Figure A22 – Typical Switchback Details (2)			Page 100

Appendix A – Figure 1

California State Parks, 1991, 9-4

Appendix A – Figure 2

California State Parks, 1991, 10-11

Appendix A – Figure 3

California State Parks, 1991, 10-12

Appendix A – Figure 4

California State Parks 1991, 8-3

Appendix A – Figure 5

California State Parks, 1991, 6-5

Appendix A – Figure 6

California State Parks, 1991, 7-3

Appendix A – Figure 7

California State Parks, 1991, 9-9

Appendix A – Figure 8

California State Parks, 1991, 9-19

Appendix A – Figure 9

California State Parks, 1991, 9-20

Appendix A – Figure 10

California State Parks, 1991, 20-6

Appendix A – Figure 11

California State Parks, 1991, 11-12

Appendix A – Figure 12California State Parks, 1991, 14-4

Appendix A – Figure 13

California State Parks, 1991, 14-6

Appendix A – Figure 14

California State Parks, 1991, 14-4

Appendix A – Figure 15

California State Parks, 1991, 11-6

Appendix A – Figure 16

California State Parks, 1991, 9-12

Appendix A – Figure 17

California State Parks, 1991, 9-17

Appendix A – Figure 18

California State Parks, 1991, 13-14

Appendix A – Figure 19

California State Parks, 1991, 9-8

Appendix A – Figure 20

California State Parks, 1991, 20-9

Appendix A – Figure 21

Califorbia State Parks, 1991, 10-14

Appendix A – Figure 22

California State Parks, 1991, 10-14

Appendix B – Trail Prescriptions

Appendix B contains field notes of trail prescriptions written for each proposed trail.  The prescriptions describe actions that need to be performed during trail construction.   In order to note the location where specific actions need to be performed, a measuring wheel is used to measure distance in relation to a trail segment’s starting point.  The numbers in “Begin Feet” and “End Feet” columns indicate this distance.  Dimensions of structures are subsequently used to estimate trail construction costs.  Detailed cost estimates that were developed from the trail prescriptions can be found in Appendix C.

Table of Contents

- Campground Connector Trail					Page 102

  - Existing Trail Improvement

  - Park Boundary to Lenox Crater TH

  - Hill Climb Bypass Realignment

  - Overlook Spur 1

  - Overlook Spur 2

  - Visitor Center Realignment

- Lava Loop Trail							Page 110

- Lenox Crater Trail – Existing Trail Obliteration		Page 111

- Lenox Lava Flow Connector Trail				Page 112

- Lenox Loop Trail							Page 114

  - North (Ascending) Leg

  - South (Descending) Leg

- Lava Overlook Trail						Page 121

| Trail: |  | Campground Connector Trail |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | Existing Trail Improvement |  |  |  |  | Land Unit: | SUCR |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute | Size/Qty |  |  | Units | Comment | Total |
|  |  |  |  |  | # L | # H | # W |  |  |  |
| 0 |  | Monitor | Segment Begins |  |  |  |  |  | ParkBoundary |  |
| 0 | 2836 | Construct | Causeway | Distance >1800'<2500' | 2836.0 | 1.0 | 2.0 | cu ft |  | 5672.0 |
| 0 | 2836 | Construct | Trail Construction | Hillslope <20% | 2836.0 |  |  | lin ft |  | 2836.0 |
| 0 | 2836 | Install | Trail Hardening Aggregate Surfacing | Distance >1800'<2500' | 2836.0 | 0.5 | 3.0 | cu ft |  | 4254.0 |
| 332 |  |  | Trail Junction |  |  |  |  |  |  |  |
| 1300 |  |  | Trail Junction |  |  |  |  |  |  |  |
| 1474 |  | Excavate | Rock | rock medium | 1.0 | 0.5 | 1.0 | cu ft |  | 0.5 |
| 1499 |  | Excavate | Rock | rock medium | 1.0 | 0.5 | 1.0 | cu ft |  | 0.5 |
| 1513 |  | Monitor | View or Vista | Mountain |  |  |  |  |  |  |
| 2602 |  |  | Trail Junction |  |  |  |  |  |  |  |
| 2770 |  | Excavate | Rock | rock medium | 9.0 | 2.5 | 2.5 | cu ft |  | 56.3 |
| 2836 |  | Construct | Causeway | Distance >1300'<1800' | 22.0 | 1.0 | 2.0 | cu ft | step landing | 44.0 |
| 2836 |  | Excavate | Rock | rock medium | 12.0 | 3.0 | 4.0 | cu ft |  | 144.0 |
| 2836 |  | Construct | Steps | Rock Structural Framed | 12.0 | 1.0 | 4.0 | cu ft |  | 48.0 |
| 2836 |  | Construct | Trail Construction | Hillslope <20% | 22.0 |  |  | lin ft |  | 22.0 |
| 2836 |  | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 22.0 | 0.5 | 3.0 | cu ft | step landing | 33.0 |
| 2867 | 2924 | Construct | Causeway | Distance >1300'<1800' | 57.0 | 1.0 | 2.0 | cu ft |  | 114.0 |
| 2867 | 2924 | Construct | Trail Construction | Hillslope <20% | 57.0 |  |  | lin ft |  | 57.0 |
| 2867 | 2924 | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 57.0 | 0.5 | 3.0 |  |  | 85.5 |
| 2881 |  | Excavate | Rock | rock medium | 4.0 | 2.0 | 3.0 | cu ft |  | 24.0 |
| 2888 | 2892 | Remove | Trail Brushing Construction | Light | 4.0 |  |  | lin ft |  | 4.0 |
| 2913 |  | Excavate | Rock | rock medium | 2.0 | 3.0 | 2.5 | cu ft |  | 15.0 |
| 2924 |  | Construct | Causeway | Distance >1300'<1800' | 7.0 | 1.0 | 2.0 | cu ft | step landing | 14.0 |
| 2924 |  | Excavate | Rock | rock medium | 6.0 | 0.5 | 3.0 | cu ft |  | 9.0 |
| 2924 |  | Construct | Steps | Rock Structural Framed | 6.0 | 1.0 | 3.0 | cu ft |  | 18.0 |
| 2924 |  | Construct | Trail Construction | Hillslope <20% | 7.0 |  |  | lin ft |  | 7.0 |
| 2924 |  | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 7.0 | 0.5 | 3.0 | cu ft | step landing | 10.5 |
| 2936 | 2954 | Construct | Causeway | Distance >1300'<1800' | 18.0 | 1.0 | 2.0 | cu ft |  | 36.0 |
| 2936 | 2954 | Construct | Trail Construction | Hillslope <20% | 18.0 |  |  | lin ft |  | 18.0 |
| 2936 | 2954 | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 18.0 | 0.5 | 3.0 | cu ft |  | 27.0 |
| 2954 |  | Construct | Causeway | Distance >1300'<1800' | 6.0 | 1.0 | 2.0 | cu ft | step landing | 12.0 |
| 2954 |  | Excavate | Rock | rock medium | 2.0 | 0.5 | 3.0 | cu ft |  | 3.0 |
| 2954 |  | Construct | Steps | Rock Structural Framed | 2.0 | 1.0 | 3.0 | cu ft |  | 6.0 |
| 2954 |  | Construct | Trail Construction | Hillslope <20% | 6.0 |  |  | lin ft |  | 6.0 |
| 2954 |  | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 6.0 | 0.5 | 3.0 | cu ft | step landing | 9.0 |
| 2962 | 2971 | Construct | Causeway | Distance >1300'<1800' | 9.0 | 1.0 | 2.0 | cu ft |  | 18.0 |
| 2962 | 2971 | Construct | Trail Construction | Hillslope <20% | 9.0 |  |  | lin ft |  | 9.0 |
| 2962 | 2971 | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 9.0 | 0.5 | 3.0 | cu ft |  | 13.5 |
| 2971 |  | Excavate | Rock | rock medium | 9.0 | 0.5 | 3.0 | cu ft |  | 13.5 |
| 2971 |  | Construct | Steps | Rock Structural Framed | 9.0 | 1.0 | 3.0 | cu ft |  | 27.0 |
| 2980 | 2983 | Construct | Causeway | Distance >1300'<1800' | 3.0 | 1.0 | 2.0 | cu ft |  | 6.0 |
| 2980 | 2983 | Construct | Trail Construction | Hillslope <20% | 3.0 |  |  | lin ft |  | 3.0 |
| 2980 | 2983 | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 3.0 | 0.5 | 3.0 | cu ft |  | 4.5 |
| 2983 |  | Construct | Causeway | Distance >1300'<1800' | 6.0 | 1.0 | 2.0 | cu ft | step landing | 12.0 |
| 2983 |  | Excavate | Rock | rock medium | 3.0 | 0.5 | 3.0 | cu ft |  | 4.5 |
| 2983 |  | Construct | Steps | Rock Structural Framed | 3.0 | 1.0 | 3.0 | cu ft |  | 9.0 |
| 2983 |  | Construct | Trail Construction | Hillslope <20% | 6.0 |  |  | lin ft |  | 6.0 |
| 2983 |  | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 6.0 | 0.5 | 3.0 | cu ft | step landing | 9.0 |
| 2992 | 3031 | Construct | Causeway | Distance >1300'<1800' | 39.0 | 1.0 | 2.0 | cu ft |  | 78.0 |
| 2992 | 3031 | Construct | Trail Construction | Hillslope <20% | 39.0 |  |  | lin ft |  | 39.0 |
| 2992 | 3031 | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 39.0 | 0.5 | 3.0 | cu ft |  | 58.5 |
| 3031 |  | Excavate | Rock | rock medium | 2.0 | 0.5 | 3.0 | cu ft |  | 3.0 |
| 3031 |  | Construct | Steps | Rock Structural-framed | 2.0 | 1.0 | 3.0 | cu ft |  | 6.0 |
| 3032 | 3145 | Construct | Causeway | Distance >1300'<1800' | 113.0 | 1.0 | 2.0 | cu ft |  | 226.0 |
| 3032 | 3145 | Construct | Trail Construction | Hillslope <20% | 113.0 |  |  | lin ft |  | 113.0 |
| 3032 | 3145 | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 113.0 | 0.5 | 3.0 | cu ft |  | 169.5 |
| 3095 |  | Excavate | Rock | rock medium | 2.0 | 1.0 | 1.0 | cu ft |  | 2.0 |
| 3103 |  | Excavate | Rock | rock medium | 3.0 | 2.0 | 1.0 | cu ft |  | 6.0 |
| 3141 |  | Excavate | Rock | rock medium | 3.0 | 1.0 | 1.0 | cu ft |  | 3.0 |
| 3145 |  | Construct | Causeway | Distance >1300'<1800' | 26.0 | 1.0 | 2.0 | cu ft | step landing | 52.0 |
| 3145 |  | Excavate | Rock | rock medium | 12.0 | 0.5 | 3.0 | cu ft |  | 18.0 |
| 3145 |  | Construct | Steps | Rock Structural Framed | 12.0 | 1.0 | 3.0 | cu ft |  | 36.0 |
| 3145 |  | Construct | Trail Construction | Hillslope <20% | 26.0 |  |  | lin ft |  | 26.0 |
| 3145 |  | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 26.0 | 0.5 | 3.0 | cu ft | step landing | 39.0 |
| 3187 | 3441 | Construct | Causeway | Distance >1300'<1800' | 254.0 | 1.0 | 2.0 | cu ft |  | 254.0 |
| 3187 | 3441 | Construct | Trail Construction | Hillslope <20% | 254.0 |  |  | lin ft |  | 508.0 |
| 3187 | 3441 | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' | 254.0 | 0.5 | 3.0 | cu ft |  | 381.0 |
| 3441 |  | Construct | Causeway | Distance >800'<1300' | 18.0 | 1.0 | 2.0 | cu ft | step landing | 36.0 |
| 3441 |  | Excavate | rock | rock medium | 10.0 | 0.5 | 3.0 | cu ft |  | 15.0 |
| 3441 |  | Construct | steps | Rock Structural Framed | 10.0 | 1.0 | 3.0 | cu ft |  | 30.0 |
| 3441 |  | Construct | Trail Construction | Hillslope <20% | 18.0 |  |  | lin ft |  | 18.0 |
| 3441 |  | Install | Trail Hardening Aggregate Surfacing | Distance >800'<1300' | 18.0 | 0.5 | 3.0 | cu ft | step landing | 27.0 |
| 3472 | 4291 | Construct | Causeway | Distance >800'<1300' | 819.0 | 1.0 | 2.0 | cu ft |  | 1638.0 |
| 3472 | 4291 | Construct | Trail Construction | Hillslope <20% | 819.0 |  |  | lin ft |  | 819.0 |
| 3472 | 4291 | Install | Trail Hardening Aggregate Surfacing | Distance >800'<1300' | 819.0 | 0.5 | 3.0 | cu ft |  | 1228.5 |
| 4278 |  | Excavate | rock | rock medium | 6.0 | 1.0 | 1.0 | cu ft |  | 6.0 |
| 4289 |  | Remove | Stump Removal Partial Stump Removal by chainsaw |  | 1.0 |  |  | ea |  | 1.0 |
| 4291 |  | Construct | Causeway | Distance >300'<800' | 5.0 | 1.0 | 2.0 | cu ft | step landing | 10.0 |
| 4291 |  | Excavate | Rock | rock medium | 5.0 | 0.5 | 3.0 | cu ft |  | 7.5 |
| 4291 |  | Construct | Steps | Rock Structural Framed | 5.0 | 1.0 | 3.0 | cu ft |  | 15.0 |
| 4291 |  | Construct | Trail Construction | Hillslope <20% | 5.0 |  |  | lin ft |  | 5.0 |
| 4291 |  | Install | Trail Hardening Aggregate Surfacing | Distance >300'<800' | 5.0 | 0.5 | 3.0 | cu ft | step landing | 7.5 |
| 4306 | 4662 | Construct | Causeway | Distance <300' | 356.0 | 1.0 | 2.0 | cu ft |  | 712.0 |
| 4306 | 4662 | Construct | Trail Construction | Hillslope <20% | 356.0 |  |  | lin ft |  | 356.0 |
| 4306 | 4662 | Install | Trail Hardening AggregateSurfacing | Distance <300' | 356.0 | 0.5 | 3.0 | cu ft |  | 534.0 |
| 4662 |  |  | Segment Ends |  |  |  |  |  | At Campground East End |  |
| 0 |  |  | Segment Begins |  |  |  |  |  | Campground, South Terminus of Restroom Sidewalk |  |
| 0 | 153 | Construct | Causeway | Distance <300' | 153.0 | 1.0 | 2.0 | cu ft | Campground to VC Connector | 306.0 |
| 0 | 153 | Construct | Trail Construction | Hillslope <20% | 153.0 |  |  | lin ft | Campground to VC Connector | 153.0 |
| 0 | 153 | Install | Trail Hardening Aggregate Surfacing | Distance <300' | 153.0 | 0.5 | 3.0 | cu ft | Campground to VC Connector | 229.5 |
| 0 |  |  | Segment Ends |  |  |  |  |  | At Junction with VC Connector |  |

| Trail: |  |  |  | Campground Connector Trail |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Segment | Park Boundary to Lenox Crater TH |  |  |  |  |  |  |  | Land Unit: | SUCR |  |
| Begin Feet | End Feet |  | Action |  | Feature | Feature Attribute |  | Size/Qty |  |  |  |  | Units | Comment | Total |
|  |  |  |  |  |  |  |  | L | H |  | W |  |  |  |  |
| 0 |  |  | Monitor |  | Segment Begins |  |  |  |  |  |  |  |  | Park Boundary |  |
| 0 | 1289 |  | Construct |  | Causeway |  |  | 1289.0 | 1.0 |  | 2.0 |  | Cu ft |  | 2578.0 |
| 0 | 1289 |  | Construct |  | Trail Construction | Hillslope <20% |  | 1289.0 |  |  |  |  | Lin ft |  | 1289.0 |
| 0 | 2919 |  | Install |  | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' |  | 2919.0 | 0.5 |  | 3.0 |  | cu ft |  | 4378.5 |
| 996 |  |  | Perform |  | Misc Labor |  |  | 3.0 |  |  |  |  | hrs | Stump Removal | 3.0 |
| 1079 |  |  | Perform |  | Misc Labor |  |  | 1.0 |  |  |  |  | hrs | Tree Removal | 1.0 |
| 1289 | 1304 |  | Excavate |  | Soil | soil soft |  | 15.0 | 3.0 |  | 4.0 |  | cu ft | For retaining wall - culverts | 180.0 |
| 1289 | 1304 |  | Construct |  | Retaining Wall Rock Multi Tier |  |  | 15.0 | 3.0 |  | 4.0 |  | Cu ft | Over culverts | 180.0 |
| 1289 |  |  |  |  | Culvert ABS Plastic Single Wall | Culvert Dia 1.5' |  | 2.0 |  |  |  |  | ea |  | 2.0 |
| 1304 | 2919 |  | Construct |  | Causeway |  |  | 1615.0 | 1.0 |  | 2.0 |  | Cu ft |  | 3230.0 |
| 1304 | 2919 |  | Construct |  | Trail Construction | Hillslope <20% |  | 1615.0 |  |  |  |  | Lin ft |  | 1615.0 |
| 1557 | 1575 |  | Perform |  | Trail Brushing Construction | Heavy |  | 18.0 |  |  |  |  | Lin ft |  | 18.0 |
| 1774 |  |  | Perform |  | Misc Labor |  |  | 1.0 |  |  |  |  | hrs | Limbing | 1.0 |
| 2014 | 2614 |  | Excavate |  | Rock | rock medium |  | 600.0 | 1.0 |  | 3.0 |  | Cu ft |  | 1800.0 |
| 2390 |  |  | Construct |  | Causeway |  |  | 127.0 | 1.0 |  | 1.0 |  | Cu ft | Overlook | 127.0 |
| 2390 |  |  | Install |  | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' |  | 30.0 | 0.5 |  | 30.0 |  | Cu ft | Overlook | 450.0 |
| 2919 | 3666 |  | Construct |  | Trail Construction | Hillslope >20%<40% |  | 747.0 |  |  |  |  | Lin ft | On Lava Flow | 747.0 |
| 2919 | 3637 |  | Construct |  | Trail Hardening Rip Rap |  |  | 718.0 | 1.0 |  | 3.0 |  | Cu ft |  | 2154.0 |
| 2919 | 3637 |  | Gather |  | Rock | rock medium |  | 718.0 | 1.0 |  | 3.0 |  | Cu ft |  | 2154.0 |
| 2922 |  |  | Install |  | Rock Crush Fill | Distance <300' |  | 2.0 | 4.0 |  | 3.0 |  | Cu ft |  | 24.0 |
| 2927 |  |  | Excavate |  | Rock | rock medium |  | 2.0 | 4.0 |  | 3.0 |  | Cu ft |  | 24.0 |
| 2936 | 2950 |  | Install |  | Rock Crush Fill | Distance <300' |  | 14.0 | 3.0 |  | 3.0 |  | cu ft |  | 126.0 |
| 2959 | 2976 |  | Excavate |  | rock | rock medium |  | 17.0 | 2.0 |  | 3.0 |  | Cu ft |  | 102.0 |
| 3014 | 3024 |  | Install |  | Rock Crush Fill | Distance <300' |  | 10.0 | 3.0 |  | 3.0 |  | Cu ft |  | 90.0 |
| 3024 | 3045 |  | Excavate |  | Rock | rock medium |  | 21.0 | 3.0 |  | 3.0 |  | Cu ft |  | 189.0 |
| 3045 | 3129 |  | Install |  | Rock Crush Fill | Distance <300' |  | 84.0 | 4.0 |  | 3.0 |  | Cu ft |  | 1008.0 |
| 3182 | 3193 |  | Install |  | Rock Crush Fill | Distance <300' |  | 11.0 | 1.0 |  | 3.0 |  | Cu ft |  | 33.0 |
| 3300 | 3322 |  | Construct |  | Retaining Wall Rock Non Structural junk wall | Junk wall small rock |  | 22.0 | 4.0 |  | 3.0 |  | Cu ft |  | 264.0 |
| 3334 | 3373 |  | Install |  | Rock Crush Fill | Distance <300' |  | 39.0 | 2.0 |  | 3.0 |  | Cu ft |  | 234.0 |
| 3400 | 3404 |  | Install |  | Rock Crush Fill | Distance <300' |  | 4.0 | 1.0 |  | 3.0 |  | Cu ft |  | 12.0 |
| 3520 | 3525 |  | Install |  | Rock Crush Fill | Distance <300' |  | 5.0 | 2.0 |  | 3.0 |  | Cu ft |  | 30.0 |
| 3552 | 3558 |  | Excavate |  | rock | rock medium |  | 6.0 | 2.0 |  | 3.0 |  | Cu ft |  | 36.0 |
| 3558 | 3562 |  | Construct |  | Retaining Wall Rock Non Structural junk wall | Junk wall small rock |  | 4.0 | 4.0 |  | 4.0 |  | Cu ft |  | 64.0 |
| 3559 | 3568 |  | Excavate |  | rock | rock medium |  | 9.0 | 1.0 |  | 3.0 |  | Cu ft |  | 27.0 |
| 3603 | 3613 |  | Install |  | Rock Crush Fill |  |  | 10.0 | 3.0 |  | 4.0 |  | Cu ft |  | 120.0 |
| 3617 | 3666 |  | Construct |  | Causeway |  |  | 49.0 | 1.0 |  | 2.0 |  | Cu ft |  | 98.0 |
| 3618 | 3666 |  | Perform |  | Trail Brushing Construction | Medium |  | 48.0 |  |  |  |  | Lin ft |  | 48.0 |
| 3666 |  |  | Monitor |  | Segment Ends |  |  |  |  |  |  |  |  | At Lenox Crater TH |  |

| Trail: |  | Campground Connector Trail |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | Hill Climb Bypass Realignment |  |  |  |  |  |  |  |  | Land Unit: |  | SUCR |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute |  | Size/Qty |  |  |  | Units |  |  | Comment |  | Total |
|  |  |  |  |  |  | L | H | W |  |  |  |  |  |  |  |
| 0 | 0 | Monitor | Segment Begins |  |  |  |  |  |  |  |  |  | Southern Terminus |  |  |
| ## 0 | ## 765 | ## Construct | ## Causeway | ## Distance >300'<800' |  | ## 765.0 | ## 1.0 | ## 2.0 |  | ## cu ft |  |  |  |  | ## 1530.0 |
| ## 0 | ## 765 | ## Construct | ## Trail Construction | ## Hillslope <20% |  | ## 765.0 |  |  |  | ## lin ft |  |  |  |  | ## 765.0 |
| ## 0 | ## 765 | ## Install | ## Trail Hardening Aggregate Surfacing | ## Distance >300'<800' |  | ## 765.0 | ## 0.5 | ## 3.0 |  | ## cu ft |  |  |  |  | ## 1147.5 |
| ## 101 | ## 109 | ## Excavate | ## Rock | ## rock medium |  | ## 8.0 | ## 1.5 | ## 3.0 |  |  |  |  |  |  | ## 36.0 |
| 765 |  | Monitor | Segment Ends |  |  |  |  |  |  |  |  |  | Northern Terminus |  |  |

| Trail: |  | Campground Connector Trail |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | Overlook Spur 1 |  |  |  |  |  |  |  |  |  |  | Land Unit: |  |  | SUCR |  |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute |  | Size/Qty |  |  |  |  | Units |  |  |  | Comment |  |  | Total |  |
|  |  |  |  |  |  | L | H | W |  |  |  |  |  |  |  |  |  |  |  |
| 0 |  | Monitor | Segment Begins |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 0 | 26 | Construct | Causeway | Distance >1800'<2500' |  | 26.0 | 1.0 | 2.0 |  |  | cu ft |  |  |  |  |  |  | 52.0 |  |
| 0 | 26 | Construct | Trail Construction | Hillslope <20% |  | 26.0 |  |  |  |  | lin ft |  |  |  |  |  |  | 26.0 |  |
| 0 | 26 | Install | Trail Hardening Aggregate Surfacing | Distance >1800'<2500' |  | 26.0 | 0.5 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 39.0 |  |
| 26 |  | Excavate | Rock | rock medium |  | 6.0 | 0.5 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 9.0 |  |
| 26 |  | Construct | Steps | Rock Structural Framed |  | 6.0 | 1.0 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 18.0 |  |
| 32 | 41 | Construct | Causeway | Distance >1800'<2500' |  | 9.0 | 1.0 | 2.0 |  |  | cu ft |  |  |  |  |  |  | 18.0 |  |
| 32 | 41 | Construct | Trail Construction | Hillslope <20% |  | 9.0 |  |  |  |  | lin ft |  |  |  |  |  |  | 9.0 |  |
| 32 | 41 | Install | Trail Hardening Aggregate Surfacing | Distance >1800'<2500' |  | 9.0 | 0.5 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 13.5 |  |
| 35 |  | Excavate | Rock | rock medium |  | 14.0 | 0.5 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 21.0 |  |
| 35 |  | Construct | Steps | Rock Structural Framed |  | 14.0 | 1.0 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 42.0 |  |
| 55 | 81 | Construct | Causeway | Distance >1800'<2500' |  | 26.0 | 1.0 | 2.0 |  |  | cu ft |  |  |  |  |  |  | 52.0 |  |
| 55 | 81 | Construct | Trail Construction | Hillslope <20% |  | 26.0 |  |  |  |  | lin ft |  |  |  |  |  |  | 26.0 |  |
| 55 | 81 | Install | Trail Hardening Aggregate Surfacing | Distance >1800'<2500' |  | 26.0 | 0.5 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 39.0 |  |
| 82 |  | Excavate | Rock | rock medium |  | 10.0 | 0.5 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 15.0 |  |
| 82 |  | Construct | Steps | Rock Structural Framed |  | 10.0 | 1.0 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 30.0 |  |
| 92 | 103 | Construct | Causeway | Distance >1800'<2500' |  | 11.0 | 1.0 | 2.0 |  |  | cu ft |  |  |  |  |  |  | 22.0 |  |
| 92 | 103 | Construct | Trail Construction | Hillslope <20% |  | 11.0 |  |  |  |  | lin ft |  |  |  |  |  |  | 11.0 |  |
| 92 | 103 | Install | Trail Hardening Aggregate Surfacing | Distance >1800'<2500' |  | 11.0 | 0.5 | 3.0 |  |  | cu ft |  |  |  |  |  |  | 16.5 |  |
| 103 |  | Install | Interpretive Panel |  |  | 1.0 |  |  |  |  | ea |  |  |  |  |  |  | 1.0 |  |
| 103 |  | Monitor | View or Vista | Mountian |  | 1.0 |  |  |  |  | ea |  |  |  |  |  |  | 1.0 |  |
| 103 |  | Monitor | Segment Ends |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trail: |  | Campground Connector Trail |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Segment | Overlook Spur 2 |  |  |  |  |  |  |  |  | Land Unit: |  |  |  | SUCR |  |  |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute |  | Size/Qty |  |  |  | Units |  |  |  |  |  | Comment |  | Total |  |
|  |  |  |  |  |  | L | H | W |  |  |  |  |  |  |  |  |  |  |  |
|  |  | construct | Cable steps |  |  | 65.0 | 7.0 | 6.0 |  |  |  |  |  |  |  |  |  | 2730.0 |  |
|  |  | ## Construct | ## causeway | ## Distance >1300'<1800' |  | ## 31.0 | ## 1.0 | ## 2.0 |  | ## cu ft |  |  |  |  |  |  |  | ## 62.0 |  |
|  |  | ## Construct | ## causeway | ## Distance >1300'<1800' |  | ## 16.0 | ## 1.0 | ## 2.0 |  | ## cu ft |  |  |  |  |  |  |  | ## 32.0 |  |
|  |  | excavate | rock | rock medium |  | 7.0 | 0.5 | 3.0 |  | cu ft |  |  |  |  |  |  |  | 10.5 |  |
|  |  | construct | Steps | Rock Structural Framed |  | 7.0 | 1.0 | 3.0 |  | cu ft |  |  |  |  |  |  |  | 21.0 |  |
|  |  | ## construct | ## Trail Construction | ## Hillslope <20% |  | ## 31.0 |  |  |  | ## lin ft |  |  |  |  |  |  |  | ## 31.0 |  |
|  |  | ## construct | ## Trail Construction | ## Hillslope <20% |  | ## 16.0 |  |  |  | ## lin ft |  |  |  |  |  |  |  | ## 16.0 |  |
|  |  | ## install | ## Trail Hardening Aggregate Surfacing | ## Distance >1300'<1800' |  | ## 31.0 | ## 0.5 | ## 3.0 |  | ## cu ft |  |  |  |  |  |  |  | ## 46.5 |  |
|  |  | ## install | ## Trail Hardening Aggregate Surfacing | ## Distance >1300'<1800' |  | ## 16.0 | ## 0.5 | ## 3.0 |  | ## cu ft |  |  |  |  |  |  |  | ## 24.0 |  |

| Trail: |  | Campground Connector Trail |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | Visitor Center Realignment |  |  |  |  |  |  | Land Unit: | SUCR |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute |  | Size/Qty |  |  |  | Units | Comment | Total |
|  |  |  |  |  |  | L | H |  | W |  |  |  |
| 0 | 0 | Monitor | Segment Begins |  |  |  |  |  |  |  | At Visitor Center Parking |  |
| 0 | 64 | Construct | Causeway | Distance <300' |  | 64.0 | 1.0 |  | 2.0 | cu ft |  | 128.0 |
| 0 | 64 | Construct | Trail Construction | Hillslope <20% |  | 64.0 |  |  |  | lin ft |  | 64.0 |
| 0 | 64 | Install | Trail Hardening Aggregate Surfacing | Distance <300' |  | 64.0 | 0.5 |  | 3.0 | cu ft |  | 96.0 |
| 35 | 45 | Excavate | Rock | rock soft |  | 10.0 | 0.5 |  | 3.0 | cu ft |  | 15.0 |
| 64 | 95 | Monitor | Road Crossing |  |  | 31.0 |  |  |  | lin ft |  | 31.0 |
| 95 | 105 | Excavate | Rock | rock soft |  | 10.0 | 0.5 |  | 3.0 | cu ft |  | 15.0 |
| 95 | 1353 | Construct | Trail Construction | Hillslope <20% |  | 1258.0 |  |  |  | lin ft |  | 1258.0 |
| 95 | 3070 | Construct | Causeway | Distance >1300'<1800' |  | 2975.0 | 1.0 |  | 2.0 | cu ft |  | 5950.0 |
| 95 | 3070 | Install | Trail Hardening Aggregate Surfacing | Distance >1300'<1800' |  | 2975.0 | 0.5 |  | 3.0 | cu ft |  | 4462.5 |
| 550 |  | Remove | Down Tree Removal Chain Saw | Tree dia. 1'-3' |  | 1.0 |  |  |  | ea |  | 1.0 |
| 1353 | 2125 | Construct | Trail Construction | Hillslope >20%<40% |  | 772.0 |  |  |  | lin ft |  | 772.0 |
| 1353 |  | Construct | Drainage Dip Reverse Grade Dip |  |  | 1.0 |  |  |  | ea |  | 1.0 |
| 1580 | 1588 | Excavate | Rock | rock soft |  | 8.0 | 1.0 |  | 7.0 | cu ft |  | 56.0 |
| 1608 | 1614 | Excavate | Rock | rock soft |  | 6.0 | 0.5 |  | 5.0 | cu ft |  | 15.0 |
| 2125 | 3070 | Construct | Trail Construction | Hillslope <20% |  | 945.0 |  |  |  | lin ft |  | 945.0 |
| 3070 |  | Monitor | Segment Ends |  |  |  |  |  |  |  | Junction with Existing Trail |  |

| Trail: |  | Lava Loop Trail |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | Main |  |  |  |  |  | Land Unit: | SUCR |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute |  | Size/Qty |  |  | Units | Comment | Total |
|  |  |  |  |  |  | L | H | W |  |  |  |
| 0 |  |  | Segment Begins |  |  |  |  |  |  | Parking North (Lenox Crater TH) |  |
| 0 | 6 | Construct | Retaining Wall Rock Single Tier |  |  | 6.0 | 2.0 | 1.0 | cu ft | Right Side Wall | 12.0 |
| 0 | 6 | Construct | Retaining Wall Rock Single Tier |  |  | 6.0 | 2.0 | 1.0 | cu ft | Left Side Wall | 12.0 |
| 6 |  | Construct | Steps | Rock Structural Framed |  | 1.5 | 2.5 | 6.0 | cu ft | Top Step | 22.5 |
| 6 |  | Construct | Steps | Rock Structural Framed |  | 1.5 | 1.8 | 6.0 | cu ft | 2nd Step | 16.5 |
| 6 |  | Construct | Steps | Rock Structural Framed |  | 1.5 | 1.2 | 6.0 | cu ft | 3rd Step | 10.4 |
| 6 |  | Construct | Steps | Rock Structural Framed |  | 1.5 | 1.2 | 6.0 | cu ft | 4th Step | 10.4 |
| 6 |  | Construct | Steps | Rock Structural Framed |  | 1.5 | 1.2 | 6.0 | cu ft | Bottom Step | 10.4 |
| 0 | 6 | Excavate | Soil | soil soft |  | 6.0 | 1.0 | 1.5 | cu ft | Left Side Wall | 9.0 |
| 0 | 6 | Excavate | Soil | soil soft |  | 6.0 | 1.0 | 1.5 | cu ft | Right Side Wall | 9.0 |
| 15 | 25 | Construct | Retaining Wall Rock Single Tier |  |  | 10.0 | 2.0 | 1.5 | cu ft | Left Side Wall | 30.0 |
| 15 | 25 | Construct | Soil | soil soft |  | 10.0 | 1.0 | 1.5 | cu ft | Left Side Wall | 15.0 |
| 25 | 105 | Perform | Trail Construction | Hillslope <20% |  | 80.0 |  |  | lin ft |  | 80.0 |
| 105 | 130 | Construct | Retaining Wall Rock Non Structural junk wall | Junk wall small rock |  | 25.0 | 3.0 | 2.0 | cu ft |  | 150.0 |
| 130 | 251 | Perform | Trail Construction | Hillslope <20% |  | 121.0 |  |  | lin ft |  | 121.0 |
| 251 | 287 | Construct | Retaining Wall Rock Non Structural junk wall | Junk wall small rock |  | 36.0 | 3.0 | 2.0 | cu ft |  | 216.0 |
| 251 | 287 | Crush | Rock Crush Fill | Distance <300' |  | 36.0 | 1.0 | 2.0 | cu ft |  | 72.0 |
| 287 | 377 | Perform | Trail Construction | Hillslope <20% |  | 90.0 |  |  | lin ft |  | 90.0 |
| 377 | 387 | Construct | Retaining Wall Rock Non Structural junk wall | Junk wall large rock |  | 10.0 | 3.0 | 2.0 | cu ft |  | 60.0 |
| 377 | 387 | Crush | Rock Crush Fill | Distance <300' |  | 10.0 | 1.0 | 2.0 | cu ft |  | 20.0 |
| 387 | 797 | Perform | Trail Construction | Hillslope <20% |  | 410.0 |  |  | lin ft |  | 410.0 |
| 413 |  | Remove | Rock | rock hard |  | 4.0 |  |  | hrs | Grip Hoist Time | 4.0 |
| 415 |  | Remove | Rock | rock hard |  | 4.0 |  |  | hrs | Grip Hoist Time | 4.0 |
| 700 | 745 | Construct | Steps | Cable |  | 45.0 | 8.0 | 4.0 | cu ft | 14 Steps | 1440.0 |
| 700 |  | Excavate | Soil | soil soft |  | 1.0 | 1.0 | 2.0 | sq ft |  | 2.0 |
| 745 |  | Excavate | Soil | soil soft |  | 1.0 | 1.0 | 2.0 | sq ft |  | 2.0 |
| 745 | 797 | Construct | Steps | Cable |  | 52.0 | 8.0 | 4.0 | cu ft | 14 Steps | 1664.0 |
| 745 |  | Excavate | Soil | soil soft |  | 1.0 | 2.0 | 5.0 |  |  | 10.0 |
| 797 |  | Excavate | Soil | soil soft |  | 1.0 | 2.0 | 5.0 |  |  | 10.0 |
| 797 |  |  | Segment Ends |  |  |  |  |  |  | Parking South (Lenox Crater TH) |  |

| Trail: |  | Lenox Crater Trail |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | Existing Trail Obliteration |  |  |  |  |  |  | Land Unit: | SUCR |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute | Size/Qty |  |  |  |  | Units | Comment | Total |
|  |  |  |  |  | L |  | H |  | W |  |  |  |
| 0 |  |  | Segment Begins |  |  |  |  |  |  |  | Lenox Crater Trailhead |  |
| 0 | 46 | Remove | Trail Obliteration | Hillslope <20% | 46.0 |  | 17.0 |  |  | lin ft |  | 782.0 |
| 46 | 175 | Remove | Trail Obliteration | Hillslope <20% | 129.0 |  | 14.0 |  |  | lin ft |  | 1806.0 |
| 175 | 460 | Remove | Trail Obliteration | Hillslope <20% | 285.0 |  | 11.0 |  |  | lin ft |  | 3135.0 |
| 460 | 508 | Remove | Trail Obliteration | Hillslope <20% | 48.0 |  | 14.0 |  |  | lin ft |  | 672.0 |
| 482 |  |  | Climbing Turn |  | 1.0 |  |  |  |  | ea | center of climbing turn | 1.0 |
| 508 | 701 | Remove | Trail Obliteration | Hillslope >20%<40% | 193.0 |  | 12.0 |  |  | lin ft |  | 2316.0 |
| 701 | 761 | Remove | Trail Obliteration | Hillslope <20% | 60.0 |  | 27.0 |  |  | lin ft |  | 1620.0 |
| 735 |  |  | Climbing Turn |  | 1.0 |  |  |  |  | ea | center of climbing turn | 1.0 |
| 752 |  |  | Climbing Turn |  | 1.0 |  |  |  |  | ea | center of climbing turn | 1.0 |
| 761 | 1118 | Remove | Trail Obliteration | Hillslope <20% | 357.0 |  | 13.0 |  |  | lin ft |  | 4641.0 |
| 1033 |  |  | Sign Trail |  |  |  |  |  |  |  |  |  |
| 1071 |  |  | Sign Trail |  |  |  |  |  |  |  |  |  |
| 1071 | 1118 | Remove | Trail Obliteration | Hillslope <20% | 47.0 |  | 25.0 |  |  | lin ft |  | 1175.0 |
| 1118 |  | Construct | Steps | Log Check | 14.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 14.0 |
| 1118 | 1346 | Remove | Trail Obliteration | Hillslope <20% | 228.0 |  | 27.0 |  |  | lin ft |  | 6156.0 |
| 1165 |  | Construct | Steps | Log Check | 14.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 14.0 |
| 1190 |  | Construct | Steps | Log Check | 14.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 14.0 |
| 1215 |  | Construct | Steps | Log Check | 14.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 14.0 |
| 1240 |  | Construct | Steps | Log Check | 14.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 14.0 |
| 1325 |  | Construct | Steps | Log Check | 14.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 14.0 |
| 1325 | 1424 | Remove | Trail Obliteration | Hillslope <20% | 99.0 |  | 15.0 |  |  | lin ft |  | 1485.0 |
| 1426 | 1517 | Remove | Trail Obliteration | Level ground | 91.0 |  | 75.0 |  |  | lin ft | De-compaction | 6825.0 |
| 1600 | 1667 | Import | Fill Material | Distance >800'<1300' | 67.0 |  | 2.0 |  | 9.0 | cu ft | material from side bench construction | 1206.0 |
| 1600 | 1667 | Remove | Trail Obliteration | Hillslope <20% | 67.0 |  | 9.0 |  |  | lin ft |  | 603.0 |
| 1610 |  | Construct | Steps | Log Check | 9.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 9.0 |
| 1620 |  | Construct | Steps | Log Check | 9.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 9.0 |
| 1630 |  | Construct | Steps | Log Check | 9.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 9.0 |
| 1640 |  | Construct | Steps | Log Check | 9.0 |  | 1.0 |  | 1.0 | cu ft | logs within 100ft | 9.0 |
| 1667 |  |  | Segment Ends |  |  |  |  |  |  |  | Lenox Crater Summit |  |

| Trail: |  | Lenox - Lava Flow Connector Trail |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | Main |  |  |  |  |  |  |  | Land Unit: |  | SUCR |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute |  | Size/Qty |  |  | Units |  |  | Comment |  | Total |
|  |  |  |  |  |  | L | H | W |  |  |  |  |  |  |
| 0 |  | Monitor | Segment Begins |  |  |  |  |  |  |  |  | East end of Lenox Crater TH opposite side of road from parking lot |  |  |
| 0 | 2497 | Perform | Trail Brushing Construction | Light |  | 2497.0 |  |  | lin ft |  |  |  |  | 2497.0 |
| 0 | 5249 | Construct | Trail Construction | Hillslope <20% |  | 5249.0 |  |  | lin ft |  |  |  |  | 5249.0 |
| 0 | 5249 | Construct | Causeway |  |  | 5249.0 | 1.0 | 2.0 | cu ft |  |  |  |  | 10498.0 |
| 0 | 5249 | Install | Trail Hardening Aggregate Surfacing | Distance >300'<800' |  | 5249.0 | 0.5 | 3.0 | cu ft |  |  |  |  | 7873.5 |
| 136 |  | Excavate | Rock | rock medium |  | 8.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 8.0 |
| 155 |  | Excavate | Rock | rock medium |  | 2.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 2.0 |
| 159 |  | Construct | Steps | Rock Structural Framed |  |  |  |  |  |  |  |  |  |  |
| 190 |  | Excavate | Rock | rock medium |  | 2.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 2.0 |
| 223 |  | Excavate | Rock | rock medium |  | 5.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 5.0 |
| 263 |  | Excavate | Rock | rock medium |  | 12.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 12.0 |
| 282 |  | Excavate | Rock | rock medium |  | 5.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 5.0 |
| 294 |  | Excavate | Rock | rock medium |  | 1.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 1.0 |
| 338 |  | Excavate | rock | rock medium |  | 5.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 5.0 |
| 383 |  | excavate | rock | rock medium |  | 9.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 9.0 |
| 419 | 431 | Excavate | Rock | rock medium |  | 12.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 12.0 |
| 438 |  | Excavate | rock | rock medium |  | 5.0 | 3.0 | 2.0 | cu ft |  |  |  |  | 30.0 |
| 447 |  | Excavate | rock | rock medium |  | 4.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 4.0 |
| 464 |  | Excavate | rock | rock medium |  | 12.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 12.0 |
| 516 | 526 | Excavate | rock | rock medium |  | 10.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 10.0 |
| 609 |  | Construct | Causeway |  |  | 90.0 | 1.0 | 1.0 | cu ft |  |  | Viewing platform |  | 90.0 |
| 609 |  | Install | Trail Hardening Aggregate Surfacing | Distance >300'<800' |  | 30.0 | 0.5 | 30.0 | cu ft |  |  | Viewing platform |  | 450.0 |
| 609 |  | install | Interpretive Panel |  |  | 1.0 |  |  | ea |  |  | for viewing platform |  | 1.0 |
| 669 |  | Excavate | Rock | rock medium |  | 1.0 | 1.0 | 1.0 | cu ft |  |  |  |  | 1.0 |
| 827 | 850 | Excavate | Rock | rock medium |  | 23.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 69.0 |
| 890 | 909 | Excavate | Rock | rock medium |  | 19.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 57.0 |
| 1050 | 1084 | Excavate | Rock | rock medium |  | 34.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 102.0 |
| 1129 | 1164 | Excavate | rock | rock medium |  | 35.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 105.0 |
| 1238 | 1289 | Excavate | rock | rock medium |  | 51.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 153.0 |
| 1372 | 1402 | Excavate | rock | rock medium |  | 30.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 90.0 |
| 1468 | 1486 | Excavate | rock | rock medium |  | 18.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 54.0 |
| 1596 | 1617 | Excavate | Rock | rock medium |  | 21.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 63.0 |
| 1733 |  | construct | Causeway |  |  | 60.0 | 1.0 | 1.0 | cu ft |  |  | Viewing platform |  | 60.0 |
| 1733 |  | install | Trail Hardening Aggregate Surfacing | Distance >300'<800' |  | 20.0 | 0.5 | 20.0 | cu ft |  |  | Viewing Platform |  | 200.0 |
| 1733 |  | install | Interpretive Panel |  |  | 1.0 |  |  | ea |  |  | for viewing platform |  | 1.0 |
| 1893 |  | perform | Down Tree Removal Chain Saw | Tree dia. 1'-3' |  | 1.0 |  |  | ea |  |  |  |  | 1.0 |
| 2253 | 2265 | Excavate | rock | rock medium |  | 12.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 36.0 |
| 2379 | 2391 | Construct | Retaining Wall Rock Single Tier |  |  | 12.0 |  |  |  |  |  |  |  | 12.0 |
| 2614 | 2684 | Perform | Trail Brushing Construction | Light |  | 70.0 |  |  | lin ft |  |  |  |  | 70.0 |
| 2881 | 2896 | Excavate | rock | rock medium |  | 15.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 45.0 |
| 3105 | 3131 | Excavate | rock | rock medium |  | 26.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 78.0 |
| 3643 | 3660 | Excavate | rock | rock medium |  | 17.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 51.0 |
| 3806 | 3884 | Perform | Trail Brushing Construction | Light |  | 78.0 |  |  | lin ft |  |  |  |  | 78.0 |
| 4141 | 4154 | Excavate | rock | rock medium |  | 13.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 39.0 |
| 4180 | 4204 | Excavate | Rock | rock medium |  | 24.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 72.0 |
| 4498 | 4521 | Excavate | Rock | rock medium |  | 23.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 69.0 |
| 4555 | 4628 | Excavate | Rock | rock medium |  | 73.0 | 1.0 | 3.0 | cu ft |  |  |  |  | 219.0 |
| 4857 |  | Construct | Causeway |  |  | 27.0 | 1.0 | 2.0 | cu ft |  |  | approach to viewing platform |  | 54.0 |
| 4857 |  | Construct | Causeway |  |  | 27.0 | 0.5 | 3.0 | cu ft |  |  | approach to viewing platform |  | 40.5 |
| 4857 |  | Construct | Causeway |  |  | 77.0 | 1.0 | 1.0 | cu ft |  |  | overlook |  | 77.0 |
| 4857 |  | Install | Trail Hardening Aggregate Surfacing | Distance >300'<800' |  | 20.0 | 0.5 | 20.0 | cu ft |  |  |  |  | 200.0 |
| 4857 |  | Install | Interpretive Panel |  |  | 1.0 |  |  | ea |  |  |  |  | 1.0 |
| 5249 |  | Install | Sign Trail | Metal |  | 1.0 |  |  | ea |  |  | at junction with Lava Flow Trail |  | 1.0 |
| 5249 |  | Monitor | Segment Ends |  |  |  |  |  |  |  |  | at junction with Lava Flow Trail |  |  |

| Trail: |  | LENOX LOOP TRAIL |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | North (Ascending) Leg |  |  |  |  |  |  |  | Land Unit: | SUCR |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute |  | Size/Qty |  |  |  | Units |  | Comment | Total |
|  |  |  |  |  |  | L | H |  | W |  |  |  |  |
| 0 |  |  | Segment Begins |  |  |  |  |  |  |  |  | At Lenox Crater Trailhead |  |
| 0 |  | Install | Sign Trail | Metal |  | 1.0 |  |  |  | ea |  | at trail head | 1.0 |
| 0 |  | Remove | Sign Trail | Metal |  | 1.0 |  |  |  | ea |  | existing sign | 1.0 |
| 0 | 2018 | Perform | Trail Construction | Hillslope >20%<40% |  | 2018.0 |  |  |  | lin ft |  | hand construction | 2018.0 |
| 0 | 2862 | Perform | Trail Brushing Construction | Light |  | 2862.0 |  |  |  | lin ft |  |  | 2862.0 |
| 174 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | lava flow view/o leary | 1.0 |
| 242 |  | Perform | Misc. Labor |  |  | 1.0 |  |  |  | hrs |  | transport stump debris to trailhead | 1.0 |
| 242 |  | Perform | Stump Removal Partial Stump Removal by chainsaw | 0 |  | 17.0 |  |  |  | cu ft |  |  | 17.0 |
| 257 |  | Remove | Down Tree Removal Chain Saw | Tree dia. 1'-3' |  | 1.0 |  |  |  | ea |  |  | 1.0 |
| 257 |  | Perform | Misc. Labor |  |  | 1.0 |  |  |  | hrs |  | transport tree debris to trailhead | 1.0 |
| 372 |  | Perform | Down Tree Removal Chain Saw | Tree dia. 1'-3' |  | 1.0 |  |  |  | ea |  |  | 1.0 |
| 372 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | natural recycling wood debris | 1.0 |
| 404 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | survey marker/ bearing tree | 1.0 |
| 480 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | fire history | 1.0 |
| 557 |  | Perform | Misc. Labor |  |  | 2.0 |  |  |  | hrs |  | grub out stump | 2.0 |
| 629 |  | Construct | Swale | 0 |  | 1.0 |  |  |  | ea |  |  | 1.0 |
| 690 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | ponderosa pine | 1.0 |
| 716 |  | Construct | Swale |  |  | 1.0 |  |  |  | ea |  |  | 1.0 |
| 718 |  | Perform | Misc. Labor |  |  | 4.0 |  |  |  | hrs |  | tree/stump | 4.0 |
| 763 |  | Perform | Misc. Labor |  |  | 40.0 |  |  |  | hrs |  | remove down tree | 40.0 |
| 834 |  | Remove | Misc. Labor |  |  | 5.0 |  |  |  | hrs |  | remove tree(s)/stump, 4 | 5.0 |
| 861 |  | Remove | Stump Removal Partial Stump Removal by chainsaw | 0 |  | 9cf |  |  |  | cu ft |  |  | 9cf |
| 894 |  | Remove | Misc. Labor |  |  | 4.0 |  |  |  | hrs |  | tree/stump | 4.0 |
| 925 |  | Perform | Misc. Labor |  |  | 4.0 |  |  |  | hrs |  | tree/stump | 4.0 |
| 925 |  |  | Material Source |  |  |  |  |  |  |  |  | timber material for edge protection at WM 2030, 35 ln ft |  |
| 1085 |  | Remove | Misc. Labor |  |  | 1.0 |  |  |  | hrs |  | remove tree(s)/stump | 1.0 |
| 1095 |  | Remove | Misc. Labor |  |  | 1.0 |  |  |  | hrs |  | remove tree(s)/stump | 1.0 |
| 1110 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | moss | 1.0 |
| 1110 |  | Remove | Misc. Labor |  |  | 2.0 |  |  |  | hrs |  | remove tree(s)/stump | 2.0 |
| 1110 |  | Excavate | Soil | soil soft |  | 28.0 | 1.0 |  | 4.0 | cu ft |  | <100 ft | 112.0 |
| 1117 |  | Remove | Misc. Labor |  |  | 3.0 |  |  |  | hrs |  | remove tree(s)/stump, 1 | 3.0 |
| 1205 |  | Construct | Swale | 0 |  | 1.0 |  |  |  | ea |  |  | 1.0 |
| 1229 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | cinder pit in view shed | 1.0 |
| 1414 |  | Install | Bench | 0 |  | 1.0 |  |  |  | ea |  | shady spot | 1.0 |
| 1414 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | ponderosa old growth | 1.0 |
| 1414 |  | Import | Misc. Labor |  |  | 2.0 |  |  |  | hrs |  | transport bench from trailhead to site | 2.0 |
| 1414 |  | Construct | Retaining Wall Rock Multi Tier | 0 |  | 14.0 | 3.5 |  | 1.0 | cu ft |  |  | 49.0 |
| 1414 |  | Import | Rock Wall Rock | Distance >1300'<1800' |  | 14.0 | 3.5 |  | 1.0 | cu ft |  |  | 49.0 |
| 1414 |  | Export | Soil | soil soft |  | 25.0 | 3.5 |  | 5.0 | cu ft |  | <100 ft export | 437.5 |
| 1414 |  | Excavate | Soil | soil soft |  | 10.0 | 1.5 |  | 4.0 | cu ft |  | soil for bench platform | 60.0 |
| 1414 |  | Excavate | Soil | soil soft |  | 15.0 | 2.0 |  | 1.5 | cu ft |  | soil from wall foundation | 45.0 |
| 1414 |  | Construct | Swale | 0 |  | 1.0 |  |  |  | ea |  |  | 1.0 |
| 1452 |  | Construct | Swale | 0 |  | 1.0 |  |  |  | ea |  |  | 1.0 |
| 1665 |  | Remove | Misc. Labor |  |  | 1.0 |  |  |  | hrs |  | tree/stump | 1.0 |
| 1695 |  | Remove | Stump Removal Partial Stump Removal by chainsaw | 0 |  | 8cf |  |  |  | cu ft |  |  | 8cf |
| 1844 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | lava flow | 1.0 |
| 1852 |  | Remove | Down Tree Removal Chain Saw | Tree dia. 1'-3' |  | 1.0 |  |  |  | ea |  |  | 1.0 |
| 1919 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | ponderosa old growth | 1.0 |
| 2018 | 2862 | Construct | Trail Construction | Hillslope <20% |  | 844.0 |  |  |  | lin ft |  | on flat and fall line segments | 844.0 |
| 2030 | 2106 | Construct | Edge Protection | Wood Curb |  | 76.0 |  |  |  | lin ft |  |  | 76.0 |
| 2045 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | cinder cone crater/ etiquette | 1.0 |
| 2194 | 2253 | Construct | Edge Protection | Wood Curb |  | 59.0 |  |  |  | lin ft |  | native round PIPO-south edge | 59.0 |
| 2211 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | root structure | 1.0 |
| 2246 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | lichen | 1.0 |
| 2302 | 2393 | Construct | Edge Protection | Wood Curb |  | 91.0 |  |  |  | lin ft |  | native round PIPO-south edge | 91.0 |
| 2393 | 2485 | Construct | Edge Protection | Wood Curb |  | 92.0 | 2.0 |  |  | lin ft |  | ” | 184.0 |
| 2393 |  | Perform | Misc. Labor |  |  | 92.0 |  |  |  | hrs |  | gathering and transporting 224 ln ft of edge timbers | 92.0 |
| 2475 |  | Perform | Misc. Labor |  |  | 140.0 |  |  |  | hrs |  | gathering and transporting 344 ln ft of edge timbers | 140.0 |
| 2485 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | san francisco peaks | 1.0 |
| 2782 | 2862 | Construct | Edge Protection | Wood Curb |  | 80.0 | 2.0 |  |  | lin ft |  | native round PIPO-both edge | 160.0 |
| 2835 |  | Remove | Down Tree Removal Chain Saw | Tree dia. 1'-3' |  | 1.0 |  |  |  | ea |  |  | 1.0 |
| 2835 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | schultz fire | 1.0 |
| 2862 |  |  | Segment Ends |  |  |  |  |  |  |  |  | At Lenox Crater Summit |  |
| 2935 |  | Install | Interpretive Panel | 0 |  | 1.0 |  |  |  | ea |  | cinder crater viewpoint | 1.0 |

| Trail: |  | Lenox Loop Trail |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | South (Descending) Leg |  |  |  |  |  |  |  | Land Unit: | SUCR |  |
| # Begin # Feet | # End Feet | # Action | # Feature | # Feature Attribute |  | # Size/Qty |  |  |  | # Units |  | # Comment | # Total |
|  |  |  |  |  |  | # L | # H | # W |  |  |  |  |  |
| # 0 |  |  | # Segment Begins |  |  |  |  |  |  |  |  | # At Lenox Crater Summit |  |
| # 0 | # 84 | # Construct | # Retaining Wall Wood Log Turnpike | # Distance >150'<300' |  | # 84.0 | # 0.7 | # 1.0 |  | # sq ft |  | # Left Side Log | # 58.8 |
| # 0 | # 84 | # Construct | # Retaining Wall Wood Log Turnpike | # Distance >150'<300' |  | # 84.0 | # 0.7 | # 1.0 |  | # sq ft |  | # Right Side Log | # 58.8 |
| # 131 | # 278 | # Perform | # Trail Clearing Stob Removal | # Light |  | # 147.0 |  |  |  | # lin ft |  |  | # 147.0 |
| # 84 | # 400 | # Perform | # Trail Brushing Construction | # Light |  | # 316.0 |  |  |  | # lin ft |  |  | # 316.0 |
| # 84 | # 625 | # Perform | # Trail Construction | # Hillslope <20% |  | # 541.0 |  |  |  | # lin ft |  |  | # 541.0 |
| # 625 | # 804 | # Excavate | # Soil | # soil soft |  | # 179.0 | # 0.7 | # 1.0 |  | # cu ft |  | # Left Side Log | # 125.3 |
| # 625 | # 804 | # Excavate | # Soil | # soil soft |  | # 179.0 | # 0.7 | # 1.0 |  | # cu ft |  | # Right Side Log | # 125.3 |
| # 804 | # 868 | # Perform | # Trail Construction | # Hillslope <20% |  | # 64.0 |  |  |  | # lin ft |  |  | # 64.0 |
| # 955 | # 971 | # Construct | # Retaining Wall Rock Multi Tier |  |  | # 16.0 | # 3.0 | # 1.0 |  | # cu ft |  | # To Protect Tree | # 48.0 |
| # 955 | # 971 | # Import | # Rock Wall Rock | # Distance >1300'<1800' |  | # 16.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 48.0 |
| # 955 | # 971 | # Excavate | # Soil | # soil soft |  | # 16.0 | # 2.0 | # 1.5 |  | # cu ft |  |  | # 48.0 |
| # 955 | # 971 | # Import | # Rock Wall Rock | # Distance >1300'<1800' |  | # 16.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 48.0 |
| # 1081 | # 1111 | # Construct | # Retaining Wall Rock Multi Tier |  |  | # 30.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 90.0 |
| # 1081 | # 1111 | # Import | # Rock Wall Rock | # Distance >1300'<1800' |  | # 30.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 90.0 |
| # 1081 | # 1111 | # Excavate | # Soil | # soil soft |  | # 30.0 | # 2.0 | # 1.5 |  | # cu ft |  |  | # 90.0 |
| # 1081 | # 1111 | # Import | # Rock Wall Rock | # Distance >1300'<1800' |  | # 30.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 90.0 |
| # 1601 | # 1659 | # Perform | # Trail Clearing Stob Removal | # Light |  | # 58.0 |  |  |  | # lin ft |  |  | # 58.0 |
| # 1665 | # 1671 | # Construct | # Retaining Wall Rock Multi Tier |  |  | # 6.0 | # 3.0 | # 1.0 |  | # cu ft |  | # To Protect Tree | # 18.0 |
| # 1665 | # 1671 | # Excavate | # Soil | # soil soft |  | # 6.0 | # 2.0 | # 1.5 |  | # cu ft |  |  | # 18.0 |
| # 1665 | # 1671 | # Import | # Rock Wall Rock | # Distance >300'<800' |  | # 6.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 18.0 |
| # 1696 | # 1709 | # Construct | # Retaining Wall Rock Multi Tier |  |  | # 13.0 | # 3.0 | # 1.0 |  | # cu ft |  | # To Protect Tree | # 39.0 |
| # 1696 | # 1709 | # Excavate | # Soil | # soil soft |  | # 13.0 | # 2.0 | # 1.5 |  | # cu ft |  |  | # 39.0 |
| # 1696 | # 1709 | # Import | # Rock Wall Rock | # Distance >300'<800' |  | # 13.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 39.0 |
| # 1731 | # 1742 | # Construct | # Retaining Wall Rock Multi Tier |  |  | # 11.0 | # 3.0 | # 1.0 |  | # cu ft |  | # To Protect Tree | # 33.0 |
| # 1731 | # 1742 | # Excavate | # Soil | # soil soft |  | # 11.0 | # 2.0 | # 1.5 |  | # cu ft |  |  | # 33.0 |
| # 1731 | # 1742 | # Import | # Rock Wall Rock | # Distance >300'<800' |  | # 11.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 33.0 |
| # 1772 | # 1813 | # Construct | # Retaining Wall Rock Multi Tier |  |  | # 41.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 123.0 |
| # 1772 | # 1813 | # Excavate | # Soil | # soil soft |  | # 41.0 | # 2.0 | # 1.5 |  | # cu ft |  |  | # 123.0 |
| # 1772 | # 1813 | # Import | # Rock Wall Rock | # Distance >1300'<1800' |  | # 41.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 123.0 |
| # 2047 | # 2060 | # Construct | # Retaining Wall Rock Multi Tier |  |  | # 13.0 | # 3.0 | # 1.0 |  | # cu ft |  | # To Protect Tree | # 39.0 |
| # 2047 | # 2060 | # Excavate | # Soil | # soil soft |  | # 13.0 | # 2.0 | # 1.5 |  | # cu ft |  |  | # 39.0 |
| # 2047 | # 2060 | # Import | # Rock Wall Rock | # Distance >300'<800' |  | # 13.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 39.0 |
| # 868 | # 2180 | # Perform | # Trail Construction | # Hillslope >20%<40% |  | # 1312.0 |  |  |  | # lin ft |  |  | # 1312.0 |
| # 2182 | # 2208 | # Construct | # Retaining Wall Rock Multi Tier |  |  | # 26.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 78.0 |
| # 2182 | # 2208 | # Excavate | # Soil | # soil soft |  | # 26.0 | # 2.0 | # 1.5 |  | # cu ft |  |  | # 78.0 |
| # 2182 | # 2208 | # Import | # Rock Wall Rock | # Distance >300'<800' |  | # 26.0 | # 3.0 | # 1.0 |  | # cu ft |  |  | # 78.0 |
| # 804 | # 2700 | # Perform | # Trail Brushing Construction | # Light |  | # 1896.0 |  |  |  | # lin ft |  |  | # 1896.0 |
| # 2180 | # 2700 | # Perform | # Trail Construction | # Hillslope <20% |  | # 520.0 |  |  |  | # lin ft |  |  | # 520.0 |
| # 322 |  | # Remove | # Stump Removal Partial Stump Removal by chainsaw |  |  | # 1.0 |  |  |  | # hrs |  | # Time Required to remove stump | # 1.0 |
| # 851 |  | # Remove | # Tree |  |  | # 3.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 3.0 |
| # 851 |  | # Remove | # Tree |  |  | # 3.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 3.0 |
| # 868 |  | # Remove | # Tree |  |  | # 3.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 3.0 |
| # 868 |  | # Remove | # Tree |  |  | # 3.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 3.0 |
| # 1004 |  | # Remove | # Down Tree Removal Chain Saw | # Tree dia. 1'-3' |  | # 1.0 |  |  |  | # hrs |  |  | # 1.0 |
| # 1209 |  | # Remove | # Down Tree Removal Chain Saw | # Tree dia. 1'-3' |  | # 1.0 |  |  |  | # ea |  |  | # 1.0 |
| # 1322 |  |  | # Park Boundary |  |  | # 1.0 |  |  |  |  |  | # Entering back into Sunset Crater NM | # 1.0 |
| # 1433 |  | # Remove | # Tree |  |  | # 2.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 2.0 |
| # 1433 |  | # Remove | # Tree |  |  | # 2.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 2.0 |
| # 1452 |  | # Remove | # Tree |  |  | # 2.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 2.0 |
| # 1567 |  | # Perform | # Stump Removal Partial Stump Removal by chainsaw |  |  | # 2.0 |  |  |  | # hrs |  |  | # 2.0 |
| # 1567 |  | # Perform | # Stump Removal Partial Stump Removal by chainsaw |  |  | # 2.0 |  |  |  | # hrs |  |  | # 2.0 |
| # 1567 |  | # Perform | # Stump Removal Partial Stump Removal by chainsaw |  |  | # 2.0 |  |  |  | # hrs |  |  | # 2.0 |
| # 1688 |  | # Remove | # Tree |  |  | # 1.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 1.0 |
| # 1688 |  | # Remove | # Tree |  |  | # 1.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 1.0 |
| # 2021 |  | # Perform | # Stump Removal Partial Stump Removal by chainsaw |  |  | # 5.0 |  |  |  | # hrs |  | # Time Required to remove stump | # 5.0 |
| # 2056 |  | # Perform | # Stump Removal Partial Stump Removal by chainsaw |  |  | # 3.0 |  |  |  | # hrs |  | # Time Required to remove stump | # 3.0 |
| # 2368 |  | # Perform | # Stump Removal Partial Stump Removal by chainsaw |  |  | # 6.0 |  |  |  | # hrs |  | # Time Required to remove stump | # 6.0 |
| # 2531 |  | # Remove | # Tree |  |  | # 2.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 2.0 |
| # 2531 |  | # Remove | # Tree |  |  | # 2.0 |  |  |  | # hrs |  | # Less than 6" Diameter | # 2.0 |
| 2700 |  |  | Segment Ends |  |  |  |  |  |  |  |  | Lenox Crater Trailhead |  |

| Trail: |  | Lava Overlook Trail |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Segment | Main |  |  |  |  |  |  |  | Land Unit: | SUCR |  |
| Begin Feet | End Feet | Action | Feature | Feature Attribute |  | Size/Qty |  |  |  |  | Units | Comment | Total |
|  |  |  |  |  |  | L | H |  | W |  |  |  |  |
| 0 |  |  | Segment Begins |  |  |  |  |  |  |  |  | SW Side of Lava Flow Parking |  |
| 0 | 52 | Construct | Retaining Wall Rock Multi Tier |  |  | 52.0 | 3.0 |  | 3.0 |  | cu ft | Ramp | 468.0 |
| 0 | 645 | Construct | Concrete |  |  | 645.0 | 0.5 |  | 3.0 |  | cu ft |  | 967.5 |
| 52 | 645 | Construct | Split Rail Fence | Fence Railing 3 high |  | 593.0 |  |  |  |  | lin ft | Left side | 593.0 |
| 52 | 645 | Construct | Split Rail Fence | Fence Railing 3 high |  | 593.0 |  |  |  |  | lin ft | Right side | 593.0 |
| 52 | 645 | construct | Trail Construction | Hillslope <20% |  | 593.0 |  |  |  |  |  |  | 593.0 |
| 645 |  | excavate | rock | rock medium |  | 10.0 | 5.0 |  | 10.0 |  | cu ft |  | 500.0 |
| 645 |  | install | Bridge |  |  | 1.0 |  |  |  |  | ea | Truss | 1.0 |
| 693 |  | construct | concrete |  |  | 25.0 | 0.5 |  | 18.0 |  | cu ft | Overlook | 225.0 |
| 693 |  | Construct | Retaining Wall Rock Multi Tier |  |  | 18.0 | 2.0 |  | 2.0 |  | cu ft | overlook | 72.0 |
| 693 |  | install | Hand Railings |  |  | 75.0 |  |  |  |  | lin ft | overlook | 75.0 |
| 693 |  | install | Interpretive Panel |  |  | 1.0 |  |  |  |  | ea | overlook | 1.0 |
| 693 |  | excavate | rock | rock medium |  | 18.0 | 1.0 |  | 2.0 |  | cu ft | overlook - | 36.0 |
| 693 |  | monitor | segment ends |  |  |  |  |  |  |  |  | overlook |  |
| 645 |  |  |  |  |  |  |  |  |  |  |  | ALTER NATIVE – CAUSEWAY INSTEAD OF BRIDGE |  |
| 645 | 720 | perform | Trail Brushing Construction | Heavy |  | 75.0 |  |  |  |  | lin ft |  | 75.0 |
| 645 | 720 | excavate | rock | rock medium |  | 75.0 |  |  |  |  | cu ft |  | 75.0 |
| 645 | 665 | Construct | Retaining Wall Rock Multi Tier |  |  | 20.0 | 3.0 |  | 3.0 |  | cu ft |  | 180.0 |
| 665 | 680 | Construct | Retaining Wall Rock Multi Tier |  |  | 15.0 | 5.0 |  | 3.0 |  | cu ft |  | 225.0 |
| 680 | 720 | Construct | Retaining Wall Rock Multi Tier |  |  | 40.0 | 6.0 |  | 3.0 |  | cu ft |  | 720.0 |
| 645 | 720 | install | Hand Railings |  |  | 75.0 |  |  |  |  | lin ft |  | 75.0 |
| 645 | 720 | Construct | Concrete |  |  | 75.0 | 0.5 |  | 3.0 |  | cu ft |  | 112.5 |
| 720 |  | monitor | segment ends |  |  |  |  |  |  |  |  | Overlook (Use actions at WM 693 from above) |  |

Appendix C – Cost Estimate Details

Cost estimates are developed utilizing trail prescriptions conducted for planned actions (prescriptions are provided in Appendix B) and Microsoft Excel spreadsheets that calculate labor and material costs based on the dimensions of structures calculated during the trail prescription.  The cost estimation spreadsheets were developed by Karl Knapp of the California State Parks Trail Program.

Table of Contents

Campground Connector Trail					Page 123

Existing Trail Improvement

Park Boundary to Lenox Crater TH

Hill Climb Bypass Realignment

Overlook Spur 1

Overlook Spur 2

Visitor Center Realignment

Lava Loop Trail							Page 126

Lenox Crater Trail – Existing Trail Obliteration			Page 127

Lenox - Lava Flow Connector Trail				Page 128

Lenox Crater Loop Trail						Page 128

North (Ascending) Leg

South (Descending) Leg

Lava Overlook Trail							Page 130

Bridge Option

Causeway Option

Campground Connector Trail Cost Details

Campground Connector Trail – Existing Trail Improvement

Labor and Transportation Costs

- Brushing, clearing and down tree removal			$          36.90

- Trail Construction (by hand crew)					$   21,361.50

- Aggregate import (via toter)					$   90,897.03

- Causeway construction						$   42,733.00

- Rock step construction						$   70,020.00

- Trail sign installation						$        126.00

- Rock excavation							$     2,981.70

- Crew travel time – 500 hours					$     9,007.69

Total Labor and Transportation Costs					$ 180,153.83

Material Costs

- Aggregate base material – 264 cubic yards			$   11,076.33

- Rock (causeway, steps) – 183.1 cubic yards			$   16,479.00

- Trail signs – 7 total							$        700.00

- Taxes									$     2,048.51

Total Material Costs								$   30,303.85

Total Cost									$ 210,457.67

Campground Connector Trail – Park Boundary to Lenox Crater TH

Labor and Transportation Costs

- Brushing and clearing						$          25.20

- Trail Construction (by hand crew)					$   15,757.20

- Aggregate import (via toter)					$   40,555.38

- Causeway construction						$   54,297.00

- Rip rap construction							$   38,772.00

- Rock wall construction (multi-tier, junk wall)			$     4,680.00

- Rock gathering (rip rap, fill)					$     8,619.75

- Culvert installation							$          18.00

- Trail/interpretation sign installation				$          54.00

- Rock and soil excavation						$   19,764.00

- Crew travel time – 534 hours					$     9,612.24

Total Labor and Transportation Costs					$ 192,244.77

Material Costs

- Aggregate base material – 108 cubic yards			$     4,556.22

- Rock (causeway) – 230.1 cubic yards				$   20,709.00

- Culverts								$        251.80

- Trail/interpretation signs – 2 total					$     1,100.00

- Misc. Labor (Stump removal, disposal, ect)			$	 90.00

- Taxes									$     1,929.73

Total Material Costs								$   28,546.76

Total Cost									$ 220,791.53

Campground Connector Trail – Hill Climb Bypass Realignment

Labor and Transportation Costs

- Trail Construction (by hand crew)					$     3,442.50

- Aggregate import (via toter)					$     4,050.00

- Causeway construction						$     6,885.00

- Rock excavation							$        367.20

- Crew travel time – 43 hours					$        776.04

Total Labor and Transportation Costs					$   15,570.24

Material Costs

- Aggregate base material – 42.5 cubic yards			$     1,785.00

- Rock (causeway, steps) – 28.4 cubic yards			$     2,556.00

- Taxes									$     8,487.29

Total Material Costs								$     4,655.72

Total Cost									$   20,176.46

Campground Connector Trail – Overlook Spur 1

Labor and Transportation Costs

- Trail Construction (by hand crew)					$        324.00

- Aggregate import (via toter)					$     1,944.00

- Causeway construction						$        648.00

- Rock step construction						$     3,240.00

- Interpretive sign installation					$          36.00

- Rock excavation							$        405.00

- Crew travel time – 20 hours					$        347.21

Total Labor and Transportation Costs					$     6,944.21

Material Costs

- Aggregate base material – 4 cubic yards 			$        168.00

- Rock (causeway, steps) – 6 cubic yards				$        540.00

- Interpretive sign – 1 total						$     1,000.00

- Taxes									$        123.83

Total Material Costs								$     1,831.83

Total Cost									$     8,776.04

Campground Connector Trail – Overlook Spur 2

Labor and Transportation Costs

- Trail Construction (by hand crew)					$        211.50

- Aggregate import (via toter)					$     2,201.54

- Causeway construction						$     1,908.00

- Rock step construction						$        756.00

- Rock excavation							$          94.50

- Crew travel time – 15 hours					$        272.19

Total Labor and Transportation Costs					$     5,443.72

Material Costs

- Aggregate base material – 6 cubic yards 			$        247.33

- Rock (causeway, steps) – 8.7 cubic yards			$        783.00

- Cable and clamps (cable steps)					$          40.70

- Wood (cable steps)							$          33.00

- Taxes									$          80.04

Total Material Costs								$     1,184.08

Total Cost									$     6,627.80

Campground Connector Trail – Visitor Center Realignment

Labor and Transportation Costs

- Brushing, clearing and down tree removal			$          36.00

- Trail Construction (by hand crew)					$   15,759.90

- Aggregate import (via toter)					$   62,042.58

- Causeway construction						$   27,351.00

- Rock excavation							$        454.50

- Crew travel time – 309 hours					$   55,060.21

Total Labor and Transportation Costs					$ 111,204.19

Material Costs

- Aggregate base material – 169 cubic yards 			$     7,091.00

- Rock (causeway, steps) – 112.6 cubic yards			$   10,134.00

- Cable and clamps (cable steps)					$          40.70

- Wood (cable steps)							$          33.00

- Taxes									$     1,248.82

Total Material Costs								$   18,473.81

Total Cost									$ 129,678.00

Lava Loop Trail Cost Details

Labor and Transportation Costs

- Trail Construction							$        630.90

- Rock wall construction (multi-tier, junk wall)			$     2,673.00

- Rock step construction						$     6,012.00

- Rock gathering/quarrying						$     2,133.83

- Rock crushing for crush fill						$        331.20

- Cable step construction						$        504.00

- Trail/interpretive sign installation					$        144.00

- Soil and Rock excavation						$        195.30

- Crew travel time – 37 hours					$        664.43

Total Labor and Transportation Costs					$   13,288.67

Material Costs

- Rock (wall, steps) – 6 cubic yards					$        259.78

- Cable and clamps (cable steps)					$        103.60

- Wood (cable steps)							$     1,008.00

- Trail and interpretive signs – 5 total				$     3,200.00

- Taxes									$        331.42

Total Material Costs								$     4,902.80

Total Cost									$   18,191.47

Lenox Crater Trail — Existing Trail Obliteration

Labor and Transportation Costs

- Log check/cribbing construction					$        330.00

- Cinder fill import (via toter)						$   16,698.46

- Mini-excavator operation						$   59,272.92

- Existing sign removal						$          18.00

- Crew travel time – 139 hours				        $        2,486.25

Total Labor and Transportation Costs					$   78,805.63

Material and Equipment Costs

- Rebar for log checks						$            4.80

- Mini-excavator rental						$     8,219.17

- Taxes									$        596.24

Total Material and Equipment Costs					$     8,820.22

Total Cost									$   87625.85

Lenox – Lava Flow Connector Trail Cost Details

Labor and Transportation Costs

- Trail brushing and down tree removal				$        384.67

- Trail Construction							$   20,996.00

- Aggregate import (via toter)					$   27,367.84

- Causeway construction						$   86,556.00

- Rock step construction						$        384.00

- Trail/interpretive sign installation					$        112.00

- Rock excavation							$   11,360.00

- Crew travel time – 485 hours					$     7,745.29

Total Labor and Transportation Costs					$ 154,905.80

Material Costs

- Aggregate base material – 323 cubic yards 			$   13,569.89

- Rock (wall, steps) – 402.2 cubic yards				$   36,198.00

- Trail and interpretive signs – 4 total				$     3,100.00

- Taxes									$     3,832.92

Total Material Costs								$   56,700.81

Total Cost									$ 211,606.61

Lenox Crater Loop Trail Cost Details

Lenox Crater Loop Trail – North (Ascending) Leg

Labor and Transportation Costs

- Brushing and down tree removal					$        446.70

- Trail Construction							$   18,327.60

- Rock wall construction (multi-tier)					$     2,232.00

- Rock gathering/quarrying						$        558.83

- Trail delineation/puncheon/turnpike construction (wood)	$     1,026.20

- Down tree gathering						$        205.20

- Bench installation							$          72.00

- Trail/interpretive sign installation					$        126.00

- Soil and Rock excavation						$     1,451.22

- Misc. Labor (stump removal, disposal, ect)			$     5,616.00

- Crew travel time – 88 hours					$     1,582.14

Total Labor and Transportation Costs					$   31,642.86

Material Costs

- Rock (wall, steps) – 4.6 cubic yards				$        192.89

- Bench									$     1,000.00

- Trail and interpretive signs – 4 total				$     3,100.00

- Taxes									$        311.23

Total Material Costs								$     4,604.12

Total Cost									$   36,246.98

Lenox Crater Loop Trail – South (Descending) Leg

Labor and Transportation Costs

- Brushing and down tree removal					$        449.63

- Trail Construction							$   14,508.90

- Rock wall construction (multi-tier)					$     8,242.00

- Rock gathering/quarrying						$     2,106.00

- Trail delineation/puncheon/turnpike construction (wood)	$        954.72

- Down tree gathering						$        205.20

- Interpretive sign installation					$          36.00

- Soil and Rock excavation						$     3,872.56

- Misc. Labor (stump removal, disposal, ect)			$        540.00

- Crew travel time – 91 hours					$     1,625.88

Total Labor and Transportation Costs					$   32,517.69

Material Costs

- Rock (wall, steps) – 17.3 cubic yards				$        728.00

- Trail and interpretive signs – 1 total				$     1,000.00

- Taxes									$        125.28

Total Material Costs								$     1,853.28

Total Cost									$   34,370.97

Lenox Crater Loop Trail Cost Totals

Labor and Transportation Costs						$   64,160.55

Material Costs								$     6,457.41

Total Cost									$   70,617.95

Lava Flow Overlook Trail Cost Details

Lava Flow Overlook Trail – Bridge Option

Labor and Transportation Costs

- Trail Construction							$     1,067.40

- Rock wall construction (multi-tier)					$     9,720.00

- Split-rail fence installation						$     2,134.80

- Hand rail installation						$        450.00

- Interpretive sign installation					$          36.00

- Concrete pouring							$     9,512.25

- Bridge installation							$     4,320.00

- Rock excavation							$     2,412.00

- Crew travel time – 87 hours					$     1,560.66

Total Labor and Transportation Costs					$   31,213.11

Material Costs

- Rock (wall, steps) – 20 cubic yards				$     1,800.00

- Split-rail fencing material						$   23,435.36

- Hand rails								$     2,290.50

- Concrete								$   17,259.57

- 48 ft. Bridge								$   29,738.02

- Trail and interpretive signs – 1 total				$     1,000.00

- Taxes									$     5,475.45

Total Material Costs								$   80,998.89

Total Cost									$  112,212.00

Lava Flow Overlook Trail – Causeway Option

Labor and Transportation Costs

- Trail Construction							$     1,067.40

- Rock wall construction (multi-tier)					$   29,970.00

- Split-rail fence installation						$     2,134.80

- Hand rail installation						$     1,350.00

- Interpretive sign installation					$          36.00

- Concrete pouring							$   10,486.50

- Rock excavation							$     1,350.00

- Crew travel time – 136 hours					$     2,441.83

Total Labor and Transportation Costs					$   48,836.53

Material Costs

- Rock (wall) – 20 cubic yards					$     5,553.00

- Split-rail fencing material						$   23,435.36

- Hand rails								$     6,565.50

- Concrete								$   18,930.40

- Trail and interpretive signs – 1 total				$     1,000.00

- Taxes									$     4,022.61

Total Material Costs								$   59,506.87

Total Cost									$  108,343.40

Appendix D – TMO Form

Appendix D contains the Trail Management Objectives (TMO) form for Sunset Crater Volcano National Monument.

As described in the Trail Sustainability and Design Parameters section of this document, the purpose of the TMO form is as follows:

In order to ensure proper communication between the park and any other entities involved in the trail planning, construction or maintenance processes (such as contracted trail crews), Sunset Crater Volcano National Monument will maintain a TMO form for all proposed and existing trails in the park system.  The TMO form allows the park to maintain documentation of the class, use, design and maintenance standards and specifications determined for a trail.

The TMO form starts on the following page (page 133).

|  |  |  | Trail Management Objectives |  |  |  |  | Date: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Trail Name: |  |  |  |  |  |  |  |
|  |  |  | Sunset Crater Volcano National Monument |  |  |  |  |  |  |  |
|  |  |  | National Park Service - U.S. Department of the Interior |  |  |  |  |  |  |  |
|  | Trail Type (Loop, Out and Back, Connecting): |  |  |  |  |  |  |  |  |  |
|  | Trail Length: |  |  |  | Source (wheel, gps, map): |  |  |  |  |  |
|  | Trailhead Location: |  |  |  |  |  |  |  |  |  |
|  | Endpoint Location (if applicable): |  |  |  |  |  |  |  |  |  |
|  | Designed Use Standards (check all that apply) |  |  |  |  |  |  |  |  |  |
|  | Use Type |  |  | Trail Class |  |  |  |  |  |  |
|  |  | Hiker / Pedestrian |  |  | 1 Primitive/Underdeveloped |  |  |  |  |  |
|  |  | Bicycle |  |  | 2 Simple/Minor Development |  |  |  |  |  |
|  |  | Motorized |  |  | 3 Developed/Improved |  |  |  |  |  |
|  |  | Pack & Saddle |  |  | 4 Highly Developed |  |  |  |  |  |
|  |  |  |  |  | 5 Fully Developed |  |  |  |  |  |
|  | Prohibited Use |  |  |  |  |  |  |  |  |  |
|  |  | All Motorized Use |  |  | Bicycle |  |  |  |  |  |
|  |  | Hiker / Pedestrian |  |  | Pack & Saddle |  |  |  |  |  |
|  | Design Specifications |  |  |  |  |  |  |  |  |  |
|  | Tread Width (inches): |  |  | Target Cross-Slope%: |  |  | Design Grade%: |  |  |  |
|  | Maximum Grade%: |  |  | Clearing Width (feet): |  |  | Clearing Height (feet): |  |  |  |
|  | Maintenance Frequency (per year) |  |  |  |  |  |  |  |  |  |
|  | Trail Opening: |  |  | Tread Repair: |  |  | Drainage Cleanout: |  |  |  |
|  | Logging Out: |  |  | Brushing: |  |  | Condition Survey: |  |  |  |
|  | Special Considerations (check all that apply) |  |  |  |  |  |  |  |  |  |
|  |  | Mechanized Tools/Equipment Prohibited |  |  |  |  |  |  |  |  |
|  |  | Sensitive Species Present (Plant/Wildlife) |  |  |  |  |  |  |  |  |
|  |  | Cultural Resource Present |  |  |  |  |  |  |  |  |
|  |  | Easement across Non-NPS Land |  |  |  |  |  |  |  |  |
|  |  | ADA compliance |  |  |  |  |  |  |  |  |
|  | Administrative Approval |  |  |  |  |  |  |  |  |  |
|  | Trails Program Manager: |  |  |  | Signature: |  |  |  |  |  |
|  | Facility Manager: |  |  |  | Signature: |  |  |  |  |  |
|  | Additional Space for Notes on Continuation Sheet |  |  |  |  |  |  |  |  |  |

|  |  |  | Trail Management Objectives |  |  |  |  | Date: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Trail Name: |  |  |  |  |  |  |  |
|  |  |  | Sunset Crater Volcano National Monument |  |  |  |  |  |  |  |
|  |  |  | National Park Service - U.S. Department of the Interior |  |  |  |  |  |  |  |
|  | Additional Notes: |  |  |  |  |  |  |  |  |  |

Source:  Sunset Crater Volcano 2002 General Management Plan, Final Environmental Impact Statement.  National Park Service, Flagstaff Area National Monuments, Flagstaff, AZ