**.conm**

**Award Number (for administrative use only):**

**PR/J Number: R1360110051**

**PROJECT TITLE PAGE**

**Colorado Plateau Cooperative Ecosystem Studies Unit**

**(Cooperative Agreement # H1200-09-0005)**

**Park:** Cedar Breaks National Monument (CEBR)

**Project Title:** CEBR Wayside FY2011 Project - Intergovernmental Internship Cooperative (IIC)

**Funding Amount:** $62,758

**CPCESU Partner Institution:** Southern Utah University (SUU)

**Principal Investigator:** Seth Ohms, Agency Coordinator, Southern Utah University, 900 W. 209S, Cedar City, UT 84720, 435-586-1981, Fax: 435-865-8236 sethohms@suu.edu.

**NPS Key Official:** Paul Roelandt, Superintendent, Cedar Breaks National Monument, 2390 West Hwy 56 , Suite #11, Cedar City, Utah 84720, (435)586-9451 ext 21, Fax: 435-586-3813 paul\_roelandt@nps.gov.

**Start Date:** December 10, 2010

**End Date:** June 1, 2015

**Career Internship Corps (CIC) -- Youth Internship Project (YIP)**

**Task Agreement / Scope of Work**

**October 7, 2010**

**Article I – Background and Objectives**

Background:

The project management information system (PMIS) project #107580A is to initially plan and design, then to fabricate and install new wayside exhibits at CEBR. This Task Agreement is for the planning, design and pre-production work that will be done by SUU students. These students will be supervised, mentored and trained by SUU Faculty and mentored and trained by NPS Employees. Planning and design efforts for this project may include plans for the possible addition of waysides located just outside the park at the USFS Zion Overlook on Utah Highway 14 and on USFS lands on Brian Head Peak, overlooking the park, to interpret particular aspects of the park’s unique, subalpine ecosystem and its 10,000 years of human history. Fabrication of exhibits will be accomplished with the assistance of the HFC Wayside Technical Assistance Program.

This project will utilize experienced IIC CIC college faculty & interns as student liaisons and design team members to organize and design wayside.

Regional NPS experts will be brought in to train SUU Facility and Students.

Completed in 2010, PMIS project #8948 utilized SUU Students and Faculty along with NPS Employees to plan, design, fabricate and installation of the first-ever wayside exhibits at CEBR. Regional NPS experts were brought in to train SUU Facility and students. SUU IIC produced 15 waysides and CEBR has to date installed 3 of these panels at the monument.

Objectives:

This Wayside Proposal was developed to meet the wayside needs of Cedar Breaks National Monument by partnering with SUU to give students experience in the development of NPS Wayside Exhibits.

The proposal is intended to provide a consistent overview of the waysides as a whole and to avoid unneeded repetition of information, orientation, or interpretation with previously developed waysides. It is in-line with the park’s goal for interpretation as described in the park’s Strategic Plan: increasing people’s understanding and appreciation of the significant resources comprising Cedar Breaks National Monument.