**PR Number:** **R7127120033**

**Award Number:** **P12AC10172**

**Project Number: UNM-75**

**Park/NPS Unit:** Bandelier National Monument

**Title of Project:** Assess impacts of Las Conchas fire and suppression activities on park vegetation

**Administered through the:** Colorado Plateau Cooperative Ecosystem Studies Unit Cooperative Agreement Number H1200-09-0005

**CESU Partner:** University of New Mexico

**Project Contacts**

**Principal Investigator:** Esteban Muldavin, Ecology Coordinator, Natural Heritage Program, Biology Dept., University of New Mexico, MSC03 2020, Albuquerque, NM 87131-0001 Ph:505.277.3822 Fx:505.277.3844 muldavin@unm.edu

**Partner Administrative Contact:** Brenda Baker, Contract & Grant Administrator, Office of Pre-Award Svcs., 1700 Lomas NE, University of New Mexico, MSC01 1247, Albuquerque, NM 87131 Ph:(505) 277-2341 Fx:(505) 277-4185, brbaker@unm.edu

**NPS Certified ATR:** Brian Jacobs, Botanist, Bandelier National Monument, Los Alamos, NM 87544 Ph:505.672.3861 x707 Fx:505.672.9607 brian\_jacobs@nps.gov

**NPS Technical Expert (if appropriate):** Brian Jacobs, Botanist, Bandelier National Monument, Los Alamos, NM 87544 Ph:505.672.3861 x707 Fx:505.672.9607 brian\_jacobs@nps.gov

**Funding Information:**

**Amount Funded:** $35,000

**NPS Account Numbers:** 1249-F5PS-B11 (35,000)

**Fund Source:** (BAER)

[x] NPS Funding

[ ]  Is this funded using a reimbursable account number? If yes, IMR contracting needs a copy of the Interagency Agreement.

**Project Dates:**

Project initiation – 03/01/2012
Draft Final 2012 Datasets: 12/31/2012

Draft Final 2013 Datasets: 12/31/2013

Final 2012-13 Datasets and Report: 10/31/2014

Project End Date – 12/31/2014

**SCOPE OF WORK**

Title: Assess impacts of Las Conchas fire and suppression activities on park vegetation

Objectives: Assess impacts of fire and suppression activities on native flora, plant communities and associated habitat including post-fire recovery of vegetative cover, rehabilitation of suppression impacts, monitoring of known sensitive plant populations, and detection of exotic plant expansion/ establishment that would warrant direct control efforts. Prescribe additional treatments as necessary based on monitoring results.