{"text_format":"1","workbook":"xlsx","n_sheets":5,"sheets":["Legend","FY20Q1","Resource Updates","Drop Down Menu","Code"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":1,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Legend","index":0,"n_rows":5,"n_cols":2,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
[]
[null,"Description"]
[null,"Work is complete"]
["Red line","hard stop for the project to meet the go live deadline"]
[null,"Timeline is TBD"]

{"sheet":"FY20Q1","index":1,"n_rows":113,"n_cols":39,"rows_kept":113,"cut":false,"hidden":false,"merged":[[111,9,111,10],[79,13,79,15],[79,16,79,17],[79,18,79,20],[86,14,86,16],[83,13,83,18],[84,13,84,16],[108,13,108,14],[20,18,20,19],[76,15,76,16],[28,13,28,14],[28,15,28,17],[74,13,74,14],[26,14,26,16],[27,15,27,17],[34,16,34,18],[43,13,43,15],[43,17,43,18],[52,13,52,15],[54,13,54,15],[54,16,54,17],[50,15,50,18],[40,17,40,20],[49,22,49,25],[10,20,10,21],[23,22,23,23],[23,24,23,25],[23,13,23,17],[12,14,12,19],[12,20,12,21],[14,14,14,19],[14,20,14,21],[27,13,27,14],[20,20,20,21],[10,14,10,19],[38,21,38,25],[40,13,40,16],[43,19,43,21],[20,13,20,17],[4,13,4,14],[4,15,4,19],[4,20,4,22],[0,22,0,25],[0,13,0,17],[2,13,2,17],[2,18,2,21],[16,18,16,25],[0,35,0,38],[0,31,0,34],[0,18,0,21],[0,26,0,30],[11,13,11,18],[11,19,11,20],[11,21,11,22],[15,22,15,24],[7,13,7,15],[7,16,7,17],[8,13,8,38],[15,13,15,21],[112,13,112,18],[16,27,16,28],[18,13,18,14],[58,13,58,17],[40,21,40,24],[45,13,45,15],[45,16,45,17],[45,18,45,20],[45,21,45,23],[45,24,45,25],[34,19,34,22],[34,23,34,25],[18,15,18,24],[23,18,23,21],[17,13,17,24],[16,13,16,17]]}
["VP","Project Title","Priority","Owner","ITS Leadership Sponsor (ITS Projects Only)","ITS Project Type","Target Completion","Enterprise Product","Health Check","Health Check Date","Delay Reason","Work needed in next quarter","Notes","2019-07-01",null,null,null,null,"2019-08-01",null,null,null,"2019-09-01",null,null,null,"2019-10-01",null,null,null,null,"2019-11-01",null,null,null,"2019-12-01"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"7/1-7/5","7/8-7/12","7/15-7/19","7/22-7/26","7/29-8/2","8/5-8/9","8/12-8/16","8/19-8/23","8/26-8/30","9/2-9/6","9/9-9/13","9/16-9/20","9/23-9/27","9/30-10/4","10/7-10/11","10/14-10/18","10/21-10/25","10/28-11/1","11/4-11/8","11/11-11/15","11/18-11/22","11/25-11/29","12/2-12/6","12/9-12/13","12/16-12/20","12/23-12/27"]
["Academic Affairs","Academic Restructure 2019","0 Critical-MUST Do","Theresa Ann Rogers",null,null,"2019-08-30","OnBase, PeopleSoft: Campus Solutions, Salesforce, Informatica, Business Objects",null,null,null,null,null,"Planning",null,null,null,null,"Development/Multiple Go Live"]
["Academic Affairs","Feed EAN comments into SF Activities","3 Low","Eddie F Waters Jr",null,null,"9/30/2019","Salesforce","On Hold"]
["Academic Affairs","PL Updates","3 Low","Eddie F Waters Jr",null,null,"9/30/2019","Custom Web App",null,null,null,null,"Development is 100% in ITS and this is merely a guesstimate","Requirements gathering",null,"Development",null,null,null,null,"Testing",null,null,"Project Close"]
["Academic Affairs","View only access requested for data integration mappings","3 Low","Eddie F Waters Jr",null,null,"9/30/2019","Business Objects, Database Administration",null,null,null,null,"Dependent on Kick off meeting"]
["Academic Affairs","SalesForce auto case creation","3 Low","Eddie F Waters Jr",null,null,"9/30/2019","Salesforce","On Hold"]
["Academic Affairs","Traditional, Accelerated and CEP Nursing Program online applications","3 Low","Eddie F Waters Jr",null,null,"9/30/2019","Custom Web App",null,null,null,null,null,"Development",null,null,"Testing",null,"Close"]
["Academic Affairs","Update SF PEP Informatica script for Yuma Title II","2 Normal","Steven Roy Hernandez",null,null,"9/30/2019","Salesforce, Informatica",null,null,null,null,null,"Development/Testing (as the Salesforce team has time)"]
["Capital Planning and Campus Operations","EnergyCap 15 Minute Interval and Billing Process Change q4","3 Low","Mark Alan Niles",null,null,"6/30/2019","OTHER MISCELLANEOUS","Bumpy","2019-07-03",null,null,"Waiting on approval of PO. No PS resources are needed. Erin will follow up with John on where this project is. Platform team would be needed. John is out on FMLA for three months. "]
["Enrollment Management","Online Appointment Scheduler for Student Service Center","3 Low","April Cook",null,null,"2019-06-30","Custom Web App",null,null,"IT resource constraint","Approval Needed",null,"UAT/Go Live","Development/BA Test (15/45)",null,null,null,null,null,"UAT/Go Live"]
["Enrollment Management","Veterans DODTA electronic form","3 Low","Tim Pettry",null,null,"9/30/2019","OnBase",null,null,null,null,null,"Development",null,null,null,null,null,"BA Testing",null,"UAT",null,"Go Live"]
["Executive Services: Other","Clockwork System for Disability Services","2 Normal","Kyle Hamilton Cawood",null,null,"7/31/2019","PeopleSoft: Campus Solutions"]
["Executive Services: University Marketing","Campus-wide New NAU Logo Roll-Out Project (Technology Updates)","3 Low","ShayAlice Asterope Aradia",null,null,"8/1/2019","Custom Web App, PeopleSoft: Campus Solutions"]
["Finance Institutional Planning and Analysis","Implement new budget software","1 High","Siri Mullaney",null,null,"12/31/2019","PeopleSoft: FMS, OTHER MISCELLANEOUS"]
["Finance Institutional Planning and Analysis","IRA DATA REQUEST ROUTING  TASK MANAGEMENT SYSTEM REQUIREMENTS q4","4 TBD/NE","Yael A Bernstein",null,null,"7/31/2019","","On Hold","2019-07-08",null,null,"Project was not able to be resourced this quarter. Moved to quarter 2.","Development/Testing",null,null,null,null,null,null,null,null,"UAT",null,null,"Go Live"]
["Human Resources","BCBS HSA Plan","2 Normal","Pam Fleece",null,null,"12/31/2019","PeopleSoft: HR","On Track","2019-07-03","Always Intended to be Multi Quarter","Approved","Kick off meeting with company last Thursday. Final spec for development. Renee needs to do set up first. Development in August","Requirements/Development",null,null,null,null,"Testing",null,null,null,null,null,null,null,"Go Live/Part 1","Testing Part 2",null,"Go Live/Part 2"]
["Human Resources","Convert HR Policies to New Format","1 High","Pam Fleece",null,null,"2019-09-30","WordPress","On Hold","2019-07-03",null,null,"Not working on this yet.","Requirements (Updating sections)",null,null,null,null,null,null,null,null,null,null,null,"Go Live (shut off archived database)"]
["Human Resources","OnBase LOA Phase Two","3 Low","Pam Fleece",null,null,"9/30/2019","OnBase","On Track","2019-07-03",null,null,"Renee is finishing finalizing the Spec. OnBase has initial draft to start work.","Development",null,"Development/Testing",null,null,null,null,null,null,null,null,null,"Go Live"]
["Human Resources","Organizational Growth and Effectiveness Initiative Implementation Planning","1 High","Pam Fleece",null,null,"12/31/2019","",null,null,"Always Intended to be Multi Quarter","Approved","Service delivery phase (Brad Miner is the project manager). Comp and Class (Cindy and Rebecca are the project managers). Kick off meetings next week. ITS work will need to happen, might have to do go out for RFP. "]
["Information Technology Services","25Live Space Management System of Record Transition","1 High","April Anne Cook","Andrea Stalker","Cross-Divisional","8/10/2020","25Live, Custom Web App, Salesforce, Custom Development, OTHER MISCELLANEOUS","On Track","2019-07-02",null,null,"Kick off meeting completed. Project work to define requirements the month of July.","Development/Requirements/Definitions",null,null,null,null,"Pilot"]
["Information Technology Services","Implement New Professional Development LMS system","1 High","Jared I Logan","Andrea Stalker","Cross-Divisional","12/31/2019","","Under Control","2019-05-22",null,null,"Go live scheduled for July 2019","Testing","Go Live"]
["Information Technology Services","Moving websites, applications and databases to Bldg 54","1 High","David B Brink","Marc Lord","Cross-Departmental","2019-07-31","Custom Web App, Linux/Unix Server, MS Windows Server","Under Control","2019-06-20","IT resource constraint","Approval Needed","No PM needed; Now having a daily stand-up (as of 5/9/2019); Some resourcing issues; ","Go Live"]
["Information Technology Services","PS Campus Solutions 92 Upgrade","1 High","Andrea Stalker","Marc Lord","Cross-Divisional","10/25/2019","PeopleSoft: Campus Solutions","On Track","2019-06-20",null,null,"Only issue is Online application/Hutch situation; knowledge transfer for next 2 weeks;","Redevelopment/Preliminary BA and SME Testing",null,null,null,null,"Full Regression Testing",null,null,null,"Prep Steps for Test",null,"Test Run",null,"Prep","Go Live"]
["Information Technology Services","Classroom Attendance Scanners","2 Normal","Kegan Remington","Don Carter","Cross-Departmental","8/1/2019","Custom App"]
["Information Technology Services","Data mining log files for student engagement analysis","2 Normal","Andrea Stalker","Andrea Stalker","Cross-Divisional","8/30/2019","CAS, OTHER MISCELLANEOUS","On Track","2019-07-02",null,null,"Data has been identified. Tim's team is working on gathering requirements. Timeline to be established in the next couple of weeks."]
["Information Technology Services","Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","2 Normal","Jason D Robinson","Marc Lord","Cross-Departmental","2019-08-15","ModoLabs/Mobile Application","On Track","2019-06-20",null,null,"Beacons in middle of next week (5/15-ish)","Add to test app","Testing/Sign Off",null,null,"Launch"]
["Information Technology Services","Professional Development LMS - Dental Hygeine Courses","3 Low","Jared I Logan","Don Carter","Cross-Divisional","2019-07-30","","Under Control","2019-06-10",null,null,"06/10/2019 Issues with the vendor being non-responsive on a needed plug in.  Risk identified and sent to Andrea for sign off.  Bumpy due to development delays, possible soft launch in July","Continued development and Testing",null,"Soft Launch"]
["Information Technology Services","Roll out new wifi access system CISCO ISE","1 High","Brett West","Brett West","Cross-Departmental","8/15/2019","Network Infrastructure, OTHER MISCELLANEOUS","On Track","2019-06-24",null,null,"6/24/2019; Might only need a communications send to NAU community;  Maybe communications position in place; 05/29/19, this project is on track.  Training with CISCO completed, testing beginning. ","Testing",null,"Soft Launch"]
["Information Technology Services","MPLS Building Cutover Phase 2","1 High","Armand Ramirez","Brett West","Single Team/Dept","9/30/2019","Network Infrastructure","DO NOT TRACK HEALTH STATUS"]
["Information Technology Services","eSports Space and Setup","2 Normal","Don Carter","Don Carter","Cross-Divisional","2019-10-31",null,"Bumpy","2019-05-22",null,null,"05/22/19 Space is found, waiting for approval.No Space avail. Don advised they are still looking, but not ready to move forward, no resources available to work on this for Q4","Researching space"]
["Information Technology Services","Implementation of Digital Signage","3 Low","Kegan Remington","Don Carter","Cross-Divisional","2019-08-01",null,"Imminent Failure","2019-05-22",null,null,"Needs Resources Allocated and Kickoff, Custom Dev resources needed"]
["Information Technology Services","Design System Pilot","4 TBD/NE","Jason D Robinson","Marc Lord","Cross-Divisional","9/30/2019",""]
["Information Technology Services","Develop technology support for updating phone numbers, contact info in Louie once a term","2 Normal","Marc H Lord","Marc Lord","Cross-Divisional","6/29/2018","No Product"]
["Information Technology Services","IAM Platform RFP","4 TBD/NE","Trey McCallie","Michael Zimmer","Cross-Departmental","9/30/2019","Unknown Systems-Solution Needed",null,null,null,null,"Dependent on funding. (per email from Michael on 5/10)","Discovery","Planning","Requirements Gathering","Authoring",null,null,"Purchasing Process; Reviews",null,null,null,"Launch RFP Formally"]
["Information Technology Services","ITS Drive Mapping","2 Normal","Tobias J Kreidl","Brett West","Cross-Departmental","3/31/2020",""]
["Information Technology Services","ITS Disaster Recovery","1 High","Tobias J Kreidl","Brett West","Cross-Divisional","7/1/2020",""]
["Information Technology Services","Key Audit OnBase Form","3 Low","Krystina Marie Kraus-Soper","Albert Sandoval","Cross-Departmental","9/30/2019","OnBase"]
["Information Technology Services","Migrate all VPN access to Two-Step Verification","2 Normal","Trey McCallie","Michael Zimmer","Cross Dept/Cross-Div Impact","9/27/2019","",null,null,null,null,null,null,"Discovery, Planning, Req Gathering Curent Ex.","Design, Communications","Build","Testing/UAT; Sign Off","Go Live",null,"Closing","Operational Support"]
["Information Technology Services","OnBase Form and Flow for Exception Request Risk Acceptance","2 Normal","Michael William Zimmer","Michael Zimmer","Cross-Departmental","2019-12-30","OnBase",null,null,"IT resource constraint",null,"Project delayed before Q1 start to Q2 to support IT constraint with OnBase team"]
["Information Technology Services","Server configuration baseline images and monitoring","1 High","Daniel Wallace","Michael Zimmer","Cross-Departmental","10/6/2019","",null,null,null,null,null,"Develop configuration profiles",null,null,null,"Integrate profiles into baseline images, develop process for bringing existing servers into compliance",null,null,null,"Develop process for monitoring and reporting on baseline compliance",null,null,null,"Deploy and Monitoring"]
["Information Technology Services","SSO for NAUgo","1 High","Dina Ann Barnese","Marc Lord","Cross-Departmental","9/30/2019","CAS, ModoLabs/Mobile Application"]
["Information Technology Services","Thin Client Replacement","2 Normal","Tobias J Kreidl","Brett West","Cross-Divisional","12/31/2019",""]
["Information Technology Services","Transition to using private IP networks to improve security posture- Phase I","2 Normal","Daniel Wallace","Michael Zimmer","Cross-Departmental","10/6/2019","",null,null,null,null,null,"Develop configuration profiles",null,null,"Develop transition plan","Go Live",null,"Define needs for future phases"]
["Information Technology Services","WiFi Core Upgrade Phase 2 Increase Capacity for ResNet","1 High","David N Russell","Brett West",null,"9/30/2019","Network Infrastructure"]
["Information Technology Services","Windows 7 End of Life, EOL, January 2020","1 High","Michael William Zimmer","Michael Zimmer","Cross Dept/Cross-Div Impact","1/10/2020","",null,null,null,null,null,"Discovery/Planning",null,null,"Inventory",null,"Owner, Dept Identification; Communication Planning;Exception Req Planning",null,null,"Evaluate Legacy SW, HW\nCreate Exception Req Process\nPlan/Identify Who First",null,null,"Begin Upgrades\nLessons Learned\nPlan Remainder…"]
["Information Technology Services","Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","3 Low","Kristopher R Bullins","Brett West","Single Team/Dept","9/30/2019","MS Windows Server, Microsoft Local Services","DO NOT TRACK HEALTH STATUS"]
["Research","Build CUI Service Offering","2 Normal","Jeremy Sanderlin",null,null,"6/30/2019","Linux/Unix Server",null,null,null,"Approval Needed"]
["Academic Affairs","Execute Group Wrangler  Global Program Manager new app - IGP","1 High","Steven Roy Hernandez",null,null,"2020-03-01","Custom Web App, Business Objects, PeopleSoft: Campus Solutions",null,null,"Always Intended to be Multi Quarter"]
["Human Resources","ADP CYQ3 Update","0 Critical-MUST Do","Pam Fleece",null,null,"2019-09-30","PeopleSoft: HR","On Hold",null,null,null,"Coming Late August.",null,null,null,null,null,null,null,null,null,"Testing/Go Live"]
["Human Resources","Rimini Tax Release RS19P03","0 Critical-MUST Do","Pam Fleece",null,null,"2019-08-05","PeopleSoft: HR","On Hold",null,null,null,"Coming July 15. Install on Sunday August 4",null,null,"Testing/Go Live"]
["Advancement and Alumni Services","iModules for Alumni","2 Normal","ShayAlice Asterope Aradia",null,null,"2019-10-31","Custom Web App"]
["Capital Planning and Campus Operations","Build Construction Estimates Form","1 High","Mark Alan Niles",null,null,"2019-09-30","OnBase","On Track","2019-07-03",null,null,"Development is ready for testing. Mark will start reviewing","Development",null,null,"Testing","Go Live"]
["Capital Planning and Campus Operations","Improvements to existing Daily Log","4 TBD/NE","Mark Alan Niles",null,null,"2019-09-30","OnBase","Completed","2019-07-03",null,null,"Approved today, needs migrate."]
["Capital Planning and Campus Operations","Inspection Request Form","2 Normal","Mark Alan Niles",null,null,"2019-09-30","OnBase","On Track","2019-07-03",null,null,"Development is starting today. July 12th development should be complete.","Development",null,null,"Testing",null,"Go Live"]
["Enrollment Management","Continuing Student Persistence (Business Object reports)","2 Normal","Tim Pettry",null,null,"8/30/2019","Business Objects, Integration Analyst"]
["Enrollment Management","FA document upload Phase 2","3 Low","Tim Pettry",null,null,"8/31/2019","OnBase"]
["Executive Services: Other","Waiver of Recruitment Request Form Digitization","3 Low","Jeremy Sanderlin",null,null,"2019-12-31",null,"On Hold","2019-07-09","IT resource constraint","Approval Needed","Project could not be resourced this quarter."]
["Human Resources","New Employee Welcome Online Version","2 Normal","Pam Fleece",null,null,"2019-09-30",null,"On Track","2019-07-03","Original scope larger than anticipated","Approval Needed","Discovery of the new employee orientation. Jeremy is invited to the kick off meeting.","Discovery"]
["Information Technology Services","Development of Badging System for CE and PD","2 Normal","Andrea Stalker","Andrea Stalker","Cross-Divisional","2019-09-30"]
["Information Technology Services","Establishing a Science DMZ","1 High","Christopher Coffeey","Don Carter","Cross Dept/Cross-Div Impact","2019-08-16"]
["Information Technology Services","ITS - ServiceNow processes, procedures and administration","3 Low","Robert Brubaker","Marc Lord","Cross-Departmental","2019-09-30","ServiceNow"]
["Information Technology Services","ITSM Training Videos","3 Low","John Lowe","Celisa Manly","Cross-Departmental","2019-12-31","LPD"]
["Information Technology Services","Lynda com upgrade to LinkedIn Learning","1 High","Jeremy Sanderlin","Don Carter","Cross-Divisional","2019-07-01","CAS, Lynda"]
["Information Technology Services","Migrate Employee Email (IRIS) to Office 365 Exchange Online","1 High","Brett West","Brett West","Cross Dept/Cross-Div Impact","2019-12-31"]
["Information Technology Services","Migrate SharePoint to SharePoint Online","3 Low","Brett West","Brett West","Cross Dept/Cross-Div Impact","2020-01-01"]
["Information Technology Services","On-boarding ITS Communications","4 TBD/NE","Sarah Lipsey","Andrea Stalker","Cross-Departmental","2019-08-30","LPD"]
["Information Technology Services","PaperCut print management version upgrade NG to MF","3 Low","David Starmer","Brett West","Single Team/Dept","2019-07-31",null,"DO NOT TRACK HEALTH STATUS"]
["Information Technology Services","Salesforce Training Development and Scheduling","3 Low","Andrea Stalker","Andrea Stalker","Cross-Divisional","2019-12-30","Salesforce, Project Management"]
["Information Technology Services","Video Conferencing technology and training improvements for classrooms","2 Normal","Kegan Remington","Don Carter","Cross-Departmental","2019-08-16","LPD"]
["Information Technology Services","Directory revamp","1 High","Jeremy Sanderlin","Marc Lord","Cross-Divisional","2019-12-30","Custom Web App, LDAP","Bumpy","2019-06-20",null,null,"6/20-Scope change - not under control;\n\nPer Chris; Vince leaving has resource gaps on the project; timelines may be bumped; front end folks waiting on backend work to be completed; Project discussion pending;"]
["Information Technology Services","Enterprise TLS Update Phase 3","1 High","Daniel Wallace","Michael Zimmer","Cross-Departmental","2019-09-30","PeopleSoft ERP","Under Control","2019-06-03"]
["Information Technology Services","Evaluate new Anti-Virus Software for Mac OS","1 High","Suzanne Hanks","Suzanne Hanks","Cross-Departmental","2019-10-31","","On Track","2019-06-12",null,null,"The Deliverables have been developed and the project is ready for kickoff.  Target completion date updated to 10/31/2019","Begin Procurement"]
["Information Technology Services","OnBase Mobile  Access","2 Normal","Wesley Walker","Marc Lord","Cross-Divisional","2019-07-31","OnBase","Under Control","2019-06-20",null,null,"Need additional infrastructure support with VMs, etc.; timeline updated 6/11","UAT Test","Sign Off","Go Live"]
["Information Technology Services","OnBase Security Request for ArcGIS Online","2 Normal","Lynn Burch","Marc Lord","Cross-Departmental","2019-08-09","OnBase, ArcGIS","Under Control","2019-06-20",null,null,"Timeline updated 6/11; Change resource to Talbert","UAT Dev",null,"UAT Test","Sign Off"]
["Information Technology Services","Upgrade BizTalk servers and the Biztalk application","2 Normal","Mark Timothy Staten","Marc Lord","Cross-Departmental","2019-09-30","OnBase, BizTalk, MS Windows Server","Trouble Ahead","2019-06-20",null,null,"Waiting on contracts/purchasing…still as of 6/20; Will need VM - Brett's team, how to do it will be a question; Need core services"]
["Information Technology Services","ArcGIS Enterprise Project","4 TBD/NE","Matthew Natividad Tafoya","Marc Lord","Cross-Departmental","2019-08-15","ArcGIS","Bumpy","2019-06-20",null,null,"Chad scheduling meeting wth Infrastructure; 5/28: Making progress, but still needs some key decision points and resourcing resolved. Azure is the decision; Chad continuing to work with Brett 6/20"]
["Enrollment Management","Campus Dining integration with NAUGo","2 Normal","Tim Pettry",null,null,"2019-06-30","Custom Web App, ModoLabs/Mobile Application"]
["Executive Services: University Marketing","Build Pre-Lead to Lead Generation Solution","1 High","Jeremy Sanderlin",null,null,"2019-10-30","Salesforce, WordPress"]
["Research","Build CUI Service Offering","2 Normal","April Cook",null,null,"2019-12-31","Linux/Unix Server",null,null,null,null,null,"Requirements/Development",null,null,"Development",null,"Testing",null,null,"Go Live"]
["Research","Loading of historical Cayuse and PS Financials data to the data warehouse for reporting HERD, Cabinet Reports","2 Normal","Laura Jones",null,null,"2019-09-30","Cayouse",null,null,"Other","Approved","Per Laura 6/25:  Still pending because there seems to be a difference of opinion regarding how to move forward.  At the last RMW meeting, it was clear the OSP team sees no value in retaining snapshots of their data, and they appear to currently be using PS Queries to pull live data for various reporting needs.  From my perspective, and based upon what I was asked to accomplish with the RMW group, this is not acceptable. I had a follow-up discussion about this with Dave Schultz and we decided to schedule a meeting with Bjorn, Dave Schultz, me, and Nick Bilyk to come to an agreement on next steps.  Due to vacation schedules, that meeting will not take place until mid-July."]
["Academic Affairs","Execute PEP Title II Project","1 High","Steven Roy Hernandez",null,null,"6/30/2019","PeopleSoft: Campus Solutions, Salesforce, Informatica",null,null,null,null,null,"Testing","Go Live"]
["Academic Affairs","Execute Suitable","3 Low","Steven Roy Hernandez",null,null,"6/30/2019","",null,null,null,null,null,"Go Live"]
["Academic Affairs","Execute Sunapsis Upgrade","0 Critical-MUST Do","Marilee Ann Laurencell",null,null,"9/30/2019","OTHER MISCELLANEOUS",null,null,null,null,null,"Testing",null,null,null,null,null,"Go Live"]
["Academic Affairs","PL Dashboard Updates","2 Normal","Brynn Nicole Dryer",null,null,"7/31/2019","",null,null,null,null,null,"Testing",null,null,null,"Go Live"]
["Capital Planning and Campus Operations","Implement Project Management service PMWeb for CapCOT","1 High","Mark Alan Niles",null,null,"2019-12-30","PeopleSoft: Campus Solutions, TMA, OTHER MISCELLANEOUS","Bumpy","2019-07-03",null,null,"Requirements. Every two weeks Mark will be doing data mappings. Going at the pace of Stephanie Bauer. Erin will follow up with Stephanie that the pace that is set will impact development. \n\nRequirements: Stephanie/Mark (need by 7/26)\nSolution Review: Mark (1-2 months)\nDevelopment: October"]
["Enrollment Management","2NAU Application-Prospect Project Phase 2","1 High","April Cook",null,null,"2019-09-30","PeopleSoft ERP, Salesforce, Informatica, LDAP",null,null,null,null,null,"Development","Testing/Sign Off",null,null,"Go Live"]
["Enrollment Management","Document Submission Form,Supply Order Request Form","1 High","Tim Pettry",null,null,"2019-07-31","OnBase"]
["Enrollment Management","Transcript Processing Improvements within OnBase","2 Normal","Cory D Holland",null,null,"2019-09-30","OnBase, PeopleSoft ERP"]
["Enrollment Management","Transfer Credit Articulation Rule Evaluation Tracking","2 Normal","Cory D Holland",null,null,"2019-09-30","OnBase"]
["Executive Services: University Marketing","Develop web services to pull course offerings from PeopleSoft q4","4 TBD/NE","Rayma Lee",null,null,"2019-08-31","PeopleSoft:Campus Solutions"]
["Information Technology Services","Address Scrubbing Software Review-QAS Experian Software Expiration","2 Normal","Andrea Stalker","Andrea Stalker","Cross-Divisional","2019-09-30","OTHER MISCELLANEOUS"]
["Information Technology Services","Complete Isilon Storage Service Offering","2 Normal","Michele Francis","Brett West","Cross-Divisional","2019-12-31",null,null,null,"Always Intended to be Multi Quarter","Approved"]
["Information Technology Services","Compliant storage environment for non-research HIPAA data","2 Normal","Brett West","Brett West","Cross-Departmental","2019-04-30"]
["Information Technology Services","Discovery for NAU Data Strategy","2 Normal","Marc H Lord","Marc Lord","Single Team/Dept","2020-01-07",null,"DO NOT TRACK HEALTH STATUS",null,"Always Intended to be Multi Quarter","Approved"]
["Information Technology Services","Hyper-converged server consolidation","1 High","Clint Gleason","Brett West","Cross Dept/Cross-Div Impact","2019-12-31","Linux/Unix Server, MS Windows Server, Microsoft Local Services, Network Infrastructure"]
["Information Technology Services","Implement Solution for NAU Strategic Goals Management System","1 High","Marc H Lord","Marc Lord","Cross-Departmental","2019-12-30",null,null,null,"Always Intended to be Multi Quarter","Approved"]
["Information Technology Services","Lifter LMS Module Conversion for LPD","4 TBD/NE","Sarah Lipsey","Andrea Stalker","Cross-Departmental","2019-09-30"]
["Information Technology Services","Migrate all websites off of www5, www7, sourwood, possumhaw","2 Normal","Bryan G Loveless","Brett West","Cross-Divisional","2020-03-30",null,"Bumpy","2109-06-24","Always Intended to be Multi Quarter","Approved","WWW5 - Single Team; WWW7 - Cross Divisional (as separate project); Need to assign avail resources"]
["Information Technology Services","MS Teams Adoption Roll-Out","3 Low","Andrea Stalker","Andrea Stalker","Cross-Divisional","2019-09-30"]
["Information Technology Services","NAUPD Verizon Small Cell","0 Critical-MUST Do","Paul Merciano Trujillo","Brett West","Cross-Divisional","2019-12-31",null,null,null,"Always Intended to be Multi Quarter","Approved","WWW5 - Single Team; WWW7 - Cross Divisional (as separate project); Need to assign avail resources"]
["Information Technology Services","OnBase for NAU Address Change approval process","2 Normal","Lynn Burch","Marc Lord","Cross-Departmental","2019-07-31"]
["Information Technology Services","On-boarding ITS communications","4 TBD/NE","Sarah Lipsey","Andrea Stalker","Cross-Departmental","2019-08-30"]
["Information Technology Services","PBX Conversion Completion","0 Critical-MUST Do","Brett West","Brett West","Cross-Divisional","2019-06-30","Network Infrastructure"]
["Information Technology Services","Project Management Module ServiceNow Configurations Development","2 Normal","Andrea Stalker","Andrea Stalker","Cross-Divisional","2019-10-25","Service Now"]
["Information Technology Services","Rebrand Trainings to match University Marketing standards","4 TBD/NE","Ashlee Annabelle Binderim","Andrea Stalker","Cross-Divisional","2019-12-31"]
["Information Technology Services","Splunk forwarder installations on all Academic and Enterprise systems","1 High","Daniel Wallace","Michael Zimmer","Cross-Departmental","2019-07-15","Linux/Unix Server, MS Windows Server, Microsoft Local Services, Splunk"]
["Information Technology Services","WordPress Enterpise Plus theme training","3 Low","Sarah Lipsey","Andrea Stalker","Single Team/Dept","2019-06-30",null,"DO NOT TRACK HEALTH STATUS"]
["Academic Affairs","Placeholder Class Management q4","2 Normal","Marilee Ann Laurencell",null,null,"2019-09-30","PeopleSoft",null,null,null,null,null,"Testing"]
["Capital Planning and Campus Operations","TMA Payroll Reconciliation Automation","4 TBD/NE","ShayAlice Asterope Aradia",null,null,"2019-09-30","PeopleSoft:HR; TMA","Bumpy","2019-07-03",null,null,"Mark reviewing the amount of time this will take. He is over allocated and may not be able to resource this project. HR also needs to be involved in whether this project can \"touch\" HR payroll data."]
["Academic Affairs","25Live Lynx Upgrade","4 TBD/NE","Eddie F Waters Jr",null,null,"2019-09-30","25Live"]
["Academic Affairs","Replace Schedule of Classes PeopleSoft Modification","3 Low","Eddie F Waters Jr",null,null,"2019-09-30"]
["Capital Planning and Campus Operations","Implement Surplus Property Software WebData2","1 High","Mark Alan Niles",null,null,"2019-08-12",null,"On Track",43655,null,null,"Project should be going into production on 8/12/2019. CAB process will take place soon.","CAB/Final Wrap Up",null,null,null,null,null,"Go Live"]

{"sheet":"Resource Updates","index":2,"n_rows":1369,"n_cols":13,"rows_kept":1369,"cut":false,"hidden":false,"merged":[]}
["ProjectName","ResourceName","TaskName","AssignmentBookingName","AssignmentPercentWorkCompleted","AssignmentRemainingWork","AssignmentWork","TaskIsActive","ResourceDepartments_R","Role_R","TeamName_R","AssignmentStartDate","AssignmentFinishDate"]
["25Live Space Management System of Record Transition","April Anne Cook","Project Allocation","Commited",0,80,80,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["25Live Space Management System of Record Transition","Mark Alan Niles","Project Allocation","Commited",0,100,100,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["25Live Space Management System of Record Transition","Kyle Hamilton Cawood","Project Allocation","Commited",0,50,50,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["25Live Space Management System of Record Transition","Kristin Michelle Brown","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["2NAU Application-Prospect Project Phase 2","Tracy Anne Locarni","Project Allocation","Proposed",0,3,3,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T09:00:00","2019-09-30T17:00:00"]
["2NAU Application-Prospect Project Phase 2","John P Goral","Resource Allocation","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["2NAU Application-Prospect Project Phase 2","Raymond Drew Walker","Resource Allocation","Commited",0,40,40,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["2NAU Application-Prospect Project Phase 2","Allie Alterio","Integration for student comment","Proposed",0,8,8,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-04-01T17:00:00","2019-06-30T17:00:00"]
["2NAU Application-Prospect Project Phase 2","Chris Graver","Photo Card Upload","Commited",0,32,32,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["2NAU Application-Prospect Project Phase 2","Raymond Drew Walker","LDAP Development","Commited",100,0,10,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-01-02T08:00:00","2019-01-03T10:00:00"]
["2NAU Application-Prospect Project Phase 2","David Borsheim","Business Analyst","Proposed",100,0,10,true,"Non-IT Functional Office",null,"Functional","2019-01-02T08:00:00","2019-01-03T10:00:00"]
["2NAU Application-Prospect Project Phase 2","Tracy Anne Locarni","PS Development","Proposed",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-02T08:00:00","2019-03-30T17:00:00"]
["2NAU Application-Prospect Project Phase 2","Raymond Drew Walker","LDAP Feed","Commited",75,20,80,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ACA Presheet Updates","PeopleSoft Developer","ITS Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["ACA Presheet Updates","Renee Schenck","HR Resource Allocation BA","Commited",0,40,40,true,"Non-IT Functional Office",null,"Functional","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["Academic & Research Technology Services Operational Work","Peter Lindsay Gomersall","Resource Allocation","Commited",0,475,475,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Clinton Wayne Baker","Resource Allocation","Commited",0,475,475,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Keith Lyle Ballou","Resource Allocation","Commited",0,475,475,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Christopher Benjamin Coffey","Resource Allocation","Commited",0,475,475,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","William Edward Wilson","Resource Allocation","Commited",0,475,475,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Stacey Brewer","Resource Allocation","Commited",0,475,475,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Shane Kenneth Tsosie","Resource Allocation","Commited",0,475,475,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Michael Kenneth Fell","Resource Allocation","Commited",0,475,475,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Edward J Smith","Resource Allocation","Commited",0,350,350,true,"Academic & Research Technology Services","Academic and Research Technology Services.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Andrew Ned Jr","Resource Allocation","Commited",0,350,350,true,"Academic & Research Technology Services","Academic and Research Technology Services.Instructional Tech","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Kegan Elliott Remington","Resource Allocation","Commited",0,501,501,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Michael Lawrence MacPhee","Resource Allocation","Commited",0,501,501,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Brian Wirth Miller","Resource Allocation","Commited",0,501,501,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Shawn C Fowler","Resource Allocation","Commited",0,501,501,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Kent Walter Parks","Resource Allocation","Commited",0,501,501,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Nate See","Resource Allocation","Commited",0,501,501,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Tyanna Briann Burton","Resource Allocation","Commited",0,501,501,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Don Carter","Director","Commited",0,400,400,true,"Academic & Research Technology Services","Academic and Research Technology Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic & Research Technology Services Operational Work","Dan Stoffel","Associate Director","Commited",0,475,475,true,"Academic & Research Technology Services","Academic and Research Technology Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic Affairs - Division Wide Appointment Scheduler","EIS Full Stack Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Academic Restructure 2019","BPSM Applications Systems Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic Restructure 2019","Morrinda Lynn Balenquah","Project Allocation","Commited",0,60,60,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic Restructure 2019","Lynn Burch","Project Allocation","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic Restructure 2019","Marla J Johnet","Project Allocation","Commited",0,6,6,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic Restructure 2019","Chris Graver","Resource Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Academic Restructure 2019","Vivek Bongu","Resource Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Address Scrubbing Software Review-QAS Experian Software Expiration","CMT Analyst","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Address Scrubbing Software Review-QAS Experian Software Expiration","EIS Full Stack Developer","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Address Scrubbing Software Review-QAS Experian Software Expiration","Trey McCallie","Resource Allocation","Commited",0,20,20,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Address Scrubbing Software Review-QAS Experian Software Expiration","Erin Lindsey Plese","Resource allocation (invite to kick off, might not be a resource)","Commited",0,20,20,true,"Information Security Services","Information Security Services.Information Assurance","Functional","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Address Scrubbing Software Review-QAS Experian Software Expiration","Daniel Wallace","Resource allocation (invite to kick off, might not be a resource)","Commited",0,20,20,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ADP CY Q3 Update","PeopleSoft Developer","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-09-02T08:00:00","2019-09-30T17:00:00"]
["ADP CY2019 Q2 Tax andor Garnishment Update q4","PeopleSoft Developer","Project Allocation","Proposed",100,0,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-06-03T08:00:00","2019-06-03T17:00:00"]
["Advisor Assignment Tool for Admin Staff  III","Custom Developer","Project Allocation","Proposed",100,0,1,true,"Academic & Research Technology Services",null,null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Amazon Business q4","Raymond Drew Walker","Project Allocation","Commited",0,30,30,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Amazon Business q4","Kenneth Thomas Sager","Project Allocation","Commited",0,19.999983,19.999983,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Amazon Business q4","Trey McCallie","Project Allocation","Commited",0,15,15,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-04-01T08:00:00","2019-05-24T17:00:00"]
["Amazon Business q4","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["Annual Epact Report","Colinda Hardy Joe","Project Allocation","Proposed",100,0,40,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Annual Epact Report","Mark Alan Niles","Project Allocation","Proposed",100,0,10,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Appointment Scheduler - Release 4 Walk in Queue","Kevin Labranche","Project Allocation","Proposed",100,0,0.99998299999999996,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Appointment Scheduler - Release 4 Walk in Queue","Trey Mason","Project Allocation","Proposed",100,0,80,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Appointment Scheduler - Release 4 Walk in Queue","Rossana Garza","Project Allocation","Proposed",100,0,0.99998299999999996,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Appointment Scheduler - Release 4 Walk in Queue","Mary Mullen","Project Allocation","Proposed",100,0,0.99998299999999996,true,"Non-IT Functional Office","Provost.BA","Functional","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Appointment Scheduler - Release 4 Walk in Queue","Kevin Labranche","Project Allocation","Proposed",100,0,225,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Appointment Scheduler - Release 4 Walk in Queue","Steven Roy Hernandez","Project Allocation","Proposed",100,0,0.99998299999999996,true,"Non-IT Functional Office","Provost.BA","Functional","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Appointment Scheduler - Release 4 Walk in Queue","Sheri Ann Fetzer","Project Allocation","Proposed",100,0,0.99998299999999996,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Appointment Scheduler - Release 4 Walk in Queue","Kevin Labranche","Set up functionality to allow appts scheduled with any advisor from anywhere","Proposed",100,0,0.99998299999999996,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Appointment Scheduler - Release 4 Walk in Queue","Kevin Labranche","Create walk in queue","Proposed",100,0,0.99998299999999996,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["ArcGIS Enterprise Project","Matthew Natividad Tafoya","Project Allocation","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["ArcGIS Enterprise Project","Brett Austin West","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ArcGIS Enterprise Project","Chad Stiller","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ArcGIS Enterprise Project","Kim Ramirez","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ArcGIS Enterprise Project","Kristin Michelle Brown","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ArcGIS Enterprise Project","Matthew Natividad Tafoya","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ARTS operational work","Andrew Ned Jr","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Instructional Tech","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Ben Alfich","Project Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.ELC Tech Support.End User Computing Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Brian Wirth Miller","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Christopher Benjamin Coffey","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Clinton Wayne Baker","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Dan Stoffel","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Don Carter","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Edward J Smith","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","James Howard Crane","Project Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Jerold Thomas Gile","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Instructional Tech","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Kegan Elliott Remington","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Keith Lyle Ballou","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Kent Walter Parks","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Michael Kenneth Fell","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Michael Lawrence MacPhee","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Nate See","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Peter Lindsay Gomersall","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Shane Kenneth Tsosie","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Shawn C Fowler","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Stacey Brewer","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","Tyanna Briann Burton","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["ARTS operational work","William Edward Wilson","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Automate Electronic Course Materials Processing","Rossana Garza","Project Time","Proposed",100,0,80,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-01-02T08:00:00","2019-03-31T17:00:00"]
["Awareness Video - Data Protection","Erin Lindsey Plese","Project Allocation","Commited",74,5.1162789999999996,20,true,"Information Security Services","Information Security Services.Information Assurance","Functional","2019-03-01T08:00:00","2019-04-30T17:00:00"]
["Awareness Video - Data Protection","Training Developer","Project Allocation","Commited",17,0.83333299999999999,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Azure Web Development Practices and Usage Research","Custom Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development",null,"2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Azure Web Development Practices and Usage Research","Kevin Labranche","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Azure Web Development Practices and Usage Research","Vivek Bongu","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Azure Web Development Practices and Usage Research","Dave Dennehey","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Azure Web Development Practices and Usage Research","John Wesley Hutchison","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["BCBS HSA Plan","Ashlee Annabelle Binderim","Project Allocation","Commited",0,70,70,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-08-01T08:00:00","2019-10-31T17:00:00"]
["BCBS HSA Plan","PeopleSoft Developer","Project Allocation","Commited",0,16,16,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-08-01T08:00:00","2019-10-31T17:00:00"]
["Benefits PreSheet Addig PSPRS Audits","Margaret Montfort","Project Allocation","Proposed",100,0,25,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-30T17:00:00"]
["Benefits PreSheet Addig PSPRS Audits","Margaret Montfort","Project Allocation","Proposed",100,0,20,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-30T17:00:00"]
["Build Construction Estimates Form","Travis Nathaniel Hudson","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build Construction Estimates Form","Mark Alan Niles","Project Allocation","Commited",0,20,20,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Service Offering","Erin Lindsey Plese","Project Allocation","Commited",0,40,40,true,"Information Security Services","Information Security Services.Information Assurance","Functional","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Service Offering","April Anne Cook","Project Allocation","Commited",0,30,30,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Service Offering","Don Carter","Project Allocation","Commited",0,40,40,true,"Academic & Research Technology Services","Academic and Research Technology Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Service Offering","Raymond Drew Walker","Project Allocation","Commited",0,4,4,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Service Offering","Jonathan Andrew Wince","Project Allocation","Commited",0,20,20,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Service Offering","Trey McCallie","Project Allocation","Commited",0,8,8,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Service Offering","Louis Arminio","Project Allocation","Commited",0,40,40,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Service Offering","Michael William Zimmer","Project Allocation","Commited",0,40,40,true,"Information Security Services","Information Security Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Service Offering","Systems Administrator (Linux/Unix)","Project Allocation","Commited",0,40,40,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Training","Ashlee Annabelle Binderim","Project Allocation","Commited",0,60,60,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build CUI Training","Audrey O'Connell","Project Allocation","Commited",0,20,20,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build OnBase Forms Construction Estimates, Grand Master Key, Contractor Key Request","Generic Local Resource","Project Allocation","Commited",0,80,80,true,null,null,null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Build OnBase Forms Construction Estimates, Grand Master Key, Contractor Key Request","Mark Alan Niles","Project Allocation","Commited",0,8,8,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Build OnBase Forms Construction Estimates, Grand Master Key, Contractor Key Request","Generic Local Resource","Project Allocation","Commited",0,240,240,true,null,null,null,"2019-02-01T08:00:00","2019-03-31T17:00:00"]
["Build OnBase Forms Construction Estimates, Grand Master Key, Contractor Key Request","Generic Local Resource","Project Allocation","Commited",0,240,240,true,null,null,null,"2019-02-01T08:00:00","2019-03-31T17:00:00"]
["Build Pre-Lead to Lead Generation Solution","Damien Michael Coy","Project Allocation","Commited",0,28,28,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Build Pre-Lead to Lead Generation Solution","Amy J Fouts","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Build Pre-Lead to Lead Generation Solution","Amy J Fouts","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Build Pre-Lead to Lead Generation Solution","Esidro Moussa Hernandez","Resource Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-02T08:00:00","2019-10-01T17:00:00"]
["Build Pre-Lead to Lead Generation Solution","Garrett D Gallegos","Resource Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build Pre-Lead to Lead Generation Solution","Allie Alterio","Resource Allocation","Commited",0,300,300,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build Pre-Lead to Lead Generation Solution","Benjamin Joseph Liszewski","Resource Allocation","Commited",0,300,300,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build Pre-Lead to Lead Generation Solution","Sam R Stroud","Resource Allocation","Commited",0,240,240,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build Pre-Lead to Lead Generation Solution","Amy J Fouts","Resource Allocation","Commited",0,200,200,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build SHERC training","Audrey O'Connell","Project Allocation","Commited",0,120,120,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Build SHERC training","Ashlee Annabelle Binderim","Project Allocation","Commited",0,10,10,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Business Food and Meal Purchase Authorization Form and Workflow","BPSM Applications Systems Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Business Food and Meal Purchase Authorization Form and Workflow","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Business Food and Meal Purchase Authorization Form and Workflow","BPSM Applications Systems Analyst","Resource Allocation Onbase Developer","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Business Food and Meal Purchase Authorization Form and Workflow","Financials Business Analyst","Resource Allocation Peoplesoft Developer","Commited",0,1,1,true,"Non-IT Functional Office",null,"Functional","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Business Food and Meal Purchase Authorization Form and Workflow","PeopleSoft Developer","Resource Allocaton FIPA BA","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Business Services Team Operational Work","Albert Raymond Sandoval","Resource Allocation","Commited",0,501,501,true,"Business Services","Business Services.Financial Services.Accountant","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Business Services Team Operational Work","Jen Mason","Resource Allocation","Commited",0,501,501,true,"Business Services","Business Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Business Services Team Operational Work","Lea Elizabeth Pochyla","Resource Allocation","Commited",0,501,501,true,"Business Services","Business Services.Leadership Support.Executive Assistant","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Business Services Team Operational Work","Thomas Scott Cislo","Resource Allocation","Commited",0,501,501,true,"Business Services","Business Services.Computer Purchasing","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Bystander Intervention","Audrey O'Connell","script editing with client (sw worker 20 hours)","Proposed",100,0,30,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Campus Dining integration with NAUGo","EIS Full Stack Developer","Project Allocation","Commited",17,0.83333299999999999,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Campus Dining integration with NAUGo","Zachary David Gerber","Project Allocation","Commited",56,43.650793999999998,100,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-01-07T08:00:00","2019-06-30T17:00:00"]
["Campus Dining integration with NAUGo","Patricia Helene Allenbaugh","Project Allocation","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-01-07T08:00:00","2019-03-31T17:00:00"]
["Campus Dining integration with NAUGo","Kyle Hamilton Cawood","Project Allocation","Commited",100,0,39.999983,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-07T08:00:00","2019-03-31T17:00:00"]
["Campus-wide New NAU Logo Roll-Out Project (Technology Updates)","Ashlee Annabelle Binderim","Project Allocation","Commited",0,70,70,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Census Mod CC01417 MODIFICATION PROPOSAL","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-03-18T08:00:00","2019-03-18T17:00:00"]
["Classlist Mailing List Tool Enhancements","Identity and Access Analyst","Project Allocation","Commited",46,0.53921600000000003,1,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-02-08T08:00:00","2019-06-30T17:00:00"]
["Classroom Attendance Scanners","Kegan Elliott Remington","Project Allocation","Commited",0,20,20,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Classroom Attendance Scanners","Kegan Elliott Remington","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Clockwork System for Disability Services","Rob Moser","SSO Integration","Commited",0,8,8,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Clockwork System for Disability Services","PeopleSoft Developer","Web Services are done this is just if they need tweaking during testing","Commited",0,3,3,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Clockwork System for Disability Services","Kyle Hamilton Cawood","Systems Analysis work","Commited",0,30,30,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Complete connection between Business Objects and Data Cookbook","Blanche Johnson","Project Allocation","Commited",0,25,25,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Complete connection between Business Objects and Data Cookbook","Lynn Burch","Project Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Complete Isilon Storage Service Offering","Michele Francis","Project Allocation","Commited",0,528,528,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Complete Isilon Storage Service Offering","Clint William Gleason","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Complete Isilon Storage Service Offering","Clint William Gleason","Cutover","Commited",100,0,2,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-03-11T08:00:00","2019-03-11T10:00:00"]
["Complete Isilon Storage Service Offering","Clint William Gleason","Replication with North Node DC","Commited",100,0,4,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-14T08:00:00","2019-02-20T17:00:00"]
["Complete Isilon Storage Service Offering","Michele Francis","Cutover","Commited",100,0,2,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-03-11T08:00:00","2019-03-11T10:00:00"]
["Compliant storage environment for non-research HIPAA data","Erin Lindsey Plese","Project Allocation","Commited",0,24,24,true,"Information Security Services","Information Security Services.Information Assurance.Identity Systems Analyst","Functional","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Compliant storage environment for non-research HIPAA data","David Michael Faguy","Project Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Non-IT Functional Office","Provost","Functional","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Compliant storage environment for non-research HIPAA data","Elizabeth M Applebee","Project Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Non-IT Functional Office","Provost","Functional","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Compliant storage environment for non-research HIPAA data","Michael William Zimmer","Project Allocation","Commited",0,5,5,true,"Information Security Services","Information Security Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Compliant storage environment for non-research HIPAA data","Systems Administrator (Linux/Unix)","Project Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Configuration Management Database Phase II - population and monitoring","John Lowe","Project Allocation","Commited",0,1,1,true,"IT Service Management","Change Management Office","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["Configuration Management Database Phase II - population and monitoring","BPSM Applications Systems Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["Configuration Management Database Phase II - population and monitoring","Trevor A Luttinen","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["Continuing Student Persistence (Business Object reports)","Lynn Burch","Project Allocation","Commited",0,45,45,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Continuing Student Persistence (Business Object reports)","Adele Sidney Pablo","Project Allocation","Commited",0,45,45,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Continuing Student Persistence (Business Object reports)","Marla J Johnet","Project Allocation","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Convert ITS Service Pages to ServiceNow Knowledge Base Articles","Sarah H Lipsey","Resource Allocation","Proposed",100,0,1040,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-01-01T08:00:00","2019-04-30T17:00:00"]
["Course Fee Project","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Course Fee Project","Kathleen Ellis","Project Allocation","Commited",0,0.5,0.5,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-02-07T08:00:00","2019-03-31T17:00:00"]
["Course Fee Project","Kyle Hamilton Cawood","Project Allocation","Commited",0,0.5,0.5,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-02-07T08:00:00","2019-03-31T17:00:00"]
["Course Fee Project","Justin B Hagin","Project Allocation BA","Commited",0,33.333333000000003,33.333333000000003,true,"Non-IT Functional Office",null,"Functional","2019-02-07T08:00:00","2019-03-31T17:00:00"]
["Course Fee Project","Meg Flieger","Project Allocation BA","Commited",0,33.333333000000003,33.333333000000003,true,"Non-IT Functional Office","Provost.BA",null,"2019-02-07T08:00:00","2019-03-31T17:00:00"]
["Data Audit, Inventory, Classification Survey Review and Interviews","Michael William Zimmer","Project Allocation","Commited",100,0,1,true,"Information Security Services","Information Security Services","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Data Audit, Inventory, Classification Survey Review and Interviews","Steven W Andariese","Project Allocation","Commited",100,0,1,true,"Information Security Services","Information Security Services.Information Assurance.Identity Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Data mining log files for student engagement analysis","Trey McCallie","Project Allocation","Commited",0,10,10,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Data mining log files for student engagement analysis","Jonathan Andrew Wince","Project Allocation","Commited",0,30,30,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Data mining log files for student engagement analysis","Raymond Drew Walker","Project Allocation","Commited",0,15,15,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Data mining log files for student engagement analysis","Trey McCallie","Project Allocation","Commited",0,10,10,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Data mining log files for student engagement analysis","Jonathan Andrew Wince","Project Allocation","Commited",0,30,30,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Data mining log files for student engagement analysis","Raymond Drew Walker","Project Allocation","Commited",0,15,15,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Data mining log files for student engagement analysis","Amy J Fouts","Resource Allocation","Commited",0,40,40,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Data mining log files for student engagement analysis","Lynn Burch","Resource Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Data mining log files for student engagement analysis","Blanche Johnson","Resource Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.BA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Data mining log files for student engagement analysis","Daniel Wallace","Resource Allocation","Commited",0,40,40,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Degree Search Wordpress Implementation with Lipman Hearne","VPAA Business Analyst","Project Allocation","Commited",0,1,1,true,"Non-IT Functional Office",null,"Functional","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Departmental Deposit Form Workflow and PeopleSoft Integration","Kathleen Ellis","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Departmental Deposit Form Workflow and PeopleSoft Integration","Wesley Walker","Project Allocation","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Departmental Deposit Form Workflow and PeopleSoft Integration","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Departmental Deposit Form Workflow and PeopleSoft Integration","Jared Logan","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst",null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Design System Pilot","Patricia Helene Allenbaugh","Resource Allocation","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-09-30T08:00:00","2019-09-30T17:00:00"]
["Design System Pilot","Jason D Robinson","Resource Allocation","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Design","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Design System Pilot","Lyric L Peate","Resource Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Develop iconography for Credly badging for NAU - Prof Development efforts","Training Developer","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["Develop iconography for Credly badging for NAU - Prof Development efforts","UI-UX Designer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["Develop technology support for updating phone numbers, contact info in Louie once a term","Kyle Hamilton Cawood","Project Allocation","Commited",0,40,40,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Develop web services to pull course offerings from PeopleSoft q4","Chris Graver","Project Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Develop web services to pull course offerings from PeopleSoft q4","Kyle Hamilton Cawood","Project Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Develop web services to pull course offerings from PeopleSoft q4","Damien Michael Coy","Project Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-07-30T17:00:00"]
["Develop web services to pull course offerings from PeopleSoft q4","Chris Graver","Project Allocation","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-08-01T08:00:00","2019-08-15T17:00:00"]
["Development of Badging System for CE and PD","Damien Michael Coy","Project Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Development of Badging System for CE and PD","Systems Administrator (Academic and Research)","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Development of Badging System for CE and PD","Ashlee Annabelle Binderim","Project Allocation","Commited",0,40,40,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Development of Badging System for CE and PD","Lyric L Peate","Project Allocation","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Development of Badging System for CE and PD","Andrea Stalker","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Development of Badging System for CE and PD","Troy Anthony Marino","Project Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Development of Badging System for CE and PD","Jared I Logan","Project Allocation","Commited",0,10,10,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Directory revamp","Jared I Logan","Project Allocation","Commited",0,440,440,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-16T08:00:00","2019-06-30T17:00:00"]
["Directory revamp","Jared I Logan","Project Allocation","Commited",0,65,65,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-16T09:45:36","2019-09-30T17:00:00"]
["Directory revamp","John P Goral","Project Allocation","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Directory revamp","Chris Graver","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Directory revamp","Ashlee Annabelle Binderim","Project Allocation","Commited",0,45,45,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Directory revamp","Kyle Hamilton Cawood","Project Allocation","Commited",0,220,220,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Directory revamp","Trey Mason","Project Allocation","Commited",17,100,120,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Directory revamp","Jason D Robinson","Project Allocation","Commited",17,33.333333000000003,40,true,"Enterprise Information Solutions","Enterprise Information Services.Design","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Directory revamp","Trey Mason","Project Allocation","Commited",10,179.6,200,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Directory revamp","Raymond Drew Walker","Project Allocation","Commited",100,0,2.5714169999999998,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-03-25T08:00:00","2019-03-30T17:00:00"]
["Directory revamp","Trey McCallie","Project Allocation","Commited",100,0,1.2857000000000001,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-03-25T08:00:00","2019-03-30T17:00:00"]
["Directory revamp","Jared I Logan","Project Allocation","Commited",100,0,0,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-03-25T08:00:00","2019-03-25T08:00:00"]
["Directory revamp","Damien Michael Coy","Project allocation (WordPress Redirects)","Commited",2,156.6,160,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Directory revamp","Jason D Robinson","Project Allocation (design)","Commited",100,0,3.3802669999999999,true,"Enterprise Information Solutions","Enterprise Information Services.Design","ITS","2019-03-25T08:00:00","2019-03-30T17:00:00"]
["Directory revamp","John Wesley Hutchison","Project Allocation (Admin)","Commited",21,62.857149999999997,80,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Directory revamp","Damien Michael Coy","Project allocation (WordPress Redirects)","Commited",12,17.600000000000001,20,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Directory revamp","Trey Mason","Project Allocation (Front End Dev)","Commited",100,0,10.2857,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-03-25T08:00:00","2019-03-30T17:00:00"]
["Directory revamp","Chris Graver","Project Allocation (PS and Elastic)","Commited",21,62.857149999999997,80,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Discovery for NAU Data Strategy","Marc H Lord","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Document Submission Form,Supply Order Request Form","BPSM Applications Systems Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Document Submission Form,Supply Order Request Form","Travis Nathaniel Hudson","Project Allocation","Commited",0,240,240,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Document Submission Form,Supply Order Request Form","Mara Nicole Hardman","Project Allocation","Proposed",0,1,1,true,"Non-IT Functional Office",null,"Functional","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["DUPE - NAU Directory Re-architecture and redevelopment Ph I","Chris Graver","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["DUPE-upgrade Informatica Cloud, Informatica Power Center and separate Databases","Database Administrator","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["DUPE-upgrade Informatica Cloud, Informatica Power Center and separate Databases","Integration Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["DUPE-upgrade Informatica Cloud, Informatica Power Center and separate Databases","IRA Business Analyst","Project Allocation","Commited",0,1,1,true,"Non-IT Functional Office",null,"Functional","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["DUPE-upgrade Informatica Cloud, Informatica Power Center and separate Databases","Systems Administrator (Linux/Unix)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["DUPE-upgrade Informatica Cloud, Informatica Power Center and separate Databases","Project Manager","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["DUPE-upgrade Informatica Cloud, Informatica Power Center and separate Databases","Data Warehouse Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["Duplicate_SMS Texting","Garrett D Gallegos","Project Allocation","Commited",0,10,10,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-06-03T08:00:00","2019-09-30T17:00:00"]
["EDI Master Project","Generic Local Resource","Project Allocation","Proposed",100,0,10,true,null,null,null,"2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Vivek Bongu","Project Allocation","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","CMT Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Database Administrator","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Dave Dennehey","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Systems Administrator (Microsoft)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Chad Stiller","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Information Security Analyst","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","James Moses","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Michael William Zimmer","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Peter Lindsay Gomersall","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Systems Administrator (Microsoft)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Jonathan Andrew Wince","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Damien Michael Coy","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","John Wesley Hutchison","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Kevin Labranche","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Trey McCallie","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["EIS Custom Development - Systems enhancement","Chris Graver","Give access to PMO of TFS","Commited",0,2,2,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-02-27T08:00:00","2019-02-27T17:00:00"]
["EIS-Operational Work","Adele Sidney Pablo","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Allie Alterio","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Benjamin Joseph Liszewski","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Blanche Johnson","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.BA","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Chad Stiller","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Chris Graver","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Damien Michael Coy","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Darla Waddell","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.CPCS","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Dave Dennehey","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","David B Brink","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","David D Bosse","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","David E Chapman","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Deb Stevens","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Dina Ann Barnese","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Donna Bartlett","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Dylan Baxter","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Fen Zheng","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Garrett D Gallegos","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Holly S Coast","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.Web Developer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","James Earl Shaeffer","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","James Moses","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Jason D Robinson","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Design","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Jean Ann Adams","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Jed David Moss","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","John P Goral","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","John Wesley Hutchison","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Joseph Flieger","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Kevin Jeffrey Theiss","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Kevin Labranche","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Kevin Michael Hayes","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Kristin Michelle Brown","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Leslie Mathews","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Linda Krey Osthreim","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Lynn Burch","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Lyric L Peate","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Marc Alan Colvin","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Marc H Lord","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Margaret Montfort","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Mark Timothy Staten","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Mark Young","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Marla J Johnet","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.Data Warehouse Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Matthew Natividad Tafoya","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Molly Holland","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Morrinda Lynn Balenquah","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Patricia Helene Allenbaugh","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Paul Lambert","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Paula Jean Aerts","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Robert Scott Brubaker","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Rusty Neeb","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Rye Schnebly Heidinger","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Sam R Stroud","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Samuel Keegan Harsha","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Syed Ahsan Imam","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Talbert A Tso","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Tracy Anne Locarni","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Travis Nathaniel Hudson","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Trevor A Luttinen","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Trey Mason","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Troy Anthony Marino","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Vincent Messenger","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Vivek Bongu","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","Wesley Walker","Project Allocation","Commited",0,200,200,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EIS-Operational Work","William Joseph Creedon","Project Allocation","Commited",0,200,200,true,null,null,null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["EMSA - Veterans Website","John Wesley Hutchison","Project work","Proposed",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2018-12-31T08:00:00","2018-12-31T17:00:00"]
["EMSA Salesforce Major Release FY19Q1","Allie Alterio","Project Allocation","Proposed",0,45,45,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["EMSA Salesforce Major Release FY19Q1","Benjamin Joseph Liszewski","Project Allocation","Proposed",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["EMSA Salesforce Major Release FY19Q1","David Borsheim","Project Allocation","Proposed",0,20,20,true,"Non-IT Functional Office",null,"Functional","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["EnergyCap 15 Minute Interval and Billing Process Change q4","Systems Administrator (Linux/Unix)","Project Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Infrastructure & Platform Services","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enrollment Override stop for financial holds","Fen Zheng","Project Allocation","Proposed",100,0,30,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-02T08:00:00","2019-01-25T17:00:00"]
["Enrollment Override stop for financial holds","Nicole Noel Kaoni","Project Allocation","Proposed",100,0,30,true,"Non-IT Functional Office","Provost.BA","Functional","2019-01-02T08:00:00","2019-01-25T17:00:00"]
["Enterprise Information Services Operational Work","Damien Michael Coy","Resource Allocation","Commited",0,317,317,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Joseph Flieger","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Chris Graver","Resource Allocation","Commited",0,317,317,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Mark Young","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Donna Bartlett","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","David D Bosse","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Leslie Mathews","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Morrinda Lynn Balenquah","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Tracy Anne Locarni","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Margaret Montfort","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Deb Stevens","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Fen Zheng","Resource Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Vivek Bongu","Resource Allocation","Commited",0,317,317,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Jason D Robinson","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Design","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Patricia Helene Allenbaugh","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Lyric L Peate","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Molly Holland","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Kevin Michael Hayes","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","David B Brink","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Marc Alan Colvin","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Marla J Johnet","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.Data Warehouse Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Allie Alterio","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Holly S Coast","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Garrett D Gallegos","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Samuel Keegan Harsha","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Benjamin Joseph Liszewski","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Kevin Jeffrey Theiss","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Sam R Stroud","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Esidro Moussa Hernandez","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Paula Jean Aerts","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","David E Chapman","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Dave Dennehey","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Rusty Neeb","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Darla Waddell","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.CPCS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Rye Schnebly Heidinger","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","James Earl Shaeffer","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Dylan Baxter","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Lynn Burch","Resource Allocation","Commited",0,314,314,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Blanche Johnson","Resource Allocation","Commited",0,314,314,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.BA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Adele Sidney Pablo","Resource Allocation","Commited",0,314,314,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Matthew Natividad Tafoya","Resource Allocation","Commited",0,314,314,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Kristin Michelle Brown","Resource Allocation","Commited",0,314,314,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Jed David Moss","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Wesley Walker","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Travis Nathaniel Hudson","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Mark Timothy Staten","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Talbert A Tso","Resource Allocation","Commited",0,218,218,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Kevin Labranche","Resource Allocation (Gateway Work Multi Admit Term)","Commited",0,100,100,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Chris Graver","Vacation","Commited",0,105,105,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Jean Ann Adams","Vacation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Jason D Robinson","Marketing Support","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Design","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Patricia Helene Allenbaugh","Marketting Support","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Lyric L Peate","Marketing Support","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Patricia Helene Allenbaugh","Nau.edu architecture","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-07-30T17:00:00"]
["Enterprise Information Services Operational Work","Lyric L Peate","Nau.edu architecture","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-07-30T17:00:00"]
["Enterprise Information Services Operational Work","Jason D Robinson","Nau.edu architecture","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Design","ITS","2019-07-01T08:00:00","2019-07-30T17:00:00"]
["Enterprise Information Services Operational Work","Troy Anthony Marino","Resource Allocation (50% Operational, 30 hours of work for departures)","Commited",0,295,295,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Trey Mason","Resource Allocation (50% Operational, 30 hours of work for departures)","Commited",0,295,295,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Jean Ann Adams","Resource Allocation (50% Operational, 30 hours of work for departures)","Commited",0,295,295,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Trevor A Luttinen","Resource Allocation (50% Operational, 30 hours of work for departures)","Commited",0,295,295,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","John P Goral","Resource Allocation (50% Operational, 30 hours of work for departures)","Commited",0,295,295,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise Information Services Operational Work","Kevin Labranche","Resource Allocation (50% Operational, 30 hours of work for departures)","Commited",0,295,295,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Enterprise TLS Update Phase 3","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Enterprise TLS Update Phase 3","Identity and Access Analyst","ITS SOC Resource Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Enterprise TLS Update Phase 3","CMT Analyst","ITS SOC Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Establishing a Science DMZ","Database Administrator","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Establishing a Science DMZ","NOC Network Engineer","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Establishing a Science DMZ","Systems Administrator (Linux/Unix)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Establishing a Science DMZ","Systems Administrator (Microsoft)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Establishing a Science DMZ","James C Davis","Project Allocation","Commited",0,80,80,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Establishing a Science DMZ","Christopher Benjamin Coffey","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Establishing a Science DMZ","Systems Administrator (Academic and Research)","Project Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Evaluate new Anti-Virus Software for Mac OS","Thomas Ashton Hahnke","Project Allocation","Commited",0,40,40,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Evaluate new Anti-Virus Software for Mac OS","Jared Logan","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst",null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Evaluate new Anti-Virus Software for Mac OS","Systems Administrator (Desktop Imaging)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Evaluate ServiceNow Project Management Module","Project Manager","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Evaluate ServiceNow Project Management Module","ServiceNow Administrator","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Evaluate ServiceNow Project Management Module","Systems Analyst","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Event Management","Lynn Burch","","Proposed",100,0,50,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-01-01T08:00:00","2019-01-09T10:00:00"]
["Event Management","Kevin Labranche","PEADMIN Development Work","Proposed",1,79,80,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-04-12T16:00:00"]
["Event Management","Benjamin Joseph Liszewski","Salesforce Work","Proposed",1,79,80,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-01-01T08:00:00","2019-04-12T16:00:00"]
["Event Management","Garrett D Gallegos","Salesforce Work","Proposed",20,4,5,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-01-01T08:00:00","2019-04-01T12:00:00"]
["Event Management","Allie Alterio","Salesforce Work","Proposed",100,0,0,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-01-01T08:00:00","2019-01-01T08:00:00"]
["Execute Automated Student Enrollment Process PS Class Match","Steven Roy Hernandez","Resource Allocation","Proposed",100,0,90,true,"Non-IT Functional Office","Provost.BA","Functional","2019-02-08T08:00:00","2019-03-31T17:00:00"]
["Execute Event Management Judging Software","Trey McCallie","SAML/CAS SSO","Proposed",100,0,3,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-02-14T08:00:00","2019-02-14T17:00:00"]
["Execute Event Management Judging Software","Brett Austin West","Networking","Proposed",100,0,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Execute Event Management Judging Software","Rob Moser","SAML Set up","Proposed",100,0,5,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-01-01T08:00:00","2019-02-14T17:00:00"]
["Execute Group Wrangler  Global Program Manager new app - IGP","EIS Full Stack Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Execute PEP Title II Project","Benjamin Joseph Liszewski","Project Allocation","Commited",0,10,10,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Execute PEP Title II Project","Allie Alterio","Project Allocation","Commited",0,10,10,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Execute PEP Title II Project","Tracy Anne Locarni","Project Allocation","Commited",0,10,10,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Execute PEP Title II Project","Steven Roy Hernandez","Project Allocation","Commited",0,40,40,true,"Non-IT Functional Office","Provost.BA","Functional","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Execute PEP Title II Project","Kathleen Ellis","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Execute Suitable","Integration Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-30T17:00:00"]
["Execute Suitable","Data Visualization Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-04-01T08:00:00","2019-04-30T17:00:00"]
["Execute Suitable","Bradley Brian Cislo","Project Allocation","Commited",0,1,1,true,null,null,null,"2019-01-30T08:00:00","2019-03-31T17:00:00"]
["Execute Suitable","Trey McCallie","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-01-30T08:00:00","2019-03-31T17:00:00"]
["Execute Sunapsis Upgrade","Bryan G Loveless","Project Allocation","Commited",0,4,4,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-03-30T08:00:00","2019-06-30T17:00:00"]
["Execute Sunapsis Upgrade","James Slebodnick","Project Allocation","Commited",0,10,10,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-03-30T08:00:00","2019-06-30T17:00:00"]
["Execute Sunapsis Upgrade","John R Meyer","Project Allocation","Commited",0,12,12,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-03-30T08:00:00","2019-06-30T17:00:00"]
["Execute Sunapsis Upgrade","John Thomas Davies","Project Allocation","Commited",0,3,3,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-03-30T08:00:00","2019-06-30T17:00:00"]
["Execute Sunapsis Upgrade","Marilee Ann Laurencell","Project Allocation","Commited",0,80,80,true,"Non-IT Functional Office","Provost.BA","Functional","2019-03-30T08:00:00","2019-06-30T17:00:00"]
["Execute Sunapsis Upgrade","Steven Roy Hernandez","Project Allocation","Commited",0,80,80,true,"Non-IT Functional Office","Provost.BA","Functional","2019-03-30T08:00:00","2019-06-30T17:00:00"]
["Execute Sunapsis Upgrade","Brian Velde","Project Allocation","Commited",0,10,10,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-03-30T08:00:00","2019-06-30T17:00:00"]
["Execute Sunapsis Upgrade","Marilee Ann Laurencell","Project Allocation","Commited",0,80,80,true,"Non-IT Functional Office","Provost.BA","Functional","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Execute Sunapsis Upgrade","Steven Roy Hernandez","Project Allocation","Commited",0,80,80,true,"Non-IT Functional Office","Provost.BA","Functional","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Execute Sunapsis Upgrade","Brian Velde","Project Allocation","Commited",0,15,15,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Execute Sunapsis Upgrade","Bryan G Loveless","Project Allocation","Commited",0,15,15,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Execute Sunapsis Upgrade","James Slebodnick","Project Allocation","Commited",0,16,16,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Execute Sunapsis Upgrade","John R Meyer","Project Allocation","Commited",0,30,30,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Execute Sunapsis Upgrade","John Thomas Davies","Project Allocation","Commited",0,4,4,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["FA document upload Phase 2","Talbert A Tso","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Faculty and Staff Degree Tracking","PeopleSoft Developer","Project Allocation","Proposed",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["Faculty and Staff Degree Tracking","HR Business Analyst","Resource Allocation","Proposed",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-01-01T08:00:00","2019-01-01T08:00:00"]
["Faculty and Staff Degree Tracking","Project Manager","Resource Allocation","Proposed",0,0,0,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-01-01T08:00:00","2019-01-01T08:00:00"]
["Fields added to a Data View for Residence Life","Mark Alan Niles","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Fields added to a Data View for Residence Life","Kevin Michael Hayes","Project Allocation","Proposed",100,0,3,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Fields added to a Data View for Residence Life","Tracy Anne Locarni","Project Allocation","Proposed",100,0,5,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Financial Aid - Upload documents into Sharebase","Talbert A Tso","Project Allocation","Proposed",100,0,77,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-27T17:00:00"]
["Financial Aid - Upload documents into Sharebase","BPSM Student Worker","Project Allocation","Proposed",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.Student Employees","ITS","2019-01-01T08:00:00","2019-03-27T17:00:00"]
["Financial Aid - Upload documents into Sharebase","Jordan Christopher Jones","Project Allocation","Proposed",100,0,30,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-01-01T08:00:00","2019-03-27T17:00:00"]
["Financial Aid - Upload documents into Sharebase","April Anne Cook","Project Allocation","Proposed",100,0,5,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-01-01T08:00:00","2019-03-27T17:00:00"]
["Going global project (CIE)","Damien Michael Coy","Project Allocation","Proposed",100,0,5,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-04-01T08:00:00","2019-05-30T17:00:00"]
["Going global project (CIE)","Jason D Robinson","Project Allocation","Proposed",100,0,5,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-04-01T08:00:00","2019-05-30T17:00:00"]
["Graduate College Accelerated Program Enhancement q4","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-28T08:00:00","2019-01-28T17:00:00"]
["Graduate College Accelerated Program Enhancement q4","Custom Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development",null,"2019-01-28T08:00:00","2019-01-28T17:00:00"]
["Graduate College Accelerated Program Enhancement q4","Amy J Fouts","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-28T08:00:00","2019-01-28T17:00:00"]
["Group Management, Access Control, Directory Synchronization","Duane Booher","Project Allocation","Commited",0,1,1,true,null,null,"ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Group Management, Access Control, Directory Synchronization","Jonathan Andrew Wince","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Group Management, Access Control, Directory Synchronization","Raymond Drew Walker","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Group Management, Access Control, Directory Synchronization","Trey McCallie","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Group Management, Access Control, Directory Synchronization","Database Administrator","ITS DBA Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Group Management, Access Control, Directory Synchronization","Systems Administrator (Microsoft)","ITS IaaS SA Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Group Management, Access Control, Directory Synchronization","Clint William Gleason","ITS Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["HLC SQR enhancements for insurance eligibility q4","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Hyper-converged server consolidation","Systems Administrator (Linux/Unix)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Hyper-converged server consolidation","Systems Administrator (Microsoft)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Hyper-converged server consolidation","NOC Network Engineer","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Hyper-converged server consolidation","Systems Administrator (Linux/Unix)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Hyper-converged server consolidation","Systems Administrator (Microsoft)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Hyper-converged server consolidation","NOC Network Engineer","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["IAM Platform RFP","Clint William Gleason","Resource Allocation","Commited",0,12,12,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["IAM Platform RFP","Devon Joseph Brookshire","Resource Allocation","Commited",0,12,12,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["IAM Platform RFP","Jared I Logan","Resource Allocation","Commited",0,60,60,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["IAM Platform RFP","Raymond Drew Walker","Resource Allocation","Commited",0,28,28,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["IAM Platform RFP","Trey McCallie","Resource Allocation","Commited",0,28,28,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["IAM Platform RFP","Kathleen Ellis","Resource Allocation","Commited",0,60,60,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["IAM Platform RFP","Jonathan Andrew Wince","Resource Allocation","Commited",0,28,28,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["iModules for Alumni","Amy J Fouts","Project Allocation","Commited",0,60,60,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["iModules for Alumni","Damien Michael Coy","Project Allocation","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["iModules for Alumni","Jason D Robinson","Project Allocation","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["iModules for Alumni","Trey McCallie","Project allocation (invite Trey to kick off)","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement CollegeNet Admit","PeopleSoft Developer","Project Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement In-Application Registration hooked to Jacks Scheduler","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement logic in pay questions","Trevor A Luttinen","Project Allocation","Commited",0,100,100,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement logic in pay questions","Kyle Hamilton Cawood","Resource Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement logic in pay questions","Bradley Allen Miner","Resource Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Non-IT Functional Office",null,"Functional","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement logic in pay questions","Gina Kaiser Vance","Resource Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,null,null,null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement logic in pay questions","Meredith A Curley","Resource Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,null,null,null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement logic in pay questions","Steven Roy Hernandez","Resource Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Non-IT Functional Office","Provost.BA","Functional","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement logic in pay questions","Theresa Ann Rogers","Resource Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Non-IT Functional Office",null,"Functional","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement new budget software","Kevin G Stoffers","Resource Allocation","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement new budget software","Computer Operator","Resource Allocation","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement new budget software","Jared I Logan","Resoure Allocation","Commited",0,60,60,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement new budget software","Training Developer","Resource allocation (Jeremy invited to kick off meeting)","Commited",0,30,30,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement new budget software","PeopleSoft Developer","Project Allocation (dependent on scope of work)","Commited",0,24,24,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement New Professional Development LMS system","EIS Programmer Student Worker","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement New Professional Development LMS system","Sarah H Lipsey","Project Allocation","Commited",0,80,80,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement New Professional Development LMS system","Jared I Logan","Project Allocation","Commited",0,299,299,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement Project Management service PMWeb for CapCOT","Mark Alan Niles","Project Allocation","Commited",0,19.999983,19.999983,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Implement Project Management service PMWeb for CapCOT","Marla J Johnet","Project Allocation","Commited",0,25,25,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["Implement Project Management service PMWeb for CapCOT","Adele Sidney Pablo","Project Allocation","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["Implement Project Management service PMWeb for CapCOT","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["Implement Project Management service PMWeb for CapCOT","Mark Alan Niles","Project Allocation","Commited",0,100,100,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement Solution for NAU Strategic Goals Management System","Financial Support","Resource Allocation","Commited",0,1,1,true,"Business Services","Business Services.Financial Services.Accountant","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement Solution for NAU Strategic Goals Management System","Marc H Lord","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement Solution for NAU Strategic Goals Management System","Software/Asset Management","Resource Allocation","Commited",0,1,1,true,"Business Services","Business Services.Computer Purchasing","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement Solution for NAU Strategic Goals Management System","Training Developer","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Implement Surplus Property Software WebData 2","Mark Alan Niles","Project Allocation","Commited",0,3,3,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-09T08:00:00","2019-08-05T17:00:00"]
["Implement Surplus Property Software WebData 2","Mark Alan Niles","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Implement Surplus Property Software WebData 2","Terrel Glenn Scambler","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Improve e-Commerce service offering for eBIZ forms, shopping carts, et al","PeopleSoft Developer","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-30T17:00:00"]
["Improve e-Commerce service offering for eBIZ forms, shopping carts, et al","Project Manager","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-01-01T08:00:00","2019-03-30T17:00:00"]
["Improve e-Commerce service offering for eBIZ forms, shopping carts, et al","EIS Full Stack Developer","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-30T17:00:00"]
["Improve Facilities Existing Forms Release FY19Q2","Mark Alan Niles","Resource Allocation","Proposed",100,0,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Improve Facilities Existing Forms Release FY19Q2","C Michael Givens","Resource Allocation","Proposed",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Improve Facilities Existing Forms Release FY19Q2","Mark Alan Niles","Resource Allocation","Proposed",100,0,40,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Improvements to existing Onbase forms - Daily Log and Vehicle Request","BPSM Student Worker","Project Allocation","Proposed",100,0,80,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.Student Employees","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Improvements to existing Onbase forms - Daily Log and Vehicle Request","BPSM Student Worker","Project Allocation","Proposed",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.Student Employees","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Improvements to existing Onbase forms - Daily Log and Vehicle Request","Mark Alan Niles","Project Allocation","Proposed",100,0,20,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Information Security Services  Operational Work","Erin Lindsey Plese","Resource Allocation","Commited",0,264,264,true,"Information Security Services","Information Security Services.Information Assurance","Functional","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Information Security Services  Operational Work","Daniel Wallace","Resource Allocation","Commited",0,264,264,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Information Security Services  Operational Work","James C Davis","Resource Allocation","Commited",0,264,264,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Information Security Services  Operational Work","Jonathan Andrew Wince","Resource Allocation","Commited",0,264,264,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Information Security Services  Operational Work","Kenneth Thomas Sager","Resource Allocation","Commited",0,264,264,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Information Security Services  Operational Work","Michael William Zimmer","Resource Allocation","Commited",0,53,53,true,"Information Security Services","Information Security Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Information Security Services  Operational Work","Raymond Drew Walker","Resource Allocation","Commited",0,53,53,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Information Security Services  Operational Work","Trey McCallie","Resource Allocation","Commited",0,264,264,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Information Technology Service Management Operational Work","Celisa Manly","Resource Allocation","Commited",0,317,317,true,"IT Service Management","Change Management Office.Change Manager","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Information Technology Service Management Operational Work","John Lowe","Resource Allocation","Commited",0,317,317,true,"IT Service Management","Change Management Office","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["InfoSec Operational Work","Raymond Drew Walker","Operational work","Commited",0,468,468,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["InfoSec Operational Work","Jonathan Andrew Wince","Operational work","Commited",0,260,260,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["InfoSec Operational Work","Trey McCallie","","Commited",0,260,260,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["InfoSec Operational Work","Erin Lindsey Plese","Operational work","Commited",0,260,260,true,"Information Security Services","Information Security Services.Information Assurance","Functional","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["InfoSec Operational Work","Daniel Wallace","Operational work","Commited",0,260,260,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["InfoSec Operational Work","Kenneth Thomas Sager","Operational work","Commited",0,260,260,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["InfoSec Operational Work","Michael William Zimmer","Operational work","Commited",0,260,260,true,"Information Security Services","Information Security Services","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["InfoSec Operational Work","James C Davis","Operational work","Commited",0,260,260,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["Infrastructure & Platform Services Operational Work","Jamie Langdon","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator",null,"2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Jacob Raymond Maxton","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant.TST",null,"2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Brett Austin West","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Kim Ramirez","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Christopher Joe Chapman","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","James Slebodnick","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Kevin G Stoffers","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Kristopher R Bullins","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Timothy William Cochran","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Bryan G Loveless","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","John R Meyer","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Tobias J Kreidl","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","John Thomas Davies","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Thomas Ashton Hahnke","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","David W Starmer","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Clint William Gleason","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Louis Arminio","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Lisa A Doherty","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Federico Gallardo","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Brian Velde","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Robert Michael Watford","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Michele Francis","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Jeremy D Anderson","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","David N Russell","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Armand E Ramirez","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Devon Joseph Brookshire","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Matthew Charles Sells","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Jason T Ailiff","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Christopher Ferris Breazeale","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant.TST","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","James Freeman Morris","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant.TST","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Paul Merciano Trujillo","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Telecom Engineer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Terrel Glenn Scambler","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Jimmy Yellowhair","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Robyn Kay Guthrie","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Mark T Hemsath","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Kathleen Elise Sweebe","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Leon Lavester Hicks","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Steven J Depinet","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Leiann Morris","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.TSC","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Stanley Richard Hague","Resource Allocation","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Infrastructure & Platform Services Operational Work","Kirk Drew Bastian","IoT & Lenel","Commited",0,264,264,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.IoT.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Inspection Request Form","Travis Nathaniel Hudson","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Inspection Request Form","Mark Alan Niles","Project Allocation","Commited",0,20,20,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["IPS Non-Project Work","Kim Ramirez"," project allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Christopher Joe Chapman"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","James Slebodnick"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Kevin G Stoffers"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Timothy William Cochran"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Bryan G Loveless"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Kristopher R Bullins"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","John R Meyer"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Tobias J Kreidl"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","John Thomas Davies"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Thomas Ashton Hahnke"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","David W Starmer"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Robert P Lightner"," project allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Louis Arminio"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Lisa A Doherty"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Federico Gallardo"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Clint William Gleason"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Brian Velde"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Robert Michael Watford"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Michele Francis"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Jamie Langdon"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator",null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Jeremy D Anderson"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Generic Local Resource"," project allocation","Commited",0,1,1,true,null,null,null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Kirk Drew Bastian"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.IoT.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Paul Merciano Trujillo"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Telecom Engineer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Armand E Ramirez"," project allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Devon Joseph Brookshire"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Matthew Charles Sells"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Jason T Ailiff"," project allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Jacob Raymond Maxton"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant.TST",null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Christopher Ferris Breazeale"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant.TST","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","William Paul Martinchuk"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant.TST","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","James Freeman Morris"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant.TST","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Terrel Glenn Scambler"," project allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Jimmy Yellowhair"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Robyn Kay Guthrie"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Mark T Hemsath"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Stanley Richard Hague"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Kathleen Elise Sweebe"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Leon Lavester Hicks"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.CO","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Steven J Depinet"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","Leiann Morris"," project allocation","Commited",0,260,260,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.TSC","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IPS Non-Project Work","David N Russell"," project allocation","Commited",0,528,528,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IRA DATA REQUEST ROUTING  TASK MANAGEMENT SYSTEM REQUIREMENTS q4","Amy J Fouts","Project Allocation","Commited",0,10,10,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IRA DATA REQUEST ROUTING  TASK MANAGEMENT SYSTEM REQUIREMENTS q4","Jared Logan","Project Allocation","Commited",0,10,10,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst",null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["IRA DATA REQUEST ROUTING  TASK MANAGEMENT SYSTEM REQUIREMENTS q4","BPSM Applications Systems Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["ITS - ServiceNow processes, procedures and administration","Jed David Moss","Project Allocation","Commited",0,213,213,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS - ServiceNow processes, procedures and administration","Travis Nathaniel Hudson","Project Allocation","Commited",0,113,113,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS - ServiceNow processes, procedures and administration","Trevor A Luttinen","Project Allocation","Commited",0,113,113,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS - ServiceNow processes, procedures and administration","Wesley Walker","Project Allocation","Commited",0,113,113,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS - ServiceNow processes, procedures and administration","John Lowe","Project Allocation","Commited",0,40,40,true,"IT Service Management","Change Management Office","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Checklist - Enhancements and CSR Inclusion","Amy J Fouts","Project Allocation","Commited",0,0.33333299999999999,0.33333299999999999,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["ITS Checklist - Enhancements and CSR Inclusion","Jared Logan","Project Allocation","Commited",0,0.33333299999999999,0.33333299999999999,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst",null,"2019-01-01T08:00:00","2019-03-29T17:00:00"]
["ITS Checklist - Enhancements and CSR Inclusion","Kathleen Ellis","Project Allocation","Commited",0,0.33333299999999999,0.33333299999999999,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["ITS Checklist - Enhancements and CSR Inclusion","BPSM Applications Systems Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["ITS Disaster Recovery","Kim Ramirez","Resource Allocation","Commited",0,528,528,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Disaster Recovery","Federico Gallardo","Resource Allocation","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Disaster Recovery","Clint William Gleason","Resource Allocation","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Disaster Recovery","Timothy William Cochran","Resource Allocation","Commited",0,9,9,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Disaster Recovery","Armand E Ramirez","Resource Allocation","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Disaster Recovery","Sarah H Lipsey","Resource Allocation","Commited",0,18,18,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Disaster Recovery","John Thomas Davies","Resource Allocation","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Disaster Recovery","Tobias J Kreidl","Resource allocation (High: 48; Low: 24)","Commited",0,36,36,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Disaster Recovery","Bryan G Loveless","Resource allocation (cannot resource Q1, ok to move forward without)","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Drive Mapping","John Angelo Cencioso","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Drive Mapping","BA Russell","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support North.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Drive Mapping","Tobias J Kreidl","Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Drive Mapping","Michele Francis","Resource Allocation","Commited",0,150,150,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Drive Mapping","Kristopher R Bullins","Resource Allocation","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Drive Mapping","Lisa P. Young","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Drive Mapping","William Edward Wilson","Resource Allocation","Commited",0,40,40,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITS Drive Mapping","Training Developer","Resource allocation (invite Jeremy to kick off)","Commited",0,30,30,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITSM Training Videos","John Lowe","Project/Resource Allocation","Commited",0,80,80,true,"IT Service Management","Change Management Office","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ITSM Training Videos","Audrey O'Connell","Project/Resource Allocation","Commited",0,80,80,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Jacks Card - Alumni Card","Custom Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development",null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Jacks Card - Alumni Card","Custom Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development",null,"2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Jacks Path CC Advisor Partnership Fact Finding","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-01-01T17:00:00"]
["Jacks Path CC Advisor Partnership Fact Finding","EIS Full Stack Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-01-01T17:00:00"]
["Jacks Path CC Advisor Partnership Fact Finding","Kyle Hamilton Cawood","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-01-01T17:00:00"]
["Jacks Path Phase VI (Site Redesign UI)","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-07T08:00:00","2019-01-07T17:00:00"]
["Jacks Path Phase VI (Site Redesign UI)","EIS Programmer Student Worker","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-07T08:00:00","2019-01-07T17:00:00"]
["Jacks Path Phase VI (Site Redesign UI)","Kyle Hamilton Cawood","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-07T08:00:00","2019-01-07T17:00:00"]
["Key Audit OnBase Form","Krystina Marie Kraus-Soper","Project Allocation","Commited",0,8,8,true,"Business Services","Business Services.Employee Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Key Audit OnBase Form","Wesley Walker","Project Allocation","Commited",0,90,90,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Key Audit OnBase Form","Jed David Moss","Project Allocation","Commited",0,90,90,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lenel LDAP AD integrations","Identity and Access Analyst","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Lenel LDAP AD integrations","Identity and Access Analyst","Resource Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Lenel LDAP AD integrations","Systems Administrator (Linux/Unix)","Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Lifter LMS Module Conversion for LPD","Training Developer","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lifter LMS Module Conversion for LPD","Identity and Access Analyst","Resource Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Albert Raymond Sandoval","Resource Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Business Services","Business Services.Financial Services.Accountant","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Dan Stoffel","Resource Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Academic & Research Technology Services","Academic and Research Technology Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","James Peter Howington","Resource Allocation","Commited",0,80,80,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Don Carter","Resource Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Academic & Research Technology Services","Academic and Research Technology Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Trey McCallie","Resource Allocation","Commited",0,2.9999829999999998,2.9999829999999998,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Kathleen Ellis","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Laurel Logan","Resource Allocation","Commited",0,80,80,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Alec Matthew Harnden","Resource Allocation","Commited",0,45,45,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Jeff I Hillock","Resource Allocation","Commited",0,45,45,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Statewide.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Rob Moser","Resource Allocation","Commited",0,16,16,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Lynda com upgrade to LinkedIn Learning","Sarah H Lipsey","Resource Allocation","Commited",0,120,120,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["McConnell Sidewalk and Multi-Modal Improvement WiFi","David N Russell","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["McConnell Sidewalk and Multi-Modal Improvement WiFi","NOC Network Engineer","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","BA Russell","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support North.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","John Angelo Cencioso","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","Trey McCallie","Resource Allocation","Commited",0,18,18,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","Lisa P. Young","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","Cory Logan","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.ELC Tech Support.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","James Peter Howington","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Help Desk Support Services Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","Armand E Ramirez","Resource Allocation","Commited",0,30,30,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","Louis Arminio","Resource Allocation","Commited",0,30,30,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","Erin Kathleen Shelley","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all VPN access to Two-Step Verification","Audrey O'Connell","Resource Allocation","Commited",0,30,30,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all websites off of www5, www7, sourwood, possumhaw","Bryan G Loveless","Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all websites off of www5, www7, sourwood, possumhaw","EIS Full Stack Developer","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate all websites off of www5, www7, sourwood, possumhaw","Systems Administrator (Microsoft)","Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate and Replace GreenPC","Systems Administrator (Desktop Imaging)","Project Allocation (Quarter 4)","Commited",100,0,0,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-03-30T17:00:00","2019-03-30T17:00:00"]
["Migrate and Replace GreenPC","David W Starmer","Migrate from kiwi printers to papercut","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-02T08:00:00","2019-01-02T17:00:00"]
["Migrate and Replace GreenPC","Timothy William Cochran","Migrate group policy for printers","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-02T08:00:00","2019-01-02T17:00:00"]
["Migrate and Replace GreenPC","Federico Gallardo","Configure Isilon for roaming profiles share","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-02T08:00:00","2019-01-02T17:00:00"]
["Migrate Employee Email (IRIS) to Office 365 Exchange Online","Brett Austin West","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate Employee Email (IRIS) to Office 365 Exchange Online","Brian Velde","Project Allocation","Commited",0,240,240,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate Employee Email (IRIS) to Office 365 Exchange Online","Desktop Support End User Computer Specialist","Project Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate Employee Email (IRIS) to Office 365 Exchange Online","Help Desk Support Specialist","Project Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Help Desk Support Services Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate SharePoint to SharePoint Online","Brett Austin West","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Migrate SharePoint to SharePoint Online","Federico Gallardo","Project Allocation","Commited",0,100,100,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Mobile TMA release to all trades q4","Mark Alan Niles","Project Allocation","Proposed",100,0,10,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","NOC Network Engineer","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","John P Goral","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","Trey McCallie","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","NOC Network Engineer","Project Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","John P Goral","Project Allocation","Commited",0,39.999983,39.999983,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","Trey McCallie","Project Allocation","Commited",0,39.999983,39.999983,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","Jason D Robinson","EIS UI/UIX","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","Telecom Service Associate","Telecom","Commited",0,0.99998299999999996,0.99998299999999996,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Telecom Engineer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","Jason D Robinson","EIS UI/UIX","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Modo App Platform - Pilot for utilizing iBeacon and Geo Fencing technologies","Telecom Service Associate","Telecom","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Telecom Engineer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Mountain Line Bus Access","Jason D Robinson","Project Allocation","Proposed",100,0,20,true,"Enterprise Information Solutions","Enterprise Information Services.Design","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["Mountain Line Bus Access","Chris Graver","Project Allocation","Proposed",100,0,80,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["Mountain Line Bus Access","Vivek Bongu","Project Allocation","Proposed",100,0,80,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["Mountain Line Bus Access","Trevor A Luttinen","Project Allocation","Proposed",100,0,120,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["Moving websites, applications and databases to Bldg 54","John R Meyer","Project Allocation","Commited",0,60,60,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","James Slebodnick","Project Allocation","Commited",0,93,93,true,null,null,null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Federico Gallardo","Project Allocation","Commited",0,3,3,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Vivek Bongu","Project Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","David B Brink","Project Allocation","Commited",0,240,240,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Moving websites, applications and databases to Bldg 54","John R Meyer","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Dave Dennehey","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Core Systems Administrator (Microsoft)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services",null,"ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Moving websites, applications and databases to Bldg 54","John R Meyer","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Marc Alan Colvin","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Vivek Bongu","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Moving websites, applications and databases to Bldg 54","James Slebodnick","Project Allocation","Commited",0,80,80,true,null,null,null,"2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","David B Brink","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Vivek Bongu","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","John R Meyer","Project Allocation","Commited",0,80,80,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Federico Gallardo","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Marc Alan Colvin","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Moving websites, applications and databases to Bldg 54","Dave Dennehey","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["MPLS Building Cutover Phase 2","Armand E Ramirez","Project Allocation","Commited",0,120,120,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["MPLS Building Cutover Phase 2","NOC Network Engineer","IaaS NOC Manager Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["MPLS Building Cutover Phase 2","Armand E Ramirez","IaaS NOC Manager Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["MS Teams Adoption Roll-Out","Desktop Support End User Computer Specialist","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["MS Teams Adoption Roll-Out","EIS Full Stack Developer","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["MS Teams Adoption Roll-Out","Help Desk Support Specialist","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Help Desk Support Services Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["MS Teams Adoption Roll-Out","STC End User Computer Specialist","Resource Allocation","Commited",0,1,1,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["MS Teams Adoption Roll-Out","Systems Administrator (Academic and Research)","Resource Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["MS Teams Adoption Roll-Out","Systems Analyst","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["MS Teams Adoption Roll-Out","Training Developer","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["NAU IRIS Email Encryption","Systems Administrator (Microsoft)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["NAU IRIS Email Encryption","Steven W Andariese","ITS Resource Allocation","Commited",0,18.461532999999999,18.461532999999999,true,"Information Security Services","Information Security Services.Information Assurance.Identity Systems Analyst","ITS","2019-01-07T08:00:00","2019-03-29T17:00:00"]
["NAU IRIS Email Encryption","Robert P Lightner","ITS Resource Allocation","Commited",0,120,120,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems","ITS","2019-01-07T08:00:00","2019-03-29T17:00:00"]
["NAU IRIS Email Encryption","Audrey O'Connell","ITS Resource Allocation","Commited",0,60,60,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-01-07T08:00:00","2019-03-29T17:00:00"]
["NAU IRIS Email Encryption","Systems Administrator (Microsoft)","ITS Resource Allocation","Commited",0,60,60,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-07T08:00:00","2019-03-29T17:00:00"]
["NAU IRIS Email Encryption","Michael William Zimmer","ITS Resource Allocation","Commited",0,20,20,true,"Information Security Services","Information Security Services","ITS","2019-01-07T08:00:00","2019-03-29T17:00:00"]
["NAU Motorola Radio Project","Jacob Raymond Maxton","Project Allocation","Commited",100,0,30,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE",null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["NAU Police Department electronic quick reference guide Cheater Book q4","Mark Alan Niles","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["NAU Sun Corridor Network Fiber","NOC Network Engineer","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["NAU Sun Corridor Network Fiber","David N Russell","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["NAUPD Verizon Small Cell","Paul Merciano Trujillo","Project Allocation","Commited",0,250,250,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["NAUPD Verizon Small Cell","Jason T Ailiff","Project Allocation","Commited",0,250,250,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["NAUPD Verizon Small Cell","Paul Merciano Trujillo","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Telecom Engineer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["NAUPD Verizon Small Cell","Jason T Ailiff","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Net Price Calculator enhancements q4","Chris Graver","Project Allocation","Commited",0,4,4,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development","ITS","2019-04-01T08:00:00","2019-04-03T17:00:00"]
["New Employee Welcome Online Version","Training Developer","Project Allocation","Commited",0,120,120,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["New Employee Welcome Online Version","Lyric L Peate","Project Allocation","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["New Fuel Management System","Mark Alan Niles","Project Allocation","Proposed",0,24,24,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["New Fuel Management System","Jean Ann Adams","Project Allocation (official hours from Custom Dev)","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["New Fuel Management System","John P Goral","Project Allocation (official hours from Custom Dev)","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["NOA Enhancements","PeopleSoft Developer","Project Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["NSTAR ERE Refinements","Integration Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["OnBase for NAU Address Change approval process","Matthew Natividad Tafoya","Resource Allocation","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["OnBase for NAU Address Change approval process","Wesley Walker","Resource Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["OnBase LOA Phase Two","Talbert A Tso","Project Allocation","Commited",0,300,300,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["OnBase Mobile  Access","Wesley Walker","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["OnBase Qualified Life Event QLE Form","Travis Nathaniel Hudson","Project Allocation","Proposed",100,0,20,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["OnBase Qualified Life Event QLE Form","Travis Nathaniel Hudson","Project Allocation","Proposed",100,0,200,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["OnBase Qualified Life Event QLE Form","BPSM Student Worker","Project Allocation","Proposed",100,0,100,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.Student Employees","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["OnBase Security Request for ArcGIS Online","Kristin Michelle Brown","Project Allocation","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["OnBase Security Request for ArcGIS Online","Kristin Michelle Brown","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["OnBase Security Request for ArcGIS Online","Talbert A Tso","Project Allocation","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["On-boarding ITS communications","Jen Mason","Resource Allocation","Commited",0,1,1,true,"Business Services","Business Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["On-boarding ITS communications","Sarah H Lipsey","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Online Alumni Class Notes","Damien Michael Coy","Project Allocation","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-30T17:00:00"]
["Online Alumni Class Notes","Damien Michael Coy","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Online Alumni Class Notes","Amy J Fouts","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Online Alumni Class Notes","UI-UX Designer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Online Application Revision","John Wesley Hutchison","Project Allocation","Proposed",100,0,39.999983,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-06-03T17:00:00"]
["Online Application Revision","Cory D Holland","Project Allocation","Proposed",100,0,0.99998299999999996,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-01-01T08:00:00","2019-06-03T17:00:00"]
["Online Appointment Scheduler for Student Service Center","Kevin Labranche","Project Allocation","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Online Appointment Scheduler for Student Service Center","Trey Mason","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Online Appointment Scheduler for Student Service Center","Kevin Labranche","Project Allocation (Admin)","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Online Appointment Scheduler for Student Service Center","Trey Mason","Project allocation (front end)","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Online Undergraduate Application (Captcha Update)","John Wesley Hutchison","Project Allocation","Proposed",100,0,19.999983,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-02-28T17:00:00"]
["PaperCut print management version upgrade NG to MF","David W Starmer","Project Allocation","Commited",0,40,40,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Pay upload workflow","Vivek Bongu","Project Allocation","Commited",0,24,24,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Pay upload workflow","Kyle Hamilton Cawood","Project Allocation","Commited",0,50,50,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Jeremy D Anderson","Project Allocation","Commited",0,175,175,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Jason T Ailiff","Project Allocation","Commited",0,160,160,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Terrel Glenn Scambler","Project Allocation","Commited",0,30,30,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","David N Russell","Project Allocation","Commited",0,100,100,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Albert Raymond Sandoval","Project Allocation","Commited",0,30,30,true,"Business Services","Business Services.Financial Services.Accountant","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Jacob Raymond Maxton","Project Allocation","Commited",0,160,160,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant.TST",null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Paul Merciano Trujillo","Project Allocation","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Telecom Engineer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Leiann Morris","Project Allocation","Commited",0,160,160,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.TSC","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Brett Austin West","Project Allocation","Commited",0,30,30,true,"Infrastructure & Platform Services","Infrastructure and Platform Services","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","William Paul Martinchuk","Project Allocation","Commited",0,160,160,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant.TST","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Wendy E Garrison","Project Allocation","Commited",0,30,30,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Office Automation Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Lisa P. Young","Project Allocation","Commited",0,60,60,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Statewide.End User Computing Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PBX Conversion Completion","Sarah H Lipsey","Project Allocation","Commited",0,20,20,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PBX Conversion Completion","Jason T Ailiff","ATA Conversion INC0445389 Blue phones, emergency and analog phones","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["PBX Conversion Completion","Jeremy D Anderson","ATA Conversion INC0445389 Blue phones, emergency and analog phones","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["PBX Conversion Completion","Jeremy D Anderson","Remote Site SIP IQ with CenturyLink INC0445381","Commited",0,360,360,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-01-01T08:00:00","2019-03-04T17:00:00"]
["PBX Conversion Completion","David N Russell","Porting orders to CenturyLink for remote sites","Commited",0,112,112,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-03-05T08:00:00","2019-03-22T17:00:00"]
["PBX Conversion Completion","Jeremy D Anderson","Match ATA list with Laurie NAUPD (list of numbers and devices)","Commited",0,168,168,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-02-01T08:00:00","2019-03-01T17:00:00"]
["PBX Conversion Completion","Jeremy D Anderson","Phone Number Data Flow and Directory Information","Commited",0,352,352,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["PBX Conversion Completion","Robert P Lightner","Phone Number Data Flow and Directory Information","Commited",0,352,352,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["PBX Conversion Completion","Jason T Ailiff","remove unused pieces in the PBX","Commited",0,176,176,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-03-01T08:00:00","2019-03-31T17:00:00"]
["PBX Conversion Completion","Jason T Ailiff","Remove Astra 2 Pair digital lines","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Jeremy D Anderson","List people and phone numbers","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Jason T Ailiff","523 number setup standard message","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Wendy E Garrison","Solution Center Support","Commited",0,8,8,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Office Automation Specialist","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Robert P Lightner","List people and phone numbers","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Robert P Lightner","523 number setup standard message","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Jeremy D Anderson","Replace old phones with YeaLink phones","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Jeremy D Anderson","Setup new PIN on YeaLink phones for user","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Jason T Ailiff","27 Fax numbers routed Astra re-route to Skype","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Jason T Ailiff","Jason will build timeline schedule","Commited",0,40,40,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-03-11T08:00:00","2019-03-15T17:00:00"]
["PBX Conversion Completion","Robert P Lightner","SBC SIP TRUNK","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Jeremy D Anderson","Migration of Tuscon Site; This is the model for other sites","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Robert P Lightner","Migration of Tuscon Site; This is the model for other sites","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems","ITS","2019-03-11T08:00:00","2019-03-11T17:00:00"]
["PBX Conversion Completion","Brett Austin West","Fax Decommission","Commited",0,352,352,true,"Infrastructure & Platform Services","Infrastructure and Platform Services","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["PBX Conversion Completion","David N Russell","Fax Decommission","Commited",0,352,352,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["PBX Conversion Completion","Jason T Ailiff","Fax Decommission","Commited",0,352,352,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["PBX Conversion Completion","Sheri Ann Fetzer","Fax Decommission","Commited",0,352,352,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["PBX Conversion Completion","Leiann Morris","Fax Decommission","Commited",0,352,352,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations.TSC","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["PBX Conversion Completion","Sheri Ann Fetzer","Determine Fax Lines to Keep","Commited",0,312,312,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-01-01T08:00:00","2019-02-22T17:00:00"]
["PBX Conversion Completion","Wendy E Garrison","Verfity numbers that need to be converted prior to shutdown","Commited",0,16,16,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Office Automation Specialist","ITS","2019-03-13T08:00:00","2019-03-15T17:00:00"]
["PBX Conversion Completion","Sheri Ann Fetzer","Verfity numbers that need to be converted prior to shutdown","Commited",0,24,24,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-03-13T08:00:00","2019-03-15T17:00:00"]
["PBX Conversion Completion","Jason T Ailiff","Fax lines converted to CenturyLink dedicated analog line (23 of #)","Commited",80,104,520,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["PBX Conversion Completion","David N Russell","New Digital Fax Solution Pilot with Retarus and ITS Admin Office","Commited",50,16.533332999999999,33.333333000000003,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-02-01T08:00:00","2019-03-01T17:00:00"]
["PBX Conversion Completion","Sheri Ann Fetzer","New Digital Fax Solution Pilot with Retarus and ITS Admin Office","Commited",50,16.533332999999999,33.333333000000003,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-02-01T08:00:00","2019-03-01T17:00:00"]
["PeopleSoft 2019 ISIR Corrections Page q4","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Determine which components must be upgraded (Weblogic, Tuxedo, PeopleTools, Java)","Commited",100,0,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-14T08:00:00","2019-01-18T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Refresh demo ‘D1’ environment to retain one generation back","Commited",100,0,4,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-16T08:00:00","2019-01-18T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Apply security patch/upgrade components to Demo environment ‘DM’","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-16T08:00:00","2019-01-18T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Refresh demo ‘D0’ environment and upgrade components for Development and BA staff","Commited",100,0,4,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-16T08:00:00","2019-01-18T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Refresh DV level and upgrade components Apply patches/patchsets","Commited",100,0,6,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-21T08:00:00","2019-01-22T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Refresh QA level and upgrade components Apply patches/patchsets","Commited",100,0,6,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-23T08:00:00","2019-01-24T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Tools testing (varies from seamless cref navigation to full regression testing of tools)","Commited",100,0,6,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-25T08:00:00","2019-01-25T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Coordinate weekend event (touchnet, ESSP, DBA, 04 refresh for Catalog)","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-04T08:00:00","2019-02-08T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Apply security patch and upgrade components 7 app, 7 web, 1 batch, report repository","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-05T08:00:00","2019-02-08T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Apply security patch and upgrade components 7 app, 7 web, 1 batch, report repository","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-06T08:00:00","2019-02-08T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Refresh 8 additional CS test environments and upgrade components","Commited",100,0,18,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-07T08:00:00","2019-02-10T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","David E Chapman","Refresh 2 additional environments (FMS/HCM) to retain sync per SLA","Commited",100,0,18,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-07T08:00:00","2019-02-10T17:00:00"]
["PeopleSoft Campus Solutions Critical Security Updates 2019 Q3","Donna Bartlett","PSTECH Resource Allocation","Commited",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-14T08:00:00","2019-02-10T17:00:00"]
["PeopleSoft FISAP Critical Fix q4","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["Phase II - ITS Duplicate Management Portal","Mark Alan Niles","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Phase II - ITS Duplicate Management Portal","Vincent Messenger","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-30T17:00:00"]
["Phase II - ITS Duplicate Management Portal","EIS Full Stack Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-05-01T08:00:00","2019-06-30T17:00:00"]
["PL Administrative Tools Development","Joseph Flieger","Project Allocation","Proposed",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["PL Administrative Tools Development","Vivek Bongu","Project Allocation","Proposed",100,0,50,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["PL Administrative Tools Development","Marc Alan Colvin","Project Allocation","Proposed",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["PL Administrative Tools Development","Joseph Flieger","Project Allocation","Proposed",100,0,80,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-07-12T16:00:00"]
["PL Administrative Tools Development","Joseph Flieger","Unenroll tool (should be done this week)","Proposed",100,0,80,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["PL Dashboard Updates","Vivek Bongu","Resource allocation Q1","Commited",0,40,40,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-07-01T08:00:00","2019-07-31T17:00:00"]
["PL Dashboard Updates","Joseph Flieger","Transcript tracker","Commited",0,240,240,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-29T17:00:00"]
["PL Dashboard Updates","Joseph Flieger","Add option for students to self drop from their subscription in the first 10 days","Commited",0,0,0,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-01-01T08:00:00"]
["PL Dashboard Updates","Joseph Flieger","Add option for students to pre-enroll in month 5 of current subscription without impacting current subscription enrollment","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PL Dashboard Updates","Joseph Flieger","Add option for students to set their own start dates (will need to include FA question during selection.","Commited",0,0,0,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-01-01T08:00:00"]
["PL Dashboard Updates","Joseph Flieger","Add option for students to change their own set start date","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PL Dashboard Updates","Marc Alan Colvin","Tables, views and stored procedure updates","Commited",0,0,0,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-01-01T08:00:00","2019-01-01T08:00:00"]
["PL National Clearinghouse Data","David B Brink","Project Allocation","Proposed",100,0,120,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["PL Personalized Learning Curriculum Changes","Marc Alan Colvin","Project Allocation","Proposed",100,0,120,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-01-01T08:00:00","2019-02-28T17:00:00"]
["PL Updates","Troy Anthony Marino","Resource Allocation","Commited",0,60,60,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PL Updates","Vivek Bongu","Resource Allocation","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Placeholder Class Management q4","Kyle Hamilton Cawood","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["Planning Course Fees Redesign 2019","Kyle Hamilton Cawood","Project Allocation","Proposed",100,0,120,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Planning Course Fees Redesign 2019","Talbert A Tso","Project Allocation","Proposed",100,0,360,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Planning Course Fees Redesign 2019","Adele Sidney Pablo","Project Allocation","Proposed",100,0,120,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Planning Course Fees Redesign 2019","Marla J Johnet","Project Allocation","Proposed",100,0,120,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.Data Warehouse Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Prochnow Renovation","Devon Joseph Brookshire","Install switches","Commited",0,88,88,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-01-03T08:00:00","2019-01-17T17:00:00"]
["Prochnow Renovation","Matthew Charles Sells","Install switches","Commited",0,88,88,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-01-03T08:00:00","2019-01-17T17:00:00"]
["Prochnow Renovation","Stephen F Lomas","Install switches","Commited",0,88,88,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-01-03T08:00:00","2019-01-17T17:00:00"]
["Prochnow Renovation","Devon Joseph Brookshire","build wireless network","Commited",0,88,88,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-01-03T08:00:00","2019-01-17T17:00:00"]
["Prochnow Renovation","Stephen F Lomas","build wireless network","Commited",0,88,88,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-01-03T08:00:00","2019-01-17T17:00:00"]
["Prochnow Renovation","Matthew Charles Sells","documentation","Commited",0,168,168,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-02-05T08:00:00","2019-03-05T17:00:00"]
["Project Management Module ServiceNow Configurations Development","Wesley Walker","Project Allocation","Commited",0,260,260,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Project Management Module ServiceNow Configurations Development","William Joseph Creedon","Project Allocation","Commited",0,260,260,true,null,null,null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Project Management Module ServiceNow Configurations Development","Amy J Fouts","Project Allocation","Commited",0,20,20,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Project Management Module ServiceNow Configurations Development","Jed David Moss","Project Allocation","Commited",0,260,260,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Project Management Module ServiceNow Configurations Development","April Anne Cook","Project Allocation","Commited",0,50,50,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Project Management Module ServiceNow Configurations Development","Jed David Moss","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Project Management Module ServiceNow Configurations Development","April Anne Cook","Project Allocation","Commited",0,80,80,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Project Management Module ServiceNow Configurations Development","Amy J Fouts","Project Allocation","Commited",0,30,30,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","PeopleSoft Developer","Project Allocation","Commited",0,0.99995000000000001,0.99995000000000001,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Project Allocation","Commited",0,113.999983,113.999983,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Project Allocation","Commited",0,520,520,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Project Allocation","Commited",0,520,520,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Rusty Neeb","Project Allocation","Commited",0,520,520,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","James Moses","Project Allocation","Commited",0,520,520,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-27T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Project Allocation","Commited",0,114,114,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Project Allocation","Commited",0,520,520,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Project Allocation","Commited",0,520,520,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","Rusty Neeb","Project Allocation","Commited",0,520,520,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","James Moses","Project Allocation","Commited",0,520,520,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","Mark Alan Niles","Project Allocation","Commited",0,195,195,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kyle Hamilton Cawood","Project Allocation","Commited",0,40,40,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kathleen Ellis","Project Allocation","Commited",0,210,210,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","David D Bosse","Development","Commited",17,216,260,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Deb Stevens","Development","Commited",17,216,260,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","Development","Commited",17,432,520,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Fen Zheng","Development","Commited",17,432,520,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Leslie Mathews","Development","Commited",17,432,520,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Linda Krey Osthreim","Development","Commited",17,432,520,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Margaret Montfort","Development","Commited",17,432,520,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Mark Young","Development","Commited",17,216,260,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Morrinda Lynn Balenquah","Development","Commited",17,216,260,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paul Lambert","Development","Commited",17,432,520,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Data Warehouse Analyst","Analyze existing mods","Commited",75,49.5,198,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Analyze existing mods","Commited",75,99,396,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","Data Warehouse Analyst","Test and verify NAU mods in PS9206","Commited",25,75,100,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-04-01T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Test and verify NAU mods in PS9206","Commited",25,150,200,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-04-01T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Review configuration information","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Any required functional tasks in new production release","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","CMT Analyst","Go-Live","Commited",0,16,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","PeopleSoft Developer","Go-Live","Commited",0,16,16,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","Lisa A Doherty","Go-Live","Commited",0,16,16,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","Integration Analyst","Go-Live","Commited",0,8,8,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Apply PUM 14 to MP","Commited",0,16,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-08-02T08:00:00","2019-08-05T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Review configuration information","Commited",0,184,184,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Any required functional tasks in new production release","Commited",0,184,184,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,184,184,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92MP from PS92PR","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-22T08:00:00","2019-07-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92D0 from PS92DM","Commited",0,2,2,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-08-02T08:00:00","2019-08-02T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Copy (RMAN Dup) PS92DV to PS9201","Commited",0,4,4,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-08-05T08:00:00","2019-08-05T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92PT from PS92MP and Verify","Commited",0,2,2,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-08-05T08:00:00","2019-08-05T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92DV/QA/06/03 from PS92PT","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-08-06T08:00:00","2019-08-06T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PF91DT/QT and PH92DT/QT from same point in time as MP refresh","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-08-05T08:00:00","2019-08-06T17:00:00"]
["PS Campus Solutions 92 Upgrade","CMT Analyst","Remaining Envs for Go-Live PS9202,05","Commited",0,184,184,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Download any new Required for Upgrade Patch and Fixes","Commited",0,8,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-22T08:00:00","2019-07-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Complete Tools Upgrade","Commited",0,16,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-23T08:00:00","2019-07-24T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Complete Application Upgrade","Commited",0,16,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-25T08:00:00","2019-07-26T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Download and Apply PUM 14 PS92DM","Commited",0,24,24,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-30T08:00:00","2019-08-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PF91ST/PH92ST/PS90ST from Same Point in Time as MP Final Test Move","Commited",0,8,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-08-15T08:00:00","2019-08-15T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Apply PUM 13 and Tools Patch to MP","Commited",0,16,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-07-29T08:00:00","2019-07-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Migrate Security Super Project from PS92PT to PS92MP","Commited",0,8,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-08-02T08:00:00","2019-08-02T17:00:00"]
["PS Campus Solutions 92 Upgrade","James Moses","Migrate projects from PS92PT to PS92MP","Commited",0,8,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management","ITS","2019-08-02T08:00:00","2019-08-02T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92D1 from PS92DM","Commited",0,2,2,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-29T08:00:00","2019-07-29T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92ST from PS92PT (Backup of PT)","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-08-02T08:00:00","2019-08-02T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Point PF91ST/PH92ST to PS92ST","Commited",0,16,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-08-16T08:00:00","2019-08-19T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS9205 from PS92PT","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-08-16T08:00:00","2019-08-16T17:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","Import PS9005 queries to PS9205","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-08-16T08:00:00","2019-08-16T17:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","Drop Records in App Designer, not in DB","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-08-19T08:00:00","2019-08-19T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Subject Matter Expert","Analyze existing mods","Commited",75,99,396,true,"Non-IT Functional Office",null,"Functional","2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Analyze existing mods","Commited",75,49.5,198,true,"Non-IT Functional Office",null,"Functional","2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Subject Matter Expert","Analyze existing mods","Commited",75,49.5,198,true,"Non-IT Functional Office",null,"Functional","2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Analyze existing mods","Commited",75,29.7,118.8,true,"Non-IT Functional Office",null,"Functional","2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Subject Matter Expert","Analyze existing mods","Commited",75,29.7,118.8,true,"Non-IT Functional Office",null,"Functional","2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Analyze existing mods","Commited",75,9.9,39.6,true,"Non-IT Functional Office",null,"Functional","2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","Generic Local Resource","Analyze existing mods","Commited",75,9.9,39.6,true,null,null,null,"2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","Generic Local Resource","Analyze integration points between CS, HCM, FMS","Commited",75,198,792,true,null,null,null,"2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","Generic Local Resource","Analyze delivered functionality (new and existing)","Commited",75,198,792,true,null,null,null,"2019-03-11T08:00:00","2019-07-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Subject Matter Expert","Test and verify NAU mods in PS9206","Commited",25,150,200,true,"Non-IT Functional Office",null,"Functional","2019-04-01T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Test and verify NAU mods in PS9206","Commited",25,75,100,true,"Non-IT Functional Office",null,"Functional","2019-04-01T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Subject Matter Expert","Test and verify NAU mods in PS9206","Commited",25,75,100,true,"Non-IT Functional Office",null,"Functional","2019-04-01T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Test and verify NAU mods in PS9206","Commited",25,37.5,50,true,"Non-IT Functional Office",null,"Functional","2019-04-01T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Subject Matter Expert","Test and verify NAU mods in PS9206","Commited",25,37.5,50,true,"Non-IT Functional Office",null,"Functional","2019-04-01T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Test and verify NAU mods in PS9206","Commited",25,7.5,10,true,"Non-IT Functional Office",null,"Functional","2019-04-01T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Generic Local Resource","Test and verify NAU mods in PS9206","Commited",25,7.5,10,true,null,null,null,"2019-04-01T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Review configuration information","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Review configuration information","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Review configuration information","Commited",0,9.1999999999999993,9.1999999999999993,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","IRA Business Analyst","Review configuration information","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Registrar Business Analyst","Review configuration information","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Student Accounts Business Analyst","Review configuration information","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","VPAA Business Analyst","Review configuration information","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Any required functional tasks in new production release","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Any required functional tasks in new production release","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Any required functional tasks in new production release","Commited",0,9.1999999999999993,9.1999999999999993,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","IRA Business Analyst","Any required functional tasks in new production release","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Registrar Business Analyst","Any required functional tasks in new production release","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Student Accounts Business Analyst","Any required functional tasks in new production release","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","VPAA Business Analyst","Any required functional tasks in new production release","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,9.1999999999999993,9.1999999999999993,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","IRA Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Registrar Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Student Accounts Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","VPAA Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,18.399999999999999,18.399999999999999,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","VPAA Business Analyst","Go-Live","Commited",0,8,8,true,"Non-IT Functional Office",null,"Functional","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","Student Accounts Business Analyst","Go-Live","Commited",0,8,8,true,"Non-IT Functional Office",null,"Functional","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","Registrar Business Analyst","Go-Live","Commited",0,8,8,true,"Non-IT Functional Office",null,"Functional","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","IRA Business Analyst","Go-Live","Commited",0,8,8,true,"Non-IT Functional Office",null,"Functional","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Go-Live","Commited",0,1.6,1.6,true,"Non-IT Functional Office",null,"Functional","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Go-Live","Commited",0,1.6,1.6,true,"Non-IT Functional Office",null,"Functional","2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","Generic Local Resource","Go-Live","Commited",0,16,16,true,null,null,null,"2019-10-11T08:00:00","2019-10-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Review configuration information","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Review configuration information","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Review configuration information","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","IRA Business Analyst","Review configuration information","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Registrar Business Analyst","Review configuration information","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Student Accounts Business Analyst","Review configuration information","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","VPAA Business Analyst","Review configuration information","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Any required functional tasks in new production release","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Any required functional tasks in new production release","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Any required functional tasks in new production release","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","IRA Business Analyst","Any required functional tasks in new production release","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Registrar Business Analyst","Any required functional tasks in new production release","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Student Accounts Business Analyst","Any required functional tasks in new production release","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","VPAA Business Analyst","Any required functional tasks in new production release","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","IRA Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Registrar Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Student Accounts Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","VPAA Business Analyst","Review baseline statistics (row counts, totals, etc.)","Commited",0,184,184,true,"Non-IT Functional Office",null,"Functional","2019-08-21T08:00:00","2019-09-20T17:00:00"]
["PS Campus Solutions 92 Upgrade","Rebecca Lee Bates","Testing Disconnected HCM Environment","Commited",0,40,40,true,"Non-IT Functional Office",null,"Functional","2019-07-08T08:00:00","2019-07-18T17:00:00"]
["PS Campus Solutions 92 Upgrade","Carla Crone","Testing Disconnected HCM Environment","Commited",0,40,40,true,"Non-IT Functional Office",null,"Functional","2019-07-08T08:00:00","2019-07-18T17:00:00"]
["PS Campus Solutions 92 Upgrade","Data Warehouse Analyst","Analyze integration points between CS, HCM, FMS","Commited",0,0,0,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","Data Warehouse Analyst","Analyze delivered functionality (new and existing)","Commited",0,0,0,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Analyze integration points between CS, HCM, FMS","Commited",0,0,0,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Subject Matter Expert","Analyze integration points between CS, HCM, FMS","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Analyze integration points between CS, HCM, FMS","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Subject Matter Expert","Analyze integration points between CS, HCM, FMS","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Analyze integration points between CS, HCM, FMS","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Subject Matter Expert","Analyze integration points between CS, HCM, FMS","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Analyze integration points between CS, HCM, FMS","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Analyze delivered functionality (new and existing)","Commited",0,0,0,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Subject Matter Expert","Analyze delivered functionality (new and existing)","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Analyze delivered functionality (new and existing)","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Subject Matter Expert","Analyze delivered functionality (new and existing)","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Analyze delivered functionality (new and existing)","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Subject Matter Expert","Analyze delivered functionality (new and existing)","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Analyze delivered functionality (new and existing)","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-03-08T17:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","Financials Business Analyst","Sign off","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-09-20T08:00:00","2019-09-20T08:00:00"]
["PS Campus Solutions 92 Upgrade","GRAD Business Analyst","Sign off","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-09-20T08:00:00","2019-09-20T08:00:00"]
["PS Campus Solutions 92 Upgrade","HR Business Analyst","Sign off","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-09-20T08:00:00","2019-09-20T08:00:00"]
["PS Campus Solutions 92 Upgrade","Integration Analyst","Sign off","Commited",0,0,0,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-09-20T08:00:00","2019-09-20T08:00:00"]
["PS Campus Solutions 92 Upgrade","IRA Business Analyst","Sign off","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-09-20T08:00:00","2019-09-20T08:00:00"]
["PS Campus Solutions 92 Upgrade","Registrar Business Analyst","Sign off","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-09-20T08:00:00","2019-09-20T08:00:00"]
["PS Campus Solutions 92 Upgrade","Student Accounts Business Analyst","Sign off","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-09-20T08:00:00","2019-09-20T08:00:00"]
["PS Campus Solutions 92 Upgrade","VPAA Business Analyst","Sign off","Commited",0,0,0,true,"Non-IT Functional Office",null,"Functional","2019-09-20T08:00:00","2019-09-20T08:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","Verify PS92QA for Release","Commited",100,0,16,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-03-07T08:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","CMT Setup PS92DV/QA","Commited",100,0,80,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-18T08:00:00","2019-03-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","CMT Setup PS92PT","Commited",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-18T08:00:00","2019-03-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","CMT Setup PS9201","Commited",100,0,32,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-04T08:00:00","2019-04-09T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Apply PUM 13 and Tools to MP","Commited",100,0,32,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-05-07T08:00:00","2019-05-10T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Review steps and changes from Initial Pass","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-02T08:00:00","2019-01-02T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Download any new Required for Upgrade Patch and Fixes","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-02T08:00:00","2019-01-02T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Planning application upgrade","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-04T08:00:00","2019-01-04T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Prepare database for upgrade","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-07T08:00:00","2019-01-07T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Apply PeopleTools Changes","Commited",100,0,56,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-08T08:00:00","2019-01-16T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Complete Database Changes","Commited",100,0,56,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-17T08:00:00","2019-01-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Run and Review Compare Reports","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-28T08:00:00","2019-01-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Apply Application Changes","Commited",100,0,56,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-29T08:00:00","2019-02-06T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Perform Post Upgrade Actions","Commited",100,0,24,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-07T08:00:00","2019-02-11T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Prepare Job export with step timings,issues encountered, and workarounds developed","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-24T08:00:00","2019-02-24T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","CS 9.2 Setup of Phire for Migrations","Commited",100,0,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-05T08:00:00","2019-03-06T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Security Setup for Functional Users in PS92QA","Commited",100,0,32,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-01T08:00:00","2019-03-06T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Security setup for development access in PS92DV","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-28T08:00:00","2019-02-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Database Refresh of DV/QA after PUM 12 Install","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-02-27T08:00:00","2019-02-27T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Database Setup of PS92DV/QA","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-01-22T08:00:00","2019-01-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","DB Refresh of PS92PT from MP","Commited",100,0,64,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-03-04T08:00:00","2019-03-13T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","DB Setup of PF91DT/QT and PH92DT/QT","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-02-13T08:00:00","2019-02-13T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92MP from PS92PR","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-04-10T08:00:00","2019-04-10T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92D0 from PS92DM","Commited",100,0,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-05-07T08:00:00","2019-05-07T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Final PT Snap and PS9203/06 Refreshes","Commited",100,0,2,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-05-15T08:00:00","2019-05-15T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92PT from PS92MP","Commited",100,0,2,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-05-15T08:00:00","2019-05-15T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PF91DT/QT and PH92DT/QT from same point in time as MP refresh","Commited",100,0,2.6666669999999999,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-05-22T08:00:00","2019-05-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Security setup PT","Commited",100,0,24,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-12T08:00:00","2019-03-14T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Update Phire for PT migration","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","Clint William Gleason","VM Setup of PS92DV/QA","Commited",100,0,64,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-11T08:00:00","2019-01-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","Clint William Gleason","VM Setup of PS92PT","Commited",100,0,40,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-28T08:00:00","2019-03-06T17:00:00"]
["PS Campus Solutions 92 Upgrade","Clint William Gleason","VM Setup of PF91DT/QT and PH92DT/QT","Commited",100,0,24,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-13T08:00:00","2019-02-15T17:00:00"]
["PS Campus Solutions 92 Upgrade","EMSA Business Analyst","Sign off","Commited",0,0,0,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-09-20T08:00:00","2019-09-20T08:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Setup Elasticsearch","Commited",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-27T08:00:00","2019-03-05T17:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","Develop/Migrate TX/SC Mods Needed for Fit/Gap (CAS, Process Monitor Output, Dynrole, Sign on PeopleCode, Branding)","Commited",100,0,32,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-03-01T08:00:00","2019-03-06T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Setup Elasticsearch PT/06","Commited",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-22T08:00:00","2019-03-28T17:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","Migrate TX/SC Mods (CAS, Process Monitor Output, Dynrole, Sign on PeopleCode, Branding) PT/ST","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","Tracy Anne Locarni","Evaluate Impacted Items/Develop Test Plan","Commited",100,0,56,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-06-03T08:00:00","2019-06-11T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Verify PS92QA for Release","Commited",100,0,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-07T08:00:00","2019-03-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","SQL Update to PS92DV/QA (Change MP to DV/QA)","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-22T08:00:00","2019-01-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Verify MP for DV/QA Build","Commited",100,0,80,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-17T08:00:00","2019-01-30T17:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","Migrate TX/SC Mods to QA (Using Phire)","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-03-06T08:00:00","2019-03-06T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Download and Install PUM 12 into MP","Commited",100,0,48,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-19T08:00:00","2019-02-26T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Complete Tools Upgrade","Commited",100,0,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-11T08:00:00","2019-04-12T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Complete Application Upgrade","Commited",100,0,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-16T08:00:00","2019-04-17T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Download and Build PUM 13","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-05-01T08:00:00","2019-05-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Copy (RMAN Dup) PS92DV to PS9201","Commited",100,0,4,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-05-21T08:00:00","2019-05-21T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Setup Weekly 06 refresh from PT","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-03T08:00:00","2019-04-03T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Download any new Required for Upgrade Patch and Fixes","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-10T08:00:00","2019-04-10T17:00:00"]
["PS Campus Solutions 92 Upgrade","Rusty Neeb","Update setup PH92DT/PF91DT to integrate with PS92DV","Commited",100,0,280,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-19T08:00:00","2019-04-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","Rusty Neeb","Update setup PH92QA/PF91QA to integrate with PS92QA","Commited",100,0,280,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-02-19T08:00:00","2019-04-08T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Create DD PF91DT/PF91QT on yellow and PH92DT/PH92QT on denim","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-01-23T08:00:00","2019-01-23T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Create DB PS92DV, PS92QA, PS92ST, and PS9201","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-01-18T08:00:00","2019-01-18T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Create DB PS9206","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-03-22T08:00:00","2019-03-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Setup webfu scripts/files (html, prl, etc.)","Commited",100,0,24,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-19T08:00:00","2019-03-21T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Add link to index page","Commited",100,0,32,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-21T08:00:00","2019-03-26T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Update phire to handle webfu/mapping config changes","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-21T08:00:00","2019-03-21T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Verify webfu","Commited",100,0,0,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-03-27T17:00:00","2019-03-27T17:00:00"]
["PS Campus Solutions 92 Upgrade","Clint William Gleason","Apache Setup","Commited",100,0,40,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-03-11T08:00:00","2019-03-15T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Migrate TX/SC Mods (CAS, Process Monitor Output, Dynrole, Sign on PeopleCode, Branding) PT/ST","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","Leslie Mathews","Migrate TX/SC Mods (CAS, Process Monitor Output, Dynrole, Sign on PeopleCode, Branding) PT/ST","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-04-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","Rusty Neeb","CMT Setup of PS92ST","Commited",100,0,10,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-29T08:00:00","2019-04-30T10:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Change PS92ST to Clone and Refresh","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-04-09T08:00:00","2019-04-09T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92DV/QA from PS92PT","Commited",100,0,3,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-05-22T08:00:00","2019-05-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","Clint William Gleason","VM Setup of PS92ST","Commited",100,0,24,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-08T08:00:00","2019-04-10T17:00:00"]
["PS Campus Solutions 92 Upgrade","Rusty Neeb","CMT Setup of PS9203","Commited",100,0,16,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-12T08:00:00","2019-04-15T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Setup Daily Refresh of PS9203","Commited",100,0,2,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-18T08:00:00","2019-04-18T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Migrate Security Super Project from PS92PT to PS92MP","Commited",100,0,4,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-05-01T08:00:00","2019-05-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92D1 from PS92DM","Commited",100,0,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-04-12T08:00:00","2019-04-12T12:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","CMT Setup for Tools Patch - PS92PT","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-05-16T08:00:00","2019-05-16T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","PIA Setup of PS92D1","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-04-25T08:00:00","2019-04-25T17:00:00"]
["PS Campus Solutions 92 Upgrade","Paula Jean Aerts","Migrate projects from PS92PT to PS92MP","Commited",100,0,4,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-05-01T08:00:00","2019-05-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92ST from PS92PT (Backup of PT)","Commited",100,0,4,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-05-01T08:00:00","2019-05-01T17:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","Reapply Group B Super Project to PS92PT","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-05-17T08:00:00","2019-05-17T17:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","\"Hits\" Communication/CR Fail Back","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-05-22T08:00:00","2019-05-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","Donna Bartlett","Reapply QA projects to DV/QA","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-05-24T08:00:00","2019-05-24T17:00:00"]
["PS Campus Solutions 92 Upgrade","Leslie Mathews","Create PT Super Project (Group B - Everything migrated after 5/1)","Commited",100,0,2,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-05-15T08:00:00","2019-05-15T17:00:00"]
["PS Campus Solutions 92 Upgrade","James Moses","Create PT Super Project (Group B - Everything migrated after 5/1)","Commited",100,0,2,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management","ITS","2019-05-15T08:00:00","2019-05-15T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS9203/06 from PS92PT","Commited",100,0,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-05-24T08:00:00","2019-05-24T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Verify PS92PT","Commited",100,0,4,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-05-17T08:00:00","2019-05-17T17:00:00"]
["PS Campus Solutions 92 Upgrade","Rusty Neeb","Refresh PF91DT/QT and PH92DT/QT from same point in time as MP refresh","Commited",100,0,5.3333329999999997,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-05-22T08:00:00","2019-05-22T17:00:00"]
["PS Campus Solutions 92 Upgrade","James Moses","Reapply QA projects to DV/QA","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management","ITS","2019-05-24T08:00:00","2019-05-24T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Apply PUM 13 and Tools Patch to MP","Commited",100,0,24,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-06-19T08:00:00","2019-06-21T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Complete Application Upgrade","Commited",100,0,24,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-06-14T08:00:00","2019-06-18T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Complete Tools Upgrade","Commited",100,0,24,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-06-06T08:00:00","2019-06-10T17:00:00"]
["PS Campus Solutions 92 Upgrade","Kevin G Stoffers","Refresh PS92MP from PS92PR","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-06-05T08:00:00","2019-06-05T17:00:00"]
["PS Campus Solutions 92 Upgrade","David E Chapman","Download any new Required for Upgrade Patch and Fixes","Commited",100,0,8,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-06-05T08:00:00","2019-06-05T17:00:00"]
["Quarterly WordPress project","James Earl Shaeffer","Project Allocation","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Quarterly WordPress project","Rye Schnebly Heidinger","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.CMS and Web Support.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Quarterly WordPress project","Custom Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development",null,"2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Rebrand Trainings to match University Marketing standards","Ashlee Annabelle Binderim","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Recital Hall-Network Installation","Matthew Charles Sells","documentation","Commited",0,168,168,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-01-03T08:00:00","2019-01-31T17:00:00"]
["Release 5 of Salesforce Community","EIS Full Stack Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Release 5 of Salesforce Community","UI-UX Designer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Remove Social Security Number from Enrollment Verifications","David D Bosse","Project Allocation","Proposed",100,0,19.999983,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-05-22T17:00:00"]
["Replace Schedule of Classes PeopleSoft Modification","PeopleSoft Developer","Project Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Rimini Street RS19P02 Update q4","Donna Bartlett","Project Allocation","Proposed",100,0,19.999983,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-15T08:00:00","2019-05-05T17:00:00"]
["Rimini Street RS19P1 Tax Update","Rebecca Lee Bates","HR BA Resource Allocation","Commited",0,21,21,true,"Non-IT Functional Office",null,"Functional","2019-01-14T08:00:00","2019-01-31T17:00:00"]
["Rimini Street RS19P1 Tax Update","Donna Bartlett","ITS Resource Allocation PS TECH","Commited",0,12,12,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-14T08:00:00","2019-01-31T17:00:00"]
["Rimini Street RS19P1 Tax Update","Paula Jean Aerts","Refresh 4 environments (2 HCM, 1 CS, 1 FMS) to prepare for Rimini update","Commited",0,5,5,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-14T08:00:00","2019-01-18T17:00:00"]
["Rimini Street RS19P1 Tax Update","Paula Jean Aerts","Production install (varies from Data update to cobol recompile +)","Commited",0,2,2,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-31T15:00:00","2019-01-31T17:00:00"]
["Rimini Street RS19P1 Tax Update","Paula Jean Aerts","Migrate Development project with Rimini update to QA level for testing","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-21T08:00:00","2019-01-21T09:00:00"]
["Rimini Street RS19P1 Tax Update","Paula Jean Aerts","Download Rimini update and populate Development folder","Commited",0,4,4,true,"Enterprise Information Solutions","Enterprise Information Services.Quality Assurance/Change Management.ASA Programmer","ITS","2019-01-14T08:00:00","2019-01-18T17:00:00"]
["Rimini Tax Release RS19P03","PeopleSoft Developer","Project Allocation","Commited",0,10,10,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-08-05T17:00:00"]
["Roll out new wifi access system CISCO ISE","Devon Joseph Brookshire","Project Allocation","Commited",0,175,175,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Roll out new wifi access system CISCO ISE","David N Russell","Project Allocation","Commited",0,30,30,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Roll out new wifi access system CISCO ISE","Armand E Ramirez","Project Allocation","Commited",0,60,60,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Roll out new wifi access system CISCO ISE","Matthew Charles Sells","Project Allocation","Commited",0,60,60,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Roll out new wifi access system CISCO ISE","Sarah H Lipsey","Project Allocation","Commited",0,16,16,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Roll out new wifi access system CISCO ISE","Devon Joseph Brookshire","Project Allocation","Commited",0,100,100,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Roll out new wifi access system CISCO ISE","David N Russell","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Roll out new wifi access system CISCO ISE","Armand E Ramirez","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Roll out new wifi access system CISCO ISE","Matthew Charles Sells","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Salesforce Training Development and Scheduling","Andrea Stalker","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-09-30T08:00:00","2019-09-30T09:00:00"]
["Salesforce Training Development and Scheduling","April Anne Cook","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-09-30T08:00:00","2019-09-30T09:00:00"]
["Salesforce Waterfall Logic fix q4","CRM Administrator","Project Allocation","Commited",0,75,75,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-10-01T08:00:00","2019-12-31T17:00:00"]
["Salesforce Waterfall Logic fix q4","Integration Analyst","Project Allocation","Commited",0,90,90,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-10-01T08:00:00","2019-12-31T17:00:00"]
["SAP Modification","BPSM Applications Systems Analyst","Project Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SAP Modification","PeopleSoft Developer","Project Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SAP Modification","Jed David Moss","Project Allocation","Commited",0,240,240,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-01-01T08:00:00","2019-02-28T17:00:00"]
["SAP Modification","Jordan Christopher Jones","Project Allocation","Commited",0,1,1,true,"Non-IT Functional Office","Enrollment Management Services and Admissions.BA","Functional","2019-01-01T08:00:00","2019-02-28T17:00:00"]
["SAP Modification","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-01-01T08:00:00","2019-02-28T17:00:00"]
["SAP Modification","April Anne Cook","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-01-01T08:00:00","2019-02-28T17:00:00"]
["SAP Modification","Generic Local Resource","","Commited",0,240,240,true,null,null,null,"2019-01-01T08:00:00","2019-02-28T17:00:00"]
["Security upddates for api nau edu applications area","Syed Ahsan Imam","Project Allocation","Commited",0,173,173,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Server configuration baseline images and monitoring","Daniel Wallace","Resource Allocation","Commited",0,13,13,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","Federico Gallardo","Resource Allocation","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","Clint William Gleason","Resource Allocation","Commited",0,18,18,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","Clinton Wayne Baker","Resource Allocation","Commited",0,38,38,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","Keith Lyle Ballou","Resource Allocation","Commited",0,38,38,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","Peter Lindsay Gomersall","Resource Allocation","Commited",0,38,38,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","Shane Kenneth Tsosie","Resource Allocation","Commited",0,38,38,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","Stacey Brewer","Resource Allocation","Commited",0,38,38,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","William Edward Wilson","Resource Allocation","Commited",0,38,38,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","Kenneth Thomas Sager","Resource Allocation","Commited",0,25,25,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","Christopher Benjamin Coffey","Resource Allocation","Commited",0,38,38,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Server configuration baseline images and monitoring","James C Davis","Resource Allocation","Commited",0,25,25,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","BA Russell","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support North.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Michael Ahkeah","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support North.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Brian J Hall","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support North.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Steven Leon DeRonge","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support North.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Tori Todachine","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support North.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","John Angelo Cencioso","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","John D Artus","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Richard F Ayres","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Emerson E Cleveland","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Alec Matthew Harnden","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Jean Aston","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Jason Buechler","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","George D Larson","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Sean Vance","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Ke-Sheng Bao","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Shawn Micheal Schwickerath","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Daniel J Waisley","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","James Howard Crane","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Lisa P. Young","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Statewide.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Brandy Gilles","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Statewide.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Jeff I Hillock","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Statewide.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Francisco A Valenzuela","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Statewide.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Wendy E Garrison","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Office Automation Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","James Peter Howington","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Help Desk Support Services Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Julie McCormick","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Office Automation Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Angie Begay","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Help Desk Support Services Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Cory Levi Wiegersma","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Help Desk Support Services Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Erin Kathleen Shelley","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.ELC Tech Support.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Anna Beth Corbett","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.ELC Tech Support.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Laurel Logan","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Luke August Mulligan","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Rocky M Steinmetz","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Caleb Hudzinski","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","German A Fermin","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Megan Elizabeth Wagar","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.TO","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Service Desk & Technology Support Services Operational Work","Cory Logan","Resource Allocation","Commited",0,422,422,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["ServiceNow Q4 Updates Bundle (ITSM)","Jed David Moss","Project Allocation","Commited",100,0,240,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SOC and IAM Operational Work","Jonathan Andrew Wince","Operational work","Commited",0,23.6,23.6,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SOC and IAM Operational Work","Raymond Drew Walker","Operational work","Commited",0,468,468,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SOC and IAM Operational Work","Erin Lindsey Plese","Operational work","Commited",0,1,1,true,"Information Security Services","Information Security Services.Information Assurance","Functional","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SOC and IAM Operational Work","Michael William Zimmer","Operational work","Commited",0,1,1,true,"Information Security Services","Information Security Services","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SOC and IAM Operational Work","Trey McCallie","Operational work","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Amy J Fouts","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Andrea Stalker","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","April Anne Cook","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Ashlee Annabelle Binderim","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Audrey O'Connell","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Colinda Hardy Joe","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Jared Logan","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst",null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Jeremy Sanderlin","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Kathleen Ellis","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Kyle Hamilton Cawood","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Mark Alan Niles","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Sarah H Lipsey","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","Sheri Ann Fetzer","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SPIES Operational work","William Daniel Hurley","Project Allocation","Commited",0,1,1,true,null,null,null,"2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Splunk forwarder installations on all Academic and Enterprise systems","Daniel Wallace","Project Allocation","Proposed",0,40,40,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Splunk forwarder installations on all Academic and Enterprise systems","Bryan G Loveless","Project Allocation","Commited",0,10,10,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Splunk forwarder installations on all Academic and Enterprise systems","Clint William Gleason","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Splunk forwarder installations on all Academic and Enterprise systems","Systems Administrator (Academic and Research)","Resource Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Splunk forwarder installations on all Academic and Enterprise systems","Systems Administrator (Linux/Unix)","Resource Allocation","Proposed",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Splunk forwarder installations on all Academic and Enterprise systems","Daniel Wallace","Resource Allocation","Proposed",0,1,1,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Spreadsheet Voucher Load","PeopleSoft Developer","Project Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["SSO for NAUgo","Dina Ann Barnese","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["SSO for NAUgo","Patricia Helene Allenbaugh","Project Allocation","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["SSO for NAUgo","Raymond Drew Walker","Project Allocation","Commited",0,15,15,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["SSO for NAUgo","Jason D Robinson","Project Allocation","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Design.Web Developer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["SSO for NAUgo","Chris Graver","Project Allocation","Commited",0,10,10,true,"Enterprise Information Solutions","Enterprise Information Services.Applications Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Staff Listings reports in Business Objects","Adele Sidney Pablo","Project Allocation","Proposed",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["Staff Listings reports in Business Objects","Lynn Burch","Project Allocation","Proposed",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["Staff Listings reports in Business Objects","Marla J Johnet","Project Allocation","Proposed",100,0,40,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.Data Warehouse Analyst","ITS","2019-01-01T08:00:00","2019-03-01T17:00:00"]
["Staff Listings reports in Business Objects","Adele Sidney Pablo","Project Allocation","Proposed",100,0,10,true,"Enterprise Information Solutions","Enterprise Information Services.Enterprise Analytics and Reporting.Data Warehouse Analyst","ITS","2019-04-01T08:00:00","2019-04-30T17:00:00"]
["Staff Listings reports in Business Objects","Marla J Johnet","Project Allocation","Proposed",100,0,10,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.Data Warehouse Analyst","ITS","2019-04-01T08:00:00","2019-04-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Kathleen Ellis","Resource Allocation","Commited",0,166,166,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Kyle Hamilton Cawood","Resource Allocation","Commited",0,166,166,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Mark Alan Niles","Resource Allocation","Commited",0,213,213,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Jared I Logan","Resource Allocation","Commited",0,148,148,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Colinda Hardy Joe","Resource Allocation","Commited",0,412,412,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Amy J Fouts","Resource Allocation","Commited",0,148,148,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","April Anne Cook","Resource Allocation","Commited",0,148,148,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Sarah H Lipsey","Resource Allocation","Commited",0,136,136,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Ashlee Annabelle Binderim","Resource Allocation","Commited",0,148,148,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Audrey O'Connell","Resource Allocation","Commited",0,148,148,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Andrea Stalker","Director","Commited",0,148,148,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Jeremy Sanderlin","Association Director","Commited",0,148,148,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Amy J Fouts","Vacation","Commited",0,40,40,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-08-19T08:00:00","2019-08-23T17:00:00"]
["Strategic Planning, Implementation, & Educational Services  Operational Work","Kathleen Ellis","Vacation","Commited",0,80,80,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis","ITS","2019-07-25T08:00:00","2019-08-07T17:00:00"]
["Thin Client Replacement","John Angelo Cencioso","Resource Allocation","Commited",0,100,100,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Thin Client Replacement","BA Russell","Resource Allocation","Commited",0,100,100,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support North.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Thin Client Replacement","Tobias J Kreidl","Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Thin Client Replacement","Kegan Elliott Remington","Resource Allocation","Commited",0,10,10,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Thin Client Replacement","Lisa P. Young","Resource Allocation","Commited",0,100,100,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Thin Client Replacement","Keith Lyle Ballou","Resource Allocation","Commited",0,10,10,true,"Academic & Research Technology Services","Academic and Research Technology Services.Academic and Research Systems Administration.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["TMA Payroll Reconciliation Automation","PeopleSoft Developer","Resource Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Traditional, Accelerated and CEP Nursing Program online applications","Jean Ann Adams","Resource Allocation","Commited",0,120,120,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Traditional, Accelerated and CEP Nursing Program online applications","Vivek Bongu","Resource Allocation","Commited",0,20,20,true,"Enterprise Information Solutions","Enterprise Information Services.Architecture.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Transcript Processing Improvements within OnBase","BPSM Applications Systems Analyst","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Transcript Processing Improvements within OnBase","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Transfer Credit Articulation Rule Evaluation Tracking","BPSM Applications Systems Analyst","Project Allocation","Commited",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Transfer Credit Articulation Rule Evaluation Tracking","PeopleSoft Developer","Project Allocation","Proposed",0,528,528,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Transfer Credit Articulation Rule Evaluation Tracking","Generic Local Resource","","Commited",0,520,520,true,null,null,null,"2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Transition Blackboard Learn to Ultra Base Navigation","Edward J Smith","Project Allocation","Proposed",0,132.57575800000001,132.57575800000001,true,"Academic & Research Technology Services","Academic and Research Technology Services.ASA Programmer","ITS","2019-04-01T08:00:00","2019-05-17T17:00:00"]
["Transition Blackboard Learn to Ultra Base Navigation","Dan Stoffel","Project Allocation","Proposed",0,95.454544999999996,95.454544999999996,true,"Academic & Research Technology Services","Academic and Research Technology Services","ITS","2019-04-01T08:00:00","2019-05-17T17:00:00"]
["Transition to using private IP networks to improve security posture- Phase I","Daniel Wallace","Resource Allocation","Commited",0,13,13,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Transition to using private IP networks to improve security posture- Phase I","James C Davis","Resource Allocation","Commited",0,25,25,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Transition to using private IP networks to improve security posture- Phase I","Kegan Elliott Remington","Resource Allocation","Commited",0,1,1,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Transition to using private IP networks to improve security posture- Phase I","NOC Network Engineer","Resource allocation (TBD from Kim)","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Two Step Verification for OWA","Trey McCallie","Resource Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Two Step Verification for OWA","Audrey O'Connell","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Two Step Verification for OWA","Raymond Drew Walker","ITS Resource Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Two Step Verification for OWA","Jonathan Andrew Wince","ITS Resource Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Two Step Verification for OWA","Robert P Lightner","ITS Resource Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Two-Step Phase IV - CAS upgrade, advanced rules, wider rollout","Jonathan Andrew Wince","Project Allocation","Proposed",100,0,39.999983,true,"Information Security Services","Information Security Services.Identity and Access Management.Identity Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Two-Step Phase IV - CAS upgrade, advanced rules, wider rollout","Raymond Drew Walker","Project Allocation","Proposed",100,0,179.99998299999999,true,"Information Security Services","Information Security Services.Identity and Access Management.SSE","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Two-Step Phase IV - CAS upgrade, advanced rules, wider rollout","Trey McCallie","Project Allocation","Proposed",100,0,34.999983,true,"Information Security Services","Information Security Services.Identity and Access Management","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Two-Step Phase IV - CAS upgrade, advanced rules, wider rollout","John P Goral","Project Allocation","Proposed",100,0,39.999983,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Unified Communications Support Model Transition","Jared I Logan","Project Allocation","Commited",0,25,25,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Unified Communications Support Model Transition","Laurel Logan","Project Allocation","Commited",0,32,32,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Student Technology Center.End User Computing Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Unified Communications Support Model Transition","Brett Austin West","Project Allocation","Commited",0,30,30,true,"Infrastructure & Platform Services","Infrastructure and Platform Services","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Unified Communications Support Model Transition","Jason T Ailiff","Project Allocation","Commited",0,70,70,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Outside Plant","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Unified Communications Support Model Transition","Jeremy D Anderson","Project Allocation","Commited",0,70,70,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.TSC","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Unified Communications Support Model Transition","Wendy E Garrison","Project Allocation","Commited",0,32,32,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Solution Center.Office Automation Specialist","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Unified Communications Support Model Transition","Robert Scott Brubaker","Project Allocation","Commited",0,65,65,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Unified Communications Support Model Transition","Terrel Glenn Scambler","Project Allocation","Commited",0,70,70,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Unified Communications Support Model Transition","Terrel Glenn Scambler","Project Allocation","Commited",0,100,100,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Computer Operations","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Update SF PEP Informatica script for Yuma Title II","Allie Alterio","Project Allocation","Commited",0,70,70,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-09-30T08:00:00","2019-10-10T15:00:00"]
["Update SF PEP Informatica script for Yuma Title II","Allie Alterio","Project Allocation","Commited",0,80,80,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-12-30T08:00:00","2020-01-10T17:00:00"]
["Update SF PEP Informatica script for Yuma Title II","CRM Administrator","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-12-30T08:00:00","2019-12-30T09:00:00"]
["Upgrade BizTalk servers and the Biztalk application","Systems Administrator (Microsoft)","Project Allocation","Commited",0,0.99998299999999996,0.99998299999999996,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Upgrade BizTalk servers and the Biztalk application","Mark Timothy Staten","Project Allocation","Commited",0,30,30,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Upgrade or decomission Coldfusion www6","Custom Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development",null,"2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Veteran Enrollment Certification Enhancement q4","PeopleSoft Developer","Project Allocation","Commited",0,1,1,true,"Enterprise Information Solutions","Enterprise Information Services.PeopleSoft Technology and Development.ASA Programmer","ITS","2019-04-01T08:00:00","2019-06-30T17:00:00"]
["Veterans DODTA electronic form","Mark Timothy Staten","Project Allocation","Commited",0,300,300,true,"Enterprise Information Solutions","Enterprise Information Services.Business Process and Service Management.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Video Conferencing technology and training improvements for classrooms","Nate See","Project Allocation","Commited",0,30,30,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Video Conferencing technology and training improvements for classrooms","Audrey O'Connell","Project Allocation","Commited",0,90,90,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Video Conferencing technology and training improvements for classrooms","Ashlee Annabelle Binderim","Project Allocation","Commited",0,15,15,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Video Conferencing technology and training improvements for classrooms","Kegan Elliott Remington","Project Allocation","Commited",0,30,30,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support.End User Computer Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["View only access requested for data integration mappings","Kevin Michael Hayes","Project Allocation","Commited",0,100,100,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["View only access requested for data integration mappings","Marla J Johnet","Project Allocation","Commited",0,100,100,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.Data Warehouse Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["View only access requested for data integration mappings","Sam R Stroud","Project Allocation","Commited",0,100,100,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["View only access requested for data integration mappings","James Slebodnick","Project Allocation","Commited",0,6,6,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["View only access requested for data integration mappings","Allie Alterio","Project Allocation","Commited",0,100,100,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.Integration/Migration.ASA Programmer","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Waiver of Recruitment Request Form Digitization","ITS Business Analyst","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-10-01T08:00:00","2019-12-31T17:00:00"]
["Web Application Firewall Implementation","Systems Administrator (Linux/Unix)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Web Application Firewall Implementation","Kenneth Thomas Sager","Project Allocation","Commited",0,1,1,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["WiFi Core Upgrade Phase 2 Increase Capacity for ResNet","Devon Joseph Brookshire","Project Allocation","Commited",0,120,120,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network.Network Operations Center.NSE","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["WiFi Core Upgrade Phase 2 Increase Capacity for ResNet","David N Russell","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Network","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","James C Davis","Resource Allocation","Commited",0,25,25,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","James C Davis","Resource Allocation","Commited",0,8,8,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2020-01-01T08:00:00","2020-01-20T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Kenneth Thomas Sager","Resource Allocation","Commited",0,19,19,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-10-01T08:00:00","2019-12-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Kenneth Thomas Sager","Resource Allocation","Commited",0,6,6,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2020-01-01T08:00:00","2020-01-20T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Daniel Wallace","Resource Allocation","Commited",0,15,15,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-10-01T08:00:00","2019-12-31T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Daniel Wallace","Resource Allocation","Commited",0,5,5,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2020-01-01T08:00:00","2020-01-20T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Kenneth Thomas Sager","Resource Allocation","Commited",0,19,19,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Daniel Wallace","Resource Allocation","Commited",0,15,15,true,"Information Security Services","Information Security Services.Security Operations Center","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","John Angelo Cencioso","Resource Allocation","Commited",0,150,150,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support South.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","BA Russell","Resource Allocation","Commited",0,150,150,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support North.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Michael William Zimmer","Resource Allocation","Commited",0,30,30,true,"Information Security Services","Information Security Services","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Kegan Elliott Remington","Resource Allocation","Commited",0,10,10,true,"Academic & Research Technology Services","Academic and Research Technology Services.Campus Classroom Support","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Lisa P. Young","Resource Allocation","Commited",0,150,150,true,"Service Desk & Technology Support Services","Service Desk and Technical Support Services.Desktop Support Central.End User Computing Specialist","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","James C Davis","Resource Allocation","Commited",0,25,25,true,"Information Security Services","Information Security Services.Security Operations Center.Information Security Analyst","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Timothy William Cochran","Resource Allocation","Commited",0,66,66,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows 7 End of Life, EOL, January 2020","Project Manager","Resource Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Project Management.Project Manager","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Setup New WSUS Server (Blackthorn.ucc.nau.edu)","Commited",0,160,160,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-18T08:00:00","2019-03-15T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Project Kickoff Meeting","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-04-09T08:00:00","2019-04-09T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Granted Access to new WSUS VM on Hyper Converged Cluster (INC0507247)","Commited",100,0,88,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-22T08:00:00","2019-02-05T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Granted Access to new Storage location on Isilon","Commited",100,0,88,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-22T08:00:00","2019-02-05T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Configured All Firewall rules for the addition of the WSUS Server (INC0507325)","Commited",100,0,88,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-04T08:00:00","2019-02-18T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Install WSUS Roles and Generate Certificates","Commited",100,0,160,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-18T08:00:00","2019-03-15T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Integrate Blackthorn as an SCCM Site Server and Update Point","Commited",100,0,160,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-18T08:00:00","2019-03-15T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Successfully Sync Updates from Microsoft to SCCM","Commited",100,0,160,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-18T08:00:00","2019-03-15T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Kristopher R Bullins","Create a DEV GPO for workstations to get updates from SCCM","Commited",100,0,160,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-18T08:00:00","2019-03-15T17:00:00"]
["Windows Server update Service (WSUS) and Service Center Configuration Manager (SCCM) Integration","Thomas Ashton Hahnke","Setup Third Party Software Integrations with Dell","Commited",100,0,56,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-03-22T08:00:00","2019-04-01T17:00:00"]
["WordPress Enterpise Plus theme training","Sarah H Lipsey","Resource Allocation","Commited",0,40,40,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Learning & Professional Development.IS TS","ITS","2019-07-01T08:00:00","2019-09-30T17:00:00"]
["Work Order System TMA Major Support","Database Administrator","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Platform Services.DBA","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Work Order System TMA Major Support","Mark Alan Niles","Project Allocation","Commited",0,1,1,true,"Strategic Planning_Implementation_& Educational Services","Strategic Planning/Implementation and Education Services.Systems Analysis.Systems Analyst","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Work Order System TMA Major Support","Systems Administrator (Microsoft)","Project Allocation","Commited",0,1,1,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-01T08:00:00","2019-03-31T17:00:00"]
["Workshops on Wellness Conference Registration","John P Goral","Resource Allocation","Proposed",100,0,10,true,"Enterprise Information Solutions","Enterprise Information Services.Systems Development.ASA Programmer","ITS","2019-05-16T08:00:00","2019-07-12T17:00:00"]
["Workshops on Wellness Conference Registration","Holly S Coast","Resource allocation (eBiz configuration)","Proposed",100,0,3,true,"Enterprise Information Solutions","Enterprise Information Services.Data Integration/Migration & CRM.CRM.Web Developer","ITS","2019-05-16T08:00:00","2019-07-12T17:00:00"]
["XenApp and GPU Based Application Delivery for Specific Apps","Tobias J Kreidl","NetScaler Gateway configuration","Commited",100,0,8,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-20T08:00:00","2019-01-20T17:00:00"]
["XenApp and GPU Based Application Delivery for Specific Apps","Timothy William Cochran","Create splash page","Commited",100,0,6,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-02-18T08:00:00","2019-03-07T17:00:00"]
["XenApp and GPU Based Application Delivery for Specific Apps","Timothy William Cochran","Incorporate into apps.nau.edu website/release to production (plan is to release to PR friday after 5:00)","Commited",100,0,24,true,"Infrastructure & Platform Services","Infrastructure and Platform Services.Core Systems.Systems Administrator","ITS","2019-01-02T08:00:00","2019-01-04T17:00:00"]

{"sheet":"Drop Down Menu","index":3,"n_rows":12,"n_cols":16,"rows_kept":12,"cut":false,"hidden":true,"merged":[]}
["Health Status",null,null,"Delay reasons",null,null,null,null,"ITS Leadership ",null,null,"ITS Project Type",null,null,null,"Work needed"]
["On Track",null,null,"Always Intended to be Multi Quarter",null,null,null,null,"Albert Sandoval",null,null,"Cross-Departmental",null,null,null,"Approved"]
["Under Control",null,null,"Business resource constraint",null,null,null,null,"Brett West",null,null,"Single Team/Dept",null,null,null,"Approval Needed"]
["Bumpy",null,null,"IT resource constraint",null,null,null,null,"Celisa Manly",null,null,"Cross-Divisional"]
["Trouble Ahead",null,null,"Original scope larger than anticipated",null,null,null,null,"Marc Lord",null,null,"Cross Dept/Cross-Div Impact"]
["Imminent Failure",null,null,"Scope change",null,null,null,null,"Michael Zimmer"]
["Cancelled",null,null,"Depriortized due with respect to another project",null,null,null,null,"Andrea Stalker"]
["Completed",null,null,"Dependent on another project",null,null,null,null,"Don Carter"]
["DO NOT TRACK HEALTH STATUS",null,null,"External Interrupt (i.e. Vendor)"]
["On Hold",null,null,"Funding constraint"]
[null,null,null,"Closing early next quarter due to logistics"]
[null,null,null,"Other"]

{"sheet":"Code","index":4,"n_rows":23,"n_cols":1,"rows_kept":23,"cut":false,"hidden":true,"merged":[]}
[]
["Additionally, it is totally interactive! By double clicking on the Project Name column in the Gantt chart sheet, the workbook will automatically take you to the resources sheet and automatically filter by the cell value you double clicked on, showing all the assignments/resources for that project."]
[]
["(This does mean that double clicking a cell in column b will not allow you to edit it, but you can just use the formula bar at the top or press f2 to edit it. )"]
[]
["Let me know if anything needs changing before I upload it to the PWA site."]
[]
["Thanks,"]
[]
["ShayAlice Aradia"]
[]
["Slight update to the code, so that you still CAN double click to enter cell edit mode if you’re not selecting something in column B where the project names are stored."]
["New Code:"]
[]
["Private Sub Worksheet_BeforeDoubleClick(ByVal Target As Range, Cancel As Boolean)"]
["  "]
["    If ActiveCell.Column = 2 Then"]
["    'Replace \"Sheet3\" with the Sheet number of the relevant sheet'"]
["     Cancel = True"]
["     Sheet3.ListObjects(\"Assignments\").Range.AutoFilter Field:=1, Criteria1:=ActiveCell.Value"]
["    Sheet3.Activate"]
["End If"]
["End Sub"]