## Slide 1: WordPress Unit Web Coordinators
Monthly Summit – August 2018

## Slide 2
“There was a time when nails were high-tech. There was a time when people had to be told how to use a telephone. Technology is just a tool. People use tools to improve their lives.” – Tom Clancy

## Slide 3: Agenda
Recent site launches
Theme enhancements
Training update
Mass migration status
Q&A

## Slide 4: Recent site launches
ITS - Louie July 3rd
COE - Educational Leadership July 12th
COE - Educational Psychology July 12th
COE - Educational Specialties July 12th
COE - Teaching & Learning July 12th
SBS - General July 26th
CHHS/SBS – IDH PhD July 26th
CHHS - School of Nursing July 30th
Advancement – Giving August 2nd
EMSA – Academic Success Centers August 2nd
EMSA – Campus Dining August 2nd
EMSA – Career Development August 2nd
EMSA – General August 2nd
EMSA – Upward Bound August 2nd
EMSA – Student Service Center August 2nd
President – Disability Resources August 2nd
SBS – IHD August 2nd
This brings us to 50+ live sites in WordPress!

## Slide 5: Theme enhancements
Three Enterprise theme update releases in July:
  New Publication Tools: Media Replace and Toolbar Publish
  NAU Core Updates
  Styling updates to Directory and Events
  Bug fixes, updates, accessibility & functional improvements
We continue to average two Enterprise themes and one Marketing theme push a month
More updates, features, and enhancements are coming!

## Slide 6: Training update
In person trainings have been ongoing and well received
  Since June of 2017, over 320 people were trained
Upcoming opportunities
Pivot to online and self guided training
Continue to reference nau.edu/web for more training and WordPress information
Online training demo

## Slide 7: Mass migration status
The August 1st deadline has slipped to later in the month for initial site launches
74 sites have been migrated by WordHerd, 65 have had initial QA and menu work complete
  Remaining site batches are being processed and should be complete by end of next week
Work continues to plan the site launches and turnover to stewards
Site Steward work can continue with DIY sites currently in staging
SiteImprove groups are currently being built for UWC and Site Stewards
  Initial reports created and site monitoring baseline established
  Additional tweaks to monitoring and test run with an initial user group will occur in the next two weeks

## Slide 8
Thank you for the continued support and involvement to deliver a high-quality OneNAU website!
Questions?