## FY23 Process Timeline
FY24 Budget Process Timeline
DUE DATES | TASKS
March 8th | UBO Kickoff to communicate position, Local and State Budget process guidelines for FY24
March 8th | Anaplan OPEN for entry (Position, Local and State Templates available)
March20th | Position review and changes finalized for Budget Office review
April 3rd | Local DeptIDs without UCA funding templates to be completed in Anaplan
April 17th | Local DeptIDs with UCA funding and State budget templates completed in Anaplan
April 18th | Budget Office review and finalization of FY23 Budget.
May 6th | Budget documents due to ABOR

## Internal Process Timeline
FY23 Budget Internal Process Timeline
Tuesday, March 1st | Kickoff to communicate position,Local and Sate Budget process guidelines for FY23
Tuesday, March 1st | Position, Local and State Templates available in Anaplan
Tuesday March 15th | Position review and changes finalized for Budget Office review
BUDGET 3/15 - 3/28 | Review position entry, confirm properly budgeted, confirm final list with areas
Tuesday March 29th | Local DeptIDs without UCA funding templates to be completed in Anaplan
BUDGET 3/29 - 4/12 | Review Local DeptIDs without UCA funding and finalize the budgets
Tuesday April 13th | Local DeptIDs with UCA funding and State budget templates completed in Anaplan
BUDGET 4/13 - 4/26 | Review and finalize budgets for Local DeptIDs with UCA funding and State budgets
During this time we will be communicating requests and budget changes in some manner - hoping it might happen earlier in the process, but we will see
Once a Cabinet is finalized, budget staff will meet with them to certifiy their budget
BUDGET | Finalize Materials for ABOR